## Overview
Request for Information Summary
Trade | Planned Equipment Material Approval | Rev0 | [10 empty] | Rev1 | [10 empty] | Rev2
|  | GAA Stats | CTA Stats |  | AUR Stats |  | STT Stats | [5 empty] | GAA Stats |  | CTA Stats |  | AUR Stats |  | STT Stats |  |  |  |  | GAA Stats |  | CTA Stats |  | AUR Stats |  | STT Stats
|  | Total Submission | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C |  | Pending resubmission | Submitted | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C | Pending resubmission | Submitted | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C
Structural | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architectural | 38 | 38 | 37 | 1 | 37 | 1 | 24 | 14 | 1 | 15 | 0 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical | 24 | 24 | 21 | 3 | 12 | 12 | 2 | 22 | 0 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire Protection | 14 | 14 | 14 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hydraulics | 11 | 11 | 11 | 0 | 0 | 11 | 0 | 11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical & Comms | 47 | 47 | 42 | 5 | 18 | 29 | 0 | 47 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall | 135 | 135 | 126 | 9 | 68 | 67 | 26 | 109 | 1 | 17 | 0 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade | Submission | Submitted | Approved by All | Rejected | Pending submission | CTA Approved | CTA Outstanding | AUR Approved | AUR Outstanding | STT Approved | STT outstanding
|  | Structural | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1
|  | Architectural | 38 | 38 | 25 | 0 | 0 | 36 | 2 | 36 | 0 | 24 | 0
|  | AR & ST | 39 | 39 | 25 | 0 | 0 | 37 | 2 | 37 | 0 | 24 | 1
|  | Mechanical | 24 | 21 | 2 | 0 | 0 | 21 | 2 | 12 | 10 | 2 | 0
|  | Fire | 14 | 14 | 0 | 0 | 0 | 14 | 0 | 14 | 14 | 0 | 0
|  | Hydraulics | 11 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 11 | 0 | 0
|  | Electrical & Comms | 47 | 47 | 0 | 0 | 0 | 42 | 5 | 18 | 24 | 0 | 0
|  | Overall | 135 | 132 | 27 | 0 | 0 | 125 | 9 | 81 | 59 | 26 | 1
|  | AR & ST |  | 100% | 64.1% | 0% | 0% | 94.87% | 5.128% | 94.87% | 0% | 61.54% | 2.564%
|  | Mechanical |  | 87.5% | 8.333% | 0% | 0% | 87.5% | 8.333% | 50% | 41.67% | 8.333% | 0%
|  | Fire |  | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 100% | 0% | 0%
|  | Hydraulics |  | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
|  | Electrical & Comms |  | 100% | 0% | 0% | 0% | 89.36% | 10.64% | 38.3% | 51.06% | 0% | 0%
|  | Overall |  | 97.78% | 20% | 0% | 0% | 92.59% | 6.667% | 60% | 43.7% | 19.26% | 0.7407%
Do not tounch

## Summary
Request for Information Summary
Structural
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-26 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-02-02 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-02-09 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-02-16 | 1 | 1 | 1
| 2026-02-23 | 1 | 1 | 1
| 2026-03-02 | 1 | 1 | 1
| 2026-03-09 | 1 | 1 | 1
Architectural
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 38 | 38 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 38 | 38 | 12 | 1 | 0 | 1 | 1 | 9 | 0
| 2026-01-26 | 38 | 38 | 33 | 1 | 0 | 7 | 1 | 24 | 0
| 2026-02-02 | 38 | 38 | 33 | 1 | 0 | 7 | 1 | 24 | 0
| 2026-02-09 | 38 | 38 | 37 | 1 | 0 | 11 | 1 | 24 | 0
| 2026-02-16 | 38 | 38 | 38
| 2026-02-23 | 38 | 38 | 38
| 2026-03-02 | 38 | 38 | 38
| 2026-03-09 | 38 | 38 | 38
Electrical
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 47 | 47 | 17 | 0 | 7 | 10 | 0 | 0 | 0
| 2026-01-26 | 47 | 47 | 30 | 0 | 12 | 18 | 0 | 0 | 0
| 2026-02-02 | 47 | 47 | 37 | 0 | 19 | 18 | 0 | 0 | 0
| 2026-02-09 | 47 | 47 | 40 | 0 | 22 | 18 | 0 | 0 | 0
| 2026-02-16 | 47 | 47 | 47
| 2026-02-23 | 47 | 47 | 47
| 2026-03-02 | 47 | 47 | 47
| 2026-03-09 | 47 | 47 | 47
Mechanical
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 24 | 24 | 5 | 0 | 0 | 4 | 0 | 0 | 0
| 2026-01-19 | 24 | 24 | 8 | 0 | 0 | 6 | 0 | 1 | 0
| 2026-01-26 | 24 | 24 | 15 | 0 | 2 | 8 | 0 | 2 | 0
| 2026-02-02 | 24 | 24 | 19 | 0 | 6 | 8 | 0 | 2 | 0
| 2026-02-09 | 24 | 24 | 22 | 0 | 9 | 8 | 0 | 2 | 0
| 2026-02-16 | 24 | 24 | 24
| 2026-02-23 | 24 | 24 | 24
| 2026-03-02 | 24 | 24 | 24
| 2026-03-09 | 24 | 24 | 24
Fire Protection
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 14 | 14 | 4 | 0 | 4 | 0 | 0 | 0 | 0
| 2026-01-26 | 14 | 14 | 13 | 0 | 13 | 0 | 0 | 0 | 0
| 2026-02-02 | 14 | 14 | 14 | 0 | 14 | 0 | 0 | 0 | 0
| 2026-02-09 | 14 | 14 | 14 | 0 | 14 | 0 | 0 | 0 | 0
| 2026-02-16 | 14 | 14 | 14
| 2026-02-23 | 14 | 14 | 14
| 2026-03-02 | 14 | 14 | 14
| 2026-03-09 | 14 | 14 | 14
Hydraulics
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2025-01-27 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2025-02-03 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 2 | 0
| 2025-02-08 | 4
| 2025-02-17 | 4
| 2025-02-24 | 4
2025-03-03
2025-03-08
2025-03-23
General
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2025-01-27 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 2025-02-03 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 2025-02-08 | 1
| 2025-02-17 | 1
| 2025-02-24 | 1
2025-03-23
Formulas:
w/e = [w/e, row above]+7

## ST (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [10 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[12 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Civil & Structure | 523213-01-RFI-ST-0001 | Request for Additional Steel Manufacturers Approval due to Material Stock Unavailability |  | 2026-02-10 | 2026-02-17 | 0 | STT | Pending |  |  | 2026-02-10 | 2026-02-11 | 2026-02-11
2 | Civil & Structure | 523213-01-RFI-ST-0002
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
x
Formulas:
Consultant Respond Date = [Submission Date]+7

## AR (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [10 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[12 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Architectural | 523213-01-RFI-AR-0001 | Clarification on Mortar Specification |  | 2026-01-12 | 2026-01-19 | 0 | CTA | Pending |  |  | 2026-01-12
2 | Architectural | 523213-01-RFI-AR-0002
3 | Architectural | 523213-01-RFI-AR-0003 | Partition wall or Block Wall HV3 and HV 4 Shaft 2nd Floor |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
4 | Architectural | 523213-01-RFI-AR-0004 | Confirmation for Store Room or EE Riser |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-05 |  | 2026-01-20 | 2026-01-21 | 2026-01-30 | 2026-02-05
5 | Architectural | 523213-01-RFI-AR-0005 | Partition wall or Block wall Chiller 2nd 3rd 4th and 5th FL |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
6 | Architectural | 523213-01-RFI-AR-0006 | Confirmation for Whether the Door Handle is to be Installed on the Right-Hand Side or Left-Hand Side. 2nd Floor |  | 2026-01-20 | 2026-01-27 | 0 | STT | Pending |  |  | 2026-01-20 | 2026-01-30 | 2026-02-05
7 | Architectural | 523213-01-RFI-AR-0007
8 | Architectural | 523213-01-RFI-AR-0008
9 | Architectural | 523213-01-RFI-AR-0009 | Indicate Wall Structure and Wall Finishes Type for Store and ELV. B Room |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
10 | Architectural | 523213-01-RFI-AR-0010 | Indicate Wall Structure and Wall Finishes Type for Batt S2, S3 and EE Room 6th Floor |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
11 | Architectural | 523213-01-RFI-AR-0011 | Indicate Wall Structure and Wall Finishes Type for D22 6th Floor |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
12 | Architectural | 523213-01-RFI-AR-0012 | Clarification on Raised Floor for DB Load Bank Room |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
13 | Architectural | 523213-01-RFI-AR-0013 | Floor Tiles Size, Start Point, Layout and Orientation for Security Room and Reception Hall 1st FL |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-06 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
14 | Architectural | 523213-01-RFI-AR-0014 | C11 Ceiling type Specification |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-04 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
15 | Architectural | 523213-01-RFI-AR-0015 | Confirm Ceiling Type 6th FL (C4 or C10) |  | 2026-01-15 | 2026-01-22 | 0 | Closed | B | 2026-02-04 |  | 2026-01-15 | 2026-01-21 | 2026-01-29 | 2026-02-04 | B
16 | Architectural | 523213-01-RFI-AR-0016 | Generator Set and PAU Rooms Waterproofing Scope |  | 2026-01-20 | 2026-01-27 | 0 | STT | Pending |  |  | 2026-01-20 | 2026-02-05 | 2026-02-06
17 | Architectural | 523213-01-RFI-AR-0017 | Busway Riser or EE Riser 2nd Floor |  | 2026-01-15 | 2026-01-22 | 0 | STT | Pending |  |  | 2026-01-15 | 2026-01-30 | 2026-02-05
18 | Architectural | 523213-01-RFI-AR-0018 | Regarding the alignment of the wall between IFC and TTI model is not the same. Gaa would like to confirm which model we should use? |  | 2026-01-13 | 2026-01-20 | 0 | Closed | B | 2026-02-05 |  | 2026-01-13 | 2026-01-21 | 2026-01-30 | 2026-02-05
19 | Architectural | 523213-01-RFI-AR-0019 | Clarification on Door Frame Depth Considering Different Wall Thicknesses |  | 2026-01-14 | 2026-01-21 | 0 | Closed | B | 2026-02-05 |  | 2026-01-14 | 2026-01-21 | 2026-01-30 | 2026-02-05
20 | Architectural | 523213-01-RFI-AR-0020 | Clarification of Return Air Grills 2nd, 3rd, 4th and 5th Floor |  | 2026-01-15 | 2026-01-22 | 0 | Closed | B | 2026-02-05 |  | 2026-01-15 | 2026-01-21 | 2026-01-30 | 2026-02-05
21 | Architectural | 523213-01-RFI-AR-0021
22 | Architectural | 523213-01-RFI-AR-0022 | Floor Flatness FM2 and Screed Reinforcement details for Data Hall and Related Area |  | 2026-01-17 | 2026-01-24 | 0 | Closed | B | 2026-02-02 |  | 2026-01-17 | 2026-01-22 | 2026-01-26
23 | Architectural | 523213-01-RFI-AR-0023 | Finishing Schedule |  | 2026-01-16 | 2026-01-23 | 0 | Closed | B | 2026-02-05 |  | 2026-01-16 | 2026-01-21 | 2026-01-30 | 2026-02-05
24 | Architectural | 523213-01-RFI-AR-0024 | Confirmation on the Wire Mesh Screen Details at the Fan wall Corridors |  | 2026-01-19 | 2026-01-26 | 0 | Closed | B | 2026-02-05 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 | 2026-02-05
25 | Architectural | 523213-01-RFI-AR-0025 | Confirm for the Final Height of HMI Display from Fan wall unit (FWU) with Respects to Human Ratio |  | 2026-01-19 | 2026-01-26 | 0 | Closed | B | 2026-02-05 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 | 2026-02-05
26 | Architectural | 523213-01-RFI-AR-0026 | Reduce the Thickness of Glass block in the Curve Wall from 12.7 mm. to 10.0 mm. |  | 2026-01-19 | 2026-01-26 | 0 | Closed | B | 2026-02-05 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 | 2026-02-05
27 | Architectural | 523213-01-RFI-AR-0027 | Confirm Colour Code and Type - Semi-Gloss or Matt Type |  | 2026-01-19 | 2026-01-26 | 0 | Closed | A | 2026-02-06 |  | 2026-01-19 | 2026-01-27 | 2026-02-02 | 2026-02-06 | A
28 | Architectural | 523213-01-RFI-AR-0028 | Proposal for Waterproofing Termination Level at RC Curb for F3, F3C and F6 |  | 2026-01-20 | 2026-01-27 | 0 | STT | Pending |  |  | 2026-01-20 | 2026-01-22 | 2026-02-02
29 | Architectural | 523213-01-RFI-AR-0029 | Confirm Colour for Partition Wall Toilet Room 1st to 5th Floor |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-06 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
30 | Architectural | 523213-01-RFI-AR-0030 | Clarify Ceiling Soffit Color for Ceiling Painting |  | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-06 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
31 | Architectural | 523213-01-RFI-AR-0031 | Request Product to Replace SIKA Bituseal-1500SA (Due to Discontinue to Produce) |  | 2026-01-21 | 2026-01-28 | 0 | STT | Pending |  |  | 2026-01-21 | 2026-02-05 | 2026-02-06
32 | Architectural | 523213-01-RFI-AR-0032 | Confirm the Correct Floor Finishes for ID Works 1st-ID Works and 2nd to 5th Toilet |  | 2026-01-21 | 2026-01-28 | 0 | Closed | B | 2026-02-06 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
33 | Architectural | 523213-01-RFI-AR-0033 | Confirm the Correct Ceiling Finishes for ID Works 1st to 5th Floor |  | 2026-01-21 | 2026-01-28 | 0 | Closed | B | 2026-02-06 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
34 | Architectural | 523213-01-RFI-AR-0034 | Clarify the C2 T-Bar Ceiling and Specify the Colour |  | 2026-01-21 | 2026-01-28 | 0 | Closed | B | 2026-02-06 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
35 | Architectural | 523213-01-RFI-AR-0035 | Confirming the Tile Type from the catalog SE206 is a Carpet Tile |  | 2026-01-21 | 2026-01-28 | 0 | STT | Pending |  |  | 2026-01-21 | 2026-01-30 | 2026-02-04
36 | Architectural | 523213-01-RFI-AR-0036 | Request for Tile Grout Specification and Colour Schemes for BKK2 |  | 2026-01-23 | 2026-01-30 | 0 | STT | Pending |  |  | 2026-01-23 | 2026-01-30 | 2026-02-04
35 | Architectural | 523213-01-RFI-AR-0037 | Confirm to Change Weberdry S3000S to Proofex GPE due to Discontinued Product |  | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 |  | 2026-01-23 | 2026-01-30 | 2026-02-04 | 2026-02-06 | B
36 | Architectural | 523213-01-RFI-AR-0038 | Change of Ceiling Panel Specification from Gypsum Board to Metal Pan Ceiling Board |  | 2026-02-11 | 2026-02-18 | 1 | CTA | Pending |  |  | 2026-02-03 | 2026-02-05 | 2026-02-06 |  |  | 2026-02-11
37 | Architectural | 523213-01-RFI-AR-0039 | Change Laminated Color due to Discontinued Product |  | 2026-02-03 | 2026-02-10 | 0 | STT | Pending |  |  | 2026-02-03 | 2026-02-05 | 2026-02-06
36 | Architectural | 523213-01-RFI-AR-0040 | Confirm to Install Ceiling Side Guard 2nd to 5th FL |  | 2026-02-04 | 2026-02-11 | 0 | STT | Pending |  |  | 2026-02-04 | 2026-02-07 | 2026-02-09
37 | Architectural | 523213-01-RFI-AR-0041 | Confirm External Paint Color and Technical Specification for Generators Room |  | 2026-02-06 | 2026-02-13 | 0 | STT | Pending |  |  | 2026-02-06 | 2026-02-09 | 2026-02-10
38 | Architectural | 523213-01-RFI-AR-0042 | Clarify Ceiling Types for Level 5 Battery Room B1,B2,C1,C2,D1 & D2 Areas. |  | 2026-02-06 | 2026-02-13 | 0 | STT | Pending |  |  | 2026-02-06 | 2026-02-09 | 2026-02-10
37 | Architectural | 523213-01-RFI-AR-0043
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
GAA = [Submission Date]

## EL (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [11 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Procurement | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[13 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Electrical | 523213-01-RFI-EL-0001 | Aux Supply Non-IT UPS for LVSB,OUSB,MSSB and ATS |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-10
2 | Electrical | 523213-01-RFI-EL-0002 | Pre-Action System for Comm Riser |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-09
3 | Electrical | 523213-01-RFI-EL-0003 | Use Local Switch or Remote Switch 2nd to 6th FL R0 |  | 2026-01-15 | 2026-01-22 | 0 |  | AUR | Pending |  |  | 2026-01-15 | 2026-02-02
4 | Electrical | 523213-01-RFI-EL-0004 | Shut down Exhaust Fan |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-01-22 | 2026-01-27
5 | Electrical | 523213-01-RFI-EL-0005 | Detector of Toilet for Fire Alarm System (Heat or Smoke?) for all Floor |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-03
6 | Electrical | 523213-01-RFI-EL-0006 | Detector of Toilet for Fire Alarm System & Fire Alarm System |  | 2026-01-15 | 2026-01-22 | 0 |  | AUR | Pending |  |  | 2026-01-15 | 2026-02-02
7 | Electrical | 523213-01-RFI-EL-0007 | Fire Alarm System Interface with Mechanical Equipment |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-01-22 | 2026-01-27
8 | Electrical | 523213-01-RFI-EL-0008 | Confirm the amount of Monitor and Control Module - Fire Alarm System |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-02-02 | 2026-02-09
9 | Electrical | 523213-01-RFI-EL-0009 | Quantity of Smoke Detector is not equal in Fan Wall A and B on 5th FL, Speaker 4th FL and Speaker L2 2nd FL |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-03
10 | Electrical | 523213-01-RFI-EL-0010
11 | Electrical | 523213-01-RFI-EL-0011 | Add & Remove Cable Ladder from HVSB to HV Riser |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-09
12 | Electrical | 523213-01-RFI-EL-0012 | Incoming HV Cable Route Problem |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-01-22 | 2026-01-28
13 | Electrical | 523213-01-RFI-EL-0013 | Need PIR for Security Room 2, Janitor, Storage and Work Shop - Lighting Control System |  | 2026-01-15 | 2026-01-22 | 0 |  | AUR | Pending |  |  | 2026-01-15 | 2026-02-02
14 | Electrical | 523213-01-RFI-EL-0014 | Confirm for Additional Power Supply for GDP |  | 2026-01-15 | 2026-01-22 | 0 |  | AUR | Pending |  |  | 2026-01-15 | 2026-02-02
15 | Electrical | 523213-01-RFI-EL-0015 | Clarification on Fire Alarm Module Type for Sysem Interface |  | 2026-01-15 | 2026-01-22 | 0 |  | STT | Pending |  |  | 2026-01-15 | 2026-02-02 | 2026-02-09
16 | Electrical | 523213-01-RFI-EL-0016 | Aux supply Non-IT DB for HVSB,TX and LB |  | 2026-01-15 | 2026-01-22 | 0 |  | AUR | Pending |  |  | 2026-01-15 | 2026-02-02
17 | Electrical | 523213-01-RFI-EL-0017 | Confirm to Add Power Supply for ASD - Staging Room 1st Floor |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-02-02 | 2026-02-09
18 | Electrical | 523213-01-RFI-EL-0018 | Confirm the Correct ASD Pipe Installation Location in Data Hall Area |  | 2026-01-14 | 2026-01-21 | 0 |  | STT | Pending |  |  | 2026-01-14 | 2026-02-02 | 2026-02-03
19 | Electrical | 523213-01-RFI-EL-0019 | Detail Location for Install CCTV at Outside Building |  | 2026-01-14 | 2026-01-21 | 0 |  | STT | Pending |  |  | 2026-01-14 | 2026-02-02 | 2026-02-09
20 | Electrical | 523213-01-RFI-EL-0020 | Quantity and Installation Locations of PIR Sensors for the Stairs |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-02
21 | Electrical | 523213-01-RFI-EL-0021 | Confirm for Power Supply for LV System |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-02
22 | Electrical | 523213-01-RFI-EL-0022 | Confirm Fire Alarm and ASD Interface |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-01-22 | 2026-01-27
23 | Electrical | 523213-01-RFI-EL-0023 | Fire Alarm Signals Interface to BMS System |  | 2026-01-22 | 2026-01-29 | 0 |  | STT | Pending |  |  | 2026-01-22 | 2026-02-02 | 2026-02-09
24 | Electrical | 523213-01-RFI-EL-0024 | Module (Control Module) for Fire Telephone of Staircases 1st FL |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-01-22 | 2026-01-27
25 | Electrical | 523213-01-RFI-EL-0025 | Scope of Earth Ground Bar and Cable for Fuel Fill Cabinet |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-03
26 | Electrical | 523213-01-RFI-EL-0026 | Electrical Routing at 2nd Floor Confirmation |  | 2026-01-17 | 2026-01-24 | 0 |  | AUR | Pending |  |  | 2026-01-17 | 2026-02-03
27 | Electrical | 523213-01-RFI-EL-0027 | Confirm to add Lamp type&room in Luminaire Schedule and PIR for Sensor 1st and 5th FL |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-03
28 | Electrical | 523213-01-RFI-EL-0028 | UDB and LCP Panels Relocation on 2nd Floor |  | 2026-01-17 | 2026-01-24 | 0 |  | AUR | Pending |  |  | 2026-01-17 | 2026-02-03
29 | Electrical | 523213-01-RFI-EL-0029 | Add Junction Box for Phase 1 on 3rd, 4th and 5th Floor for Convenience for Tie-In in the Future Phase |  | 2026-01-17 | 2026-01-24 | 0 |  | STT | Pending |  |  | 2026-01-17 | 2026-02-03 | 2026-02-09
30 | Electrical | 523213-01-RFI-EL-0030 | Relay of Lighting Control at 2nd floor Confirmation |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-03
31 | Electrical | 523213-01-RFI-EL-0031 | Lighting Circuit at Garbage and Janitor Rooms, 1st Floor - Supply from Source B Only |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-03
32 | Electrical | 523213-01-RFI-EL-0032 | Confirm Phase of TH-BKK02-02-06-LVSB-002-S1 on 6th Floor (Phase 1 or Phase 2) |  | 2026-01-20 | 2026-01-27 | 0 |  | STT | Pending |  |  | 2026-01-20 | 2026-02-03 | 2026-02-09
33 | Electrical | 523213-01-RFI-EL-0033 | Confirmation on Identification of Relay Numbers Lighting System Roof Floor |  | 2026-01-29 | 2026-02-05 | 0 |  | AUR | Pending |  |  | 2026-01-29 | 2026-02-06
34 | Electrical | 523213-01-RFI-EL-0034 | Confirmation on Power Supply for TH-BKK2-02-01-EAF-007 and 008 1st FL |  | 2026-01-29 | 2026-02-05 | 0 |  | AUR | Pending |  |  | 2026-01-29 | 2026-02-11
35 | Electrical | 523213-01-RFI-EL-0035 | Requirement for PIR Sensor for lighting L1 Type 2nd to 6th FL |  | 2026-01-29 | 2026-02-05 | 0 |  | AUR | Pending |  |  | 2026-01-29 | 2026-02-11
36 | Electrical | 523213-01-RFI-EL-0036
37 | Electrical | 523213-01-RFI-EL-0037 | Tag Confirmation for Electrical Panel 1st to Roof FL |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-07
38 | Electrical | 523213-01-RFI-EL-0038 | Connection for Fire Alarm Phase 1 on 3rd FL system |  | 2026-01-29 | 2026-02-05 | 0 |  | AUR | Pending |  |  | 2026-01-29 | 2026-02-11
39 | Electrical | 523213-01-RFI-EL-0039
40 | Electrical | 523213-01-RFI-EL-0040
41 | Electrical | 523213-01-RFI-EL-0041 | Clarification on Scope of Work for Plug-in Units and Sub Main Cables |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-11
42 | Electrical | 523213-01-RFI-EL-0042
43 | Electrical | 523213-01-RFI-EL-0043 | Confirmation for NSCP interface with BMS as - HHI or LLI? |  | 2026-02-06 | 2026-02-13 | 0 |  | AUR | Pending |  |  | 2026-02-06 | 2026-02-07
43 | Electrical | 523213-01-RFI-EL-0044 | Clarification of Heat Detector for Genset Room Fire Alarm System |  | 2026-02-04 | 2026-02-11 | 0 |  | AUR | Pending |  |  | 2026-02-04 | 2026-02-11
42 | Electrical | 523213-01-RFI-EL-0045 | Confirm to use Steel Plint for all LV Switch Board as same as Phase 4 and 5. |  | 2026-02-06 | 2026-02-13 | 0 |  | AUR | Pending |  |  | 2026-02-06 | 2026-02-07
44 | Electrical | 523213-01-RFI-EL-0046 | Confirm of Interface Method for Tap-off Unit (Non-IT) : HLI or LLI? |  | 2026-02-10 | 2026-02-17 | 0 |  | AUR | Pending |  |  | 2026-02-10 | 2026-02-11
44 | Electrical | 523213-01-RFI-EL-0047 | Confirm Switch Control for Lighting System 1st FL (Entrance, Reception, Lift Lobby and Sec. Room 2) |  | 2026-02-10 | 2026-02-17 | 0 |  | AUR | Pending |  |  | 2026-02-10 | 2026-02-11
45 | Electrical | 523213-01-RFI-EL-0048 | Cable trays obstruct a spare space of FWU |  | 2026-02-11 | 2026-02-18 | 0 |  | CTA | Pending |  |  | 2026-02-11
43 | Electrical | 523213-01-RFI-EL-0049 | Confirm Supply source for junction boxes in shower room (1st floor) |  | 2026-02-11 | 2026-02-18 | 0 |  | CTA | Pending |  |  | 2026-02-11
46 | Electrical | 523213-01-RFI-EL-0050 | Clarification on BMS Monitoring Points for IG-100 Fire Suppression System |  | 2026-02-11 | 2026-02-18 | 0 |  | CTA | Pending |  |  | 2026-02-11
45 | Electrical | 523213-01-RFI-EL-0051 | Clarification on PACP Low-Level Interface (Hardwired) Point List Requirements |  | 2026-02-11 | 2026-02-18 | 0 |  | CTA | Pending |  |  | 2026-02-11
47 | Electrical | 523213-01-RFI-EL-0052 | Confirmation for MV Cable Ladder Color Coding |  | 2026-02-11 | 2026-02-18 | 0 |  | CTA | Pending |  |  | 2026-02-11
44 | Electrical | 523213-01-RFI-EL-0053
48 | Electrical | 523213-01-RFI-EL-0054
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
GAA = [Submission Date]

## FI (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [11 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Procurement | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[13 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Fire Protection | 523213-01-RFI-FI-0001 | Request for Information - IG 100 or Wet Sprinkler for HV UG Entry Room 1st FL |  | 2026-01-22 | 2026-01-29 | 0 |  | AUR | Pending |  |  | 2026-01-22 | 2026-02-06
2 | Fire Protection | 523213-01-RFI-FI-0002 | Symbol to use with Jockey Pump |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-02-06
2 | Fire Protection | 523213-01-RFI-FI-0003 | Name of Data Hall (1, 2, 3 or A, B, C ) |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-02-06
3 | Fire Protection | 523213-01-RFI-FI-0004 | Sprinkler Corridor 1st FL is Fit Out |  | 2026-01-22 | 2026-01-29 | 0 |  | AUR | Pending |  |  | 2026-01-22 | 2026-02-09
3 | Fire Protection | 523213-01-RFI-FI-0005 | Confirm the Location of Fire Hose Cabinet 1st |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-02-06
4 | Fire Protection | 523213-01-RFI-FI-0006 | Needed Installation Detail of Fire Hose Cabinet in Pump Room |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-02-06
4 | Fire Protection | 523213-01-RFI-FI-0007 | Confirm The Main Pipe Size |  | 2026-01-22 | 2026-01-29 | 0 |  | AUR | Pending |  |  | 2026-01-22 | 2026-01-22
5 | Fire Protection | 523213-01-RFI-FI-0008 | Confirmation of Nitrogen Suppression System for MDF A & ELV A and MDF B & ELV B (Level 2) |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-06
5 | Fire Protection | 523213-01-RFI-FI-0009 | Confirmation of Butterfly Valve with Supervisory Switch Status Indication to Fire Alarm System |  | 2026-01-22 | 2026-01-29 | 0 |  | AUR | Pending |  |  | 2026-01-22 | 2026-02-06
6 | Fire Protection | 523213-01-RFI-FI-0010 | Confirm the details of the first and second horn tones activation in the Nitrogen Suppression System |  | 2026-01-22 | 2026-01-29 | 0 |  | AUR | Pending |  |  | 2026-01-22 | 2026-02-09
6 | Fire Protection | 523213-01-RFI-FI-0011 | Confirmation of the Details of the Activation of the LED Indication R0 |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
7 | Fire Protection | 523213-01-RFI-FI-0012 | Confirmation of the Details of the First and Second Horn Tones Activation |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
7 | Fire Protection | 523213-01-RFI-FI-0013 | Confirmation of the Details of the Strobe Light & Second Horn Activated for all Genset to the Pre Action System |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
8 | Fire Protection | 523213-01-RFI-FI-0014 | Confirmation of 2-Layer Silent Nozzle – IG-100 System due to height more than 5 m. 2nd-6th FL |  | 2026-01-29 | 2026-02-05 | 0 |  | AUR | Pending |  |  | 2026-01-29 | 2026-02-09
8 | Fire Protection | 523213-01-RFI-FI-0015
9 | Fire Protection | 523213-01-RFI-FI-0016
9 | Fire Protection | 523213-01-RFI-FI-0017
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
GAA = [Submission Date]

## ME (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [11 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Procurement | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[13 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Mechanical | 523213-01-RFI-ME-0001 | FCU Fan Type |  | 2026-01-16 | 2026-01-23 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-01-22 | 2026-02-10
2 | Mechanical | 523213-01-RFI-ME-0002 | Gas Purging Fan Tag Number is 02-01-GPF-002 or 02-02-GPF-002 for 2nd FL |  | 2026-01-20 | 2026-01-27 | 0 |  | CTA | CANCEL |  |  | 2026-01-20
3 | Mechanical | 523213-01-RFI-ME-0003 | Correct reference of the Supply Air of FCU 2nd FL (No. 001 to 012) |  | 2026-01-16 | 2026-01-23 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-01-22 | 2026-02-10
4 | Mechanical | 523213-01-RFI-ME-0004 | CCU is not Equipped with a motorized Damper? 2nd - 4th FL |  | 2026-01-16 | 2026-01-23 | 0 |  | Closed | B | 2026-01-27 |  | 2026-01-12 | 2026-01-21 | 2026-01-27 | 2026-01-27 | B
5 | Mechanical | 523213-01-RFI-ME-0005 | MEP Pipe at 2.1m. conflict with door height 2.8 meters 1st Floor |  | 2026-01-21 | 2026-01-28 | 0 |  | Closed | B | 2026-01-29 |  | 2026-01-21 | 2026-01-26 | 2026-01-28 | 2026-01-29 | B
6 | Mechanical | 523213-01-RFI-ME-0006 | Cooling Coil amount and type for PAHU 1st & Roof FL |  | 2026-01-12 | 2026-01-19 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-02-09 | 2026-02-10
7 | Mechanical | 523213-01-RFI-ME-0007 | PAHU Supply Air Conflict 1st FL |  | 2026-01-12 | 2026-01-19 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-01-22 | 2026-02-10
8 | Mechanical | 523213-01-RFI-ME-0008 | Add Isolation Valve and Check Valve for DRG-ME-0103, 0104 and 0105 |  | 2026-01-12 | 2026-01-19 | 0 |  | STT | CANCEL |  |  | 2026-01-12 | 2026-01-22 | 2026-02-10
9 | Mechanical | 523213-01-RFI-ME-0009 | Add Isolation Valves for 4th &5 th FL |  | 2026-01-22 | 2026-01-29 | 0 |  | STT | CANCEL |  |  | 2026-01-22 |  | 2026-02-10
10 | Mechanical | 523213-01-RFI-ME-0010 | Change CVV Cable from 2C-1.5 mm2 to 4C-1.5 mm2 in MCC Panel for DRG-ME-8000, 8001, 8002, 8003 |  | 2026-01-22 | 2026-01-29 | 0 |  | STT | Pending |  |  | 2026-01-22 | 2026-02-09 | 2026-02-10
11 | Mechanical | 523213-01-RFI-ME-0011 | Power Supply and cable size from MCC Panel in Drawing 523213-02-DRG-ME-0201 |  | 2026-01-12 | 2026-01-19 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-02-09 | 2026-02-10
12 | Mechanical | 523213-01-RFI-ME-0012 | DP Sensor for Fan Wall at DATA HALL is Required |  | 2026-01-22 | 2026-01-29 | 0 |  | STT | Pending |  |  | 2026-01-22 | 2026-02-09 | 2026-02-10
13 | Mechanical | 523213-01-RFI-ME-0013 | Verify position for 02-01-EAF-019 |  | 2026-01-12 | 2026-01-19 | 0 |  | STT | Pending |  |  | 2026-01-12 | 2026-02-09 | 2026-02-10
14 | Mechanical | 523213-01-RFI-ME-0014 | Pressure Gauge for ACMV Riser Needed? |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-11
15 | Mechanical | 523213-01-RFI-ME-0015 | Confirm Temp/Hum. amount In LV Room A and B 2nd Floor.(Total 4 or 6 set) 2nd FL |  | 2026-01-27 | 2026-02-03 | 0 |  | AUR | Pending |  |  | 2026-01-27 | 2026-02-09
16 | Mechanical | 523213-01-RFI-ME-0016 | Confirm for Fresh Air Fan for TH-BKK2-02-01-FAF-005 N2 Cylinder Room 1st Floor |  | 2026-01-23 | 2026-01-30 | 0 |  | AUR | Pending |  |  | 2026-01-23 | 2026-02-09
17 | Mechanical | 523213-01-RFI-ME-0017 | Please Confirm the Power Supply for the Motorized Damper 2nd to 6th FL |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-09
18 | Mechanical | 523213-01-RFI-ME-0018 | Confirmation of Harmonic Filter Type (AHF) |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-11
19 | Mechanical | 523213-01-RFI-ME-0019 | FCU as the Spec (HH-D Double Skin) Sizing too Big. It Can't Install in Room - 02-02-FCU-001&002 2nd FL |  | 2026-01-31 | 2026-02-07 | 0 |  | AUR | Pending |  |  | 2026-01-31 | 2026-02-11
20 | Mechanical | 523213-01-RFI-ME-0020 | Confirm PRD at 5th FL (for TX LV MSB 3, UPS Room A, B, C and D) |  | 2026-02-06 | 2026-02-13 | 0 |  | AUR | Pending |  |  | 2026-02-06 | 2026-02-11
21 | Mechanical | 523213-01-RFI-ME-0021 | Confirm Air Flow Value for TH-BKK2-02-01-FAF-001 and 002 1st FL |  | 2026-02-06 | 2026-02-13 | 0 |  | AUR | Pending |  |  | 2026-02-06 | 2026-02-11
22 | Mechanical | 523213-01-RFI-ME-0022 | Need Slab to Beam Height 4.1 m for Installing DUCT at PAU Room Roof FL (Currently h=2.6m.) |  | 2026-02-06 | 2026-02-13 | 0 |  | AUR | Pending |  |  | 2026-02-06 | 2026-02-11
23 | Mechanical | 523213-01-RFI-ME-0023 | Confirm weather TH-BKK2-02-06-CH-001, 002 and 003 are provided with MDV or not? |  | 2026-02-10 | 2026-02-17 | 0 |  | AUR | Pending |  |  | 2026-02-10 | 2026-02-11
24 | Mechanical | 523213-01-RFI-ME-0024 | Confirm whether the FCU power supply requirement is 3 Phase or Single Phase on DRG-ME-0203 |  | 2026-02-10 | 2026-02-17 | 0 |  | CTA | Pending |  |  | 2026-02-10
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
GAA = [Submission Date]
Note on P11: Panjarin Insuan: ส่งเมลยกเลิกไป 23/1
Note on P12: Panjarin Insuan: ส่งเมลยกเลิกไป 23/1

## HY (hidden)
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [11 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Doc Ref No. | Document Description | Planned Date | Submission Date | Consultant Respond Date | Rev | Procurement | Action | Status | Approval Date | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2
[13 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Hydraulics | 523213-01-RFI-HY-0001 | Water Meter Type for Toilet Room |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
2 | Hydraulics | 523213-01-RFI-HY-0002 | Confirm fit Out Scope |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
2 | Hydraulics | 523213-01-RFI-HY-0003 | Confirm Sewage Submersible Pump Control Panel Scope |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
3 | Hydraulics | 523213-01-RFI-HY-0004 | Propose to use 20 Inched BSP SCh20 for Generator Exhaust Pipe |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-01-22
3 | Hydraulics | 523213-01-RFI-HY-0005 | Confirm to Connect with MWA by Existing Pipe or not |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
4 | Hydraulics | 523213-01-RFI-HY-0006 | Confirm to Install Digital Water Meter at Softener Drain Line |  | 2026-01-20 | 2026-01-27 | 0 |  | AUR | Pending |  |  | 2026-01-20 | 2026-02-09
4 | Hydraulics | 523213-01-RFI-HY-0007 | Confirm Generator Exhaust Pipe (Head Type) |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-01-22
5 | Hydraulics | 523213-01-RFI-HY-0008 | Details of the FUS-A and FUS-B pipelines for the day tank |  | 2026-01-14 | 2026-01-21 | 0 |  | AUR | Pending |  |  | 2026-01-14 | 2026-02-09
5 | Hydraulics | 523213-01-RFI-HY-0009 | Confirm whether flow meters are required for the FOU-A and FOU-B drain lines |  | 2026-02-10 | 2026-02-17 | 0 |  | AUR | Pending |  |  | 2026-02-10 | 2026-02-11
6 | Hydraulics | 523213-01-RFI-HY-0010 | Confirmation of Gate Valve Installation Details for FUS-A, FUS-B, FUO-A, FUO-B and FUPSL Lines at Pump Room |  | 2026-01-19 | 2026-01-26 | 0 |  | AUR | Pending |  |  | 2026-01-19 | 2026-02-09
7 | Hydraulics | 523213-01-RFI-HY-0011 | Clarification on Fuel Consumption Meter (FCM) Intent |  | 2026-01-27 | 2026-02-03 | 0 |  | AUR | Pending |  |  | 2026-01-27 | 2026-02-09
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
GAA = [Submission Date]

## Priority
| Trade | Doc Ref No. | Document Description | Rev | Plan Date | Actual Submission Date | Approval Date |  |  | Action By | Delays Date | Approved Status | Priority | Needed
[7 empty] | CTA | AUR | STT
[5 empty] | *Put only this | dd/mm/yy
1 | Architectural | 523213-01-RFI-AR-0001 | Clarification on Mortar Specification | 0 |  | 2026-01-12 |  |  |  | CTA | 30 | Pending | Overdue | Urgent
2 | Architectural | 523213-01-RFI-AR-0002 | 0 | [6 empty] | 0 | #N/A | 0
3 | Architectural | 523213-01-RFI-AR-0003 | Partition wall or Block Wall HV3 and HV 4 Shaft 2nd Floor | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
4 | Architectural | 523213-01-RFI-AR-0004 | Confirmation for Store Room or EE Riser | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
5 | Architectural | 523213-01-RFI-AR-0005 | Partition wall or Block wall Chiller 2nd 3rd 4th and 5th FL | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
6 | Architectural | 523213-01-RFI-AR-0006 | Confirmation for Whether the Door Handle is to be Installed on the Right-Hand Side or Left-Hand Side. 2nd Floor | 0 |  | 2026-01-20 | 2026-01-30 | 2026-02-05 |  | STT | 6 | Pending | Overdue
7 | Architectural | 523213-01-RFI-AR-0007 | 0 | [6 empty] | 0 | #N/A | 0
8 | Architectural | 523213-01-RFI-AR-0008 | 0 | [6 empty] | 0 | #N/A | 0
9 | Architectural | 523213-01-RFI-AR-0009 | Indicate Wall Structure and Wall Finishes Type for Store and ELV. B Room | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
10 | Architectural | 523213-01-RFI-AR-0010 | Indicate Wall Structure and Wall Finishes Type for Batt S2, S3 and EE Room 6th Floor | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
11 | Architectural | 523213-01-RFI-AR-0011 | Indicate Wall Structure and Wall Finishes Type for D22 6th Floor | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
12 | Architectural | 523213-01-RFI-AR-0012 | Clarification on Raised Floor for DB Load Bank Room | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
13 | Architectural | 523213-01-RFI-AR-0013 | Floor Tiles Size, Start Point, Layout and Orientation for Security Room and Reception Hall 1st FL | 0 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
14 | Architectural | 523213-01-RFI-AR-0014 | C11 Ceiling type Specification | 0 |  | 2026-01-20 | 2026-01-21 | 2026-01-29 | B | Closed |  | B
15 | Architectural | 523213-01-RFI-AR-0015 | Confirm Ceiling Type 6th FL (C4 or C10) | 0 |  | 2026-01-15 | 2026-01-21 | 2026-01-29 | B | Closed |  | B |  | Urgent
16 | Architectural | 523213-01-RFI-AR-0016 | Generator Set and PAU Rooms Waterproofing Scope | 0 |  | 2026-01-20 | 2026-02-05 | 2026-02-06 |  | STT | 5 | Pending | Overdue
17 | Architectural | 523213-01-RFI-AR-0017 | Busway Riser or EE Riser 2nd Floor | 0 |  | 2026-01-15 | 2026-01-30 | 2026-02-05 |  | STT | 6 | Pending | Overdue
18 | Architectural | 523213-01-RFI-AR-0018 | Regarding the alignment of the wall between IFC and TTI model is not the same. Gaa would like to confirm which model we should use? | 0 |  | 2026-01-13 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
19 | Architectural | 523213-01-RFI-AR-0019 | Clarification on Door Frame Depth Considering Different Wall Thicknesses | 0 |  | 2026-01-14 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
20 | Architectural | 523213-01-RFI-AR-0020 | Clarification of Return Air Grills 2nd, 3rd, 4th and 5th Floor | 0 |  | 2026-01-15 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
21 | Architectural | 523213-01-RFI-AR-0021 | 0 | [6 empty] | 0 | #N/A | 0
22 | Architectural | 523213-01-RFI-AR-0022 | Floor Flatness FM2 and Screed Reinforcement details for Data Hall and Related Area | 0 |  | 2026-01-17 | 2026-01-22 | 2026-01-26 |  | Closed |  | B |  | Urgent
23 | Architectural | 523213-01-RFI-AR-0023 | Finishing Schedule | 0 |  | 2026-01-16 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
24 | Architectural | 523213-01-RFI-AR-0024 | Confirmation on the Wire Mesh Screen Details at the Fan wall Corridors | 0 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
25 | Architectural | 523213-01-RFI-AR-0025 | Confirm for the Final Height of HMI Display from Fan wall unit (FWU) with Respects to Human Ratio | 0 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
26 | Architectural | 523213-01-RFI-AR-0026 | Reduce the Thickness of Glass block in the Curve Wall from 12.7 mm. to 10.0 mm. | 0 |  | 2026-01-19 | 2026-01-21 | 2026-01-30 |  | Closed |  | B
27 | Architectural | 523213-01-RFI-AR-0027 | Confirm Colour Code and Type - Semi-Gloss or Matt Type | 0 |  | 2026-01-19 | 2026-01-27 | 2026-02-02 | A | Closed |  | A
28 | Architectural | 523213-01-RFI-AR-0028 | Proposal for Waterproofing Termination Level at RC Curb for F3, F3C and F6 | 0 |  | 2026-01-20 | 2026-01-22 | 2026-02-02 |  | STT | 9 | Pending | Overdue | Urgent
29 | Architectural | 523213-01-RFI-AR-0029 | Confirm Colour for Partition Wall Toilet Room 1st to 5th Floor | 0 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
30 | Architectural | 523213-01-RFI-AR-0030 | Clarify Ceiling Soffit Color for Ceiling Painting | 0 |  | 2026-01-20 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
31 | Architectural | 523213-01-RFI-AR-0031 | Request Product to Replace SIKA Bituseal-1500SA (Due to Discontinue to Produce) | 0 |  | 2026-01-21 | 2026-02-05 | 2026-02-06 |  | STT | 5 | Pending | Overdue
32 | Architectural | 523213-01-RFI-AR-0032 | Confirm the Correct Floor Finishes for ID Works 1st-ID Works and 2nd to 5th Toilet | 0 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
33 | Architectural | 523213-01-RFI-AR-0033 | Confirm the Correct Ceiling Finishes for ID Works 1st to 5th Floor | 0 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
34 | Architectural | 523213-01-RFI-AR-0034 | Clarify the C2 T-Bar Ceiling and Specify the Colour | 0 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
35 | Architectural | 523213-01-RFI-AR-0035 | Confirming the Tile Type from the catalog SE206 is a Carpet Tile | 0 |  | 2026-01-21 | 2026-01-30 | 2026-02-04 |  | STT | 7 | Pending | Overdue
36 | Architectural | 523213-01-RFI-AR-0036 | Request for Tile Grout Specification and Colour Schemes for BKK2 | 0 |  | 2026-01-23 | 2026-01-30 | 2026-02-04 |  | STT | 7 | Pending | Overdue
37 | Architectural | 523213-01-RFI-AR-0037 | Confirm to Change Weberdry S3000S to Proofex GPE due to Discontinued Product | 0 |  | 2026-01-23 | 2026-01-30 | 2026-02-04 | B | Closed |  | B
38 | Architectural | 523213-01-RFI-AR-0038 | Change of Ceiling Panel Specification from Gypsum Board to Metal Pan Ceiling Board | 1 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
39 | Architectural | 523213-01-RFI-AR-0039 | Change Laminated Color due to Discontinued Product | 0 |  | 2026-02-03 | 2026-02-05 | 2026-02-06 |  | STT | 5 | Pending | Overdue
40 | Architectural | 523213-01-RFI-AR-0040 | Confirm to Install Ceiling Side Guard 2nd to 5th FL | 0 |  | 2026-02-04 | 2026-02-07 | 2026-02-09 |  | STT | 2 | Pending
41 | Architectural | 523213-01-RFI-AR-0041 | Confirm External Paint Color and Technical Specification for Generators Room | 0 |  | 2026-02-06 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
42 | Architectural | 523213-01-RFI-AR-0042 | Clarify Ceiling Types for Level 5 Battery Room B1,B2,C1,C2,D1 & D2 Areas. | 0 |  | 2026-02-06 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
43 | Architectural | 523213-01-RFI-AR-0043 | 0 | [6 empty] | 0 | #N/A | 0
44 | Architectural | 523213-01-RFI-AR-0044 | #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ELECTRICAL |  |  |  |  | *Put only this
1 | Electrical | 523213-01-RFI-EL-0001 | Aux Supply Non-IT UPS for LVSB,OUSB,MSSB and ATS | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-10 |  | STT | 1 | Pending
2 | Electrical | 523213-01-RFI-EL-0002 | Pre-Action System for Comm Riser | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
3 | Electrical | 523213-01-RFI-EL-0003 | Use Local Switch or Remote Switch 2nd to 6th FL R0 | 0 |  | 2026-01-15 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
4 | Electrical | 523213-01-RFI-EL-0004 | Shut down Exhaust Fan | 0 |  | 2026-01-20 | 2026-01-22 | 2026-01-27 |  | STT | 15 | Pending | Overdue | Urgent
5 | Electrical | 523213-01-RFI-EL-0005 | Detector of Toilet for Fire Alarm System (Heat or Smoke?) for all Floor | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-03 |  | STT | 8 | Pending | Overdue
6 | Electrical | 523213-01-RFI-EL-0006 | Detector of Toilet for Fire Alarm System & Fire Alarm System | 0 |  | 2026-01-15 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
7 | Electrical | 523213-01-RFI-EL-0007 | Fire Alarm System Interface with Mechanical Equipment | 0 |  | 2026-01-20 | 2026-01-22 | 2026-01-27 |  | STT | 15 | Pending | Overdue | Urgent
8 | Electrical | 523213-01-RFI-EL-0008 | Confirm the amount of Monitor and Control Module - Fire Alarm System | 0 |  | 2026-01-20 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
9 | Electrical | 523213-01-RFI-EL-0009 | Quantity of Smoke Detector is not equal in Fan Wall A and B on 5th FL, Speaker 4th FL and Speaker L2 2nd FL | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-03 |  | STT | 8 | Pending | Overdue
10 | Electrical | 523213-01-RFI-EL-0010 | 0 | [6 empty] | 0 | #N/A | 0
11 | Electrical | 523213-01-RFI-EL-0011 | Add & Remove Cable Ladder from HVSB to HV Riser | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
12 | Electrical | 523213-01-RFI-EL-0012 | Incoming HV Cable Route Problem | 0 |  | 2026-01-15 | 2026-01-22 | 2026-01-28 |  | STT | 14 | Pending | Overdue | Urgent
13 | Electrical | 523213-01-RFI-EL-0013 | Need PIR for Security Room 2, Janitor, Storage and Work Shop - Lighting Control System | 0 |  | 2026-01-15 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
14 | Electrical | 523213-01-RFI-EL-0014 | Confirm for Additional Power Supply for GDP | 0 |  | 2026-01-15 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
15 | Electrical | 523213-01-RFI-EL-0015 | Clarification on Fire Alarm Module Type for Sysem Interface | 0 |  | 2026-01-15 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
16 | Electrical | 523213-01-RFI-EL-0016 | Aux supply Non-IT DB for HVSB,TX and LB | 0 |  | 2026-01-15 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
17 | Electrical | 523213-01-RFI-EL-0017 | Confirm to Add Power Supply for ASD - Staging Room 1st Floor | 0 |  | 2026-01-20 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
18 | Electrical | 523213-01-RFI-EL-0018 | Confirm the Correct ASD Pipe Installation Location in Data Hall Area | 0 |  | 2026-01-14 | 2026-02-02 | 2026-02-03 |  | STT | 8 | Pending | Overdue
19 | Electrical | 523213-01-RFI-EL-0019 | Detail Location for Install CCTV at Outside Building | 0 |  | 2026-01-14 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending
20 | Electrical | 523213-01-RFI-EL-0020 | Quantity and Installation Locations of PIR Sensors for the Stairs | 0 |  | 2026-01-20 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
21 | Electrical | 523213-01-RFI-EL-0021 | Confirm for Power Supply for LV System | 0 |  | 2026-01-20 | 2026-02-02 |  |  | AUR | 9 | Pending | Overdue
22 | Electrical | 523213-01-RFI-EL-0022 | Confirm Fire Alarm and ASD Interface | 0 |  | 2026-01-20 | 2026-01-22 | 2026-01-27 |  | STT | 15 | Pending | Overdue | Urgent
23 | Electrical | 523213-01-RFI-EL-0023 | Fire Alarm Signals Interface to BMS System | 0 |  | 2026-01-22 | 2026-02-02 | 2026-02-09 |  | STT | 2 | Pending |  | Urgent
24 | Electrical | 523213-01-RFI-EL-0024 | Module (Control Module) for Fire Telephone of Staircases 1st FL | 0 |  | 2026-01-20 | 2026-01-22 | 2026-01-27 |  | STT | 15 | Pending | Overdue
25 | Electrical | 523213-01-RFI-EL-0025 | Scope of Earth Ground Bar and Cable for Fuel Fill Cabinet | 0 |  | 2026-01-20 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
26 | Electrical | 523213-01-RFI-EL-0026 | Electrical Routing at 2nd Floor Confirmation | 0 |  | 2026-01-17 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
27 | Electrical | 523213-01-RFI-EL-0027 | Confirm to add Lamp type&room in Luminaire Schedule and PIR for Sensor 1st and 5th FL | 0 |  | 2026-01-31 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
28 | Electrical | 523213-01-RFI-EL-0028 | UDB and LCP Panels Relocation on 2nd Floor | 0 |  | 2026-01-17 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
29 | Electrical | 523213-01-RFI-EL-0029 | Add Junction Box for Phase 1 on 3rd, 4th and 5th Floor for Convenience for Tie-In in the Future Phase | 0 |  | 2026-01-17 | 2026-02-03 | 2026-02-09 |  | STT | 2 | Pending
30 | Electrical | 523213-01-RFI-EL-0030 | Relay of Lighting Control at 2nd floor Confirmation | 0 |  | 2026-01-20 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
31 | Electrical | 523213-01-RFI-EL-0031 | Lighting Circuit at Garbage and Janitor Rooms, 1st Floor - Supply from Source B Only | 0 |  | 2026-01-20 | 2026-02-03 |  |  | AUR | 8 | Pending | Overdue
32 | Electrical | 523213-01-RFI-EL-0032 | Confirm Phase of TH-BKK02-02-06-LVSB-002-S1 on 6th Floor (Phase 1 or Phase 2) | 0 |  | 2026-01-20 | 2026-02-03 | 2026-02-09 |  | STT | 2 | Pending
33 | Electrical | 523213-01-RFI-EL-0033 | Confirmation on Identification of Relay Numbers Lighting System Roof Floor | 0 |  | 2026-01-29 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
34 | Electrical | 523213-01-RFI-EL-0034 | Confirmation on Power Supply for TH-BKK2-02-01-EAF-007 and 008 1st FL | 0 |  | 2026-01-29 | 2026-02-11 |  |  | AUR | 0 | Pending
35 | Electrical | 523213-01-RFI-EL-0035 | Requirement for PIR Sensor for lighting L1 Type 2nd to 6th FL | 0 |  | 2026-01-29 | 2026-02-11 |  |  | AUR | 0 | Pending
36 | Electrical | 523213-01-RFI-EL-0036 | 0 | [6 empty] | 0 | #N/A | 0
37 | Electrical | 523213-01-RFI-EL-0037 | Tag Confirmation for Electrical Panel 1st to Roof FL | 0 |  | 2026-01-31 | 2026-02-07 |  |  | AUR | 4 | Pending | High
38 | Electrical | 523213-01-RFI-EL-0038 | Connection for Fire Alarm Phase 1 on 3rd FL system | 0 |  | 2026-01-29 | 2026-02-11 |  |  | AUR | 0 | Pending
39 | Electrical | 523213-01-RFI-EL-0039 | 0 | [6 empty] | 0 | #N/A | 0
40 | Electrical | 523213-01-RFI-EL-0040 | 0 | [6 empty] | 0 | #N/A | 0
41 | Electrical | 523213-01-RFI-EL-0041 | Clarification on Scope of Work for Plug-in Units and Sub Main Cables | 0 |  | 2026-01-31 | 2026-02-11 |  |  | AUR | 0 | Pending
42 | Electrical | 523213-01-RFI-EL-0042 | 0 | [6 empty] | 0 | #N/A | 0
43 | Electrical | 523213-01-RFI-EL-0043 | Confirmation for NSCP interface with BMS as - HHI or LLI? | 0 |  | 2026-02-06 | 2026-02-07 |  |  | AUR | 4 | Pending | High
44 | Electrical | 523213-01-RFI-EL-0044 | Clarification of Heat Detector for Genset Room Fire Alarm System | 0 |  | 2026-02-04 | 2026-02-11 |  |  | AUR | 0 | Pending
45 | Electrical | 523213-01-RFI-EL-0045 | Confirm to use Steel Plint for all LV Switch Board as same as Phase 4 and 5. | 0 |  | 2026-02-06 | 2026-02-07 |  |  | AUR | 4 | Pending | High
46 | Electrical | 523213-01-RFI-EL-0046 | Confirm of Interface Method for Tap-off Unit (Non-IT) : HLI or LLI? | 0 |  | 2026-02-10 | 2026-02-11 |  |  | AUR | 0 | Pending
47 | Electrical | 523213-01-RFI-EL-0047 | Confirm Switch Control for Lighting System 1st FL (Entrance, Reception, Lift Lobby and Sec. Room 2) | 0 |  | 2026-02-10 | 2026-02-11 |  |  | AUR | 0 | Pending
48 | Electrical | 523213-01-RFI-EL-0048 | Cable trays obstruct a spare space of FWU | 0 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
49 | Electrical | 523213-01-RFI-EL-0049 | Confirm Supply source for junction boxes in shower room (1st floor) | 0 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
50 | Electrical | 523213-01-RFI-EL-0050 | Clarification on BMS Monitoring Points for IG-100 Fire Suppression System | 0 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
51 | Electrical | 523213-01-RFI-EL-0051 | Clarification on PACP Low-Level Interface (Hardwired) Point List Requirements | 0 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
52 | Electrical | 523213-01-RFI-EL-0052 | Confirmation for MV Cable Ladder Color Coding | 0 |  | 2026-02-11 |  |  |  | CTA | 0 | Pending
53 | Electrical | 523213-01-RFI-EL-0053 | 0 | [6 empty] | 0 | #N/A | 0
54 | Electrical | 523213-01-RFI-EL-0054 | 0 | [6 empty] | 0 | #N/A | 0
[6 empty] | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
FIRE PROTECTION |  |  |  |  | *Put only this
1 | Fire Protection | 523213-01-RFI-FI-0001 | Request for Information - IG 100 or Wet Sprinkler for HV UG Entry Room 1st FL | 0 |  | 2026-01-22 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
2 | Fire Protection | 523213-01-RFI-FI-0002 | Symbol to use with Jockey Pump | 0 |  | 2026-01-14 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
3 | Fire Protection | 523213-01-RFI-FI-0003 | Name of Data Hall (1, 2, 3 or A, B, C ) | 0 |  | 2026-01-14 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
4 | Fire Protection | 523213-01-RFI-FI-0004 | Sprinkler Corridor 1st FL is Fit Out | 0 |  | 2026-01-22 | 2026-02-09 |  |  | AUR | 2 | Pending
5 | Fire Protection | 523213-01-RFI-FI-0005 | Confirm the Location of Fire Hose Cabinet 1st | 0 |  | 2026-01-14 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
6 | Fire Protection | 523213-01-RFI-FI-0006 | Needed Installation Detail of Fire Hose Cabinet in Pump Room | 0 |  | 2026-01-14 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
7 | Fire Protection | 523213-01-RFI-FI-0007 | Confirm The Main Pipe Size | 0 |  | 2026-01-22 | 2026-01-22 |  |  | AUR | 20 | Pending | Overdue | Urgent
8 | Fire Protection | 523213-01-RFI-FI-0008 | Confirmation of Nitrogen Suppression System for MDF A & ELV A and MDF B & ELV B (Level 2) | 0 |  | 2026-01-20 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
9 | Fire Protection | 523213-01-RFI-FI-0009 | Confirmation of Butterfly Valve with Supervisory Switch Status Indication to Fire Alarm System | 0 |  | 2026-01-22 | 2026-02-06 |  |  | AUR | 5 | Pending | Overdue
10 | Fire Protection | 523213-01-RFI-FI-0010 | Confirm the details of the first and second horn tones activation in the Nitrogen Suppression System | 0 |  | 2026-01-22 | 2026-02-09 |  |  | AUR | 2 | Pending
11 | Fire Protection | 523213-01-RFI-FI-0011 | Confirmation of the Details of the Activation of the LED Indication R0 | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
12 | Fire Protection | 523213-01-RFI-FI-0012 | Confirmation of the Details of the First and Second Horn Tones Activation | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
13 | Fire Protection | 523213-01-RFI-FI-0013 | Confirmation of the Details of the Strobe Light & Second Horn Activated for all Genset to the Pre Action System | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
14 | Fire Protection | 523213-01-RFI-FI-0014 | Confirmation of 2-Layer Silent Nozzle – IG-100 System due to height more than 5 m. 2nd-6th FL | 0 |  | 2026-01-29 | 2026-02-09 |  |  | AUR | 2 | Pending
15 | Fire Protection | 523213-01-RFI-FI-0015 | 0 | [6 empty] | 0 | #N/A | 0
16 | Fire Protection | 523213-01-RFI-FI-0016 | 0 | [6 empty] | 0 | #N/A | 0
17 | Fire Protection | 523213-01-RFI-FI-0017 | 0 | [6 empty] | 0 | #N/A | 0
18 | Fire Protection | 523213-01-RFI-FI-0018 | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Fire Protection | 523213-01-RFI-FI-0019 | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Fire Protection | 523213-01-RFI-FI-0020 | #N/A | #N/A |  | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[8 empty] | #N/A | #N/A | #N/A
HYDRAULIC |  |  |  |  | *Put only this
1 | Hydraulics | 523213-01-RFI-HY-0001 | Water Meter Type for Toilet Room | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
2 | Hydraulics | 523213-01-RFI-HY-0002 | Confirm fit Out Scope | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
3 | Hydraulics | 523213-01-RFI-HY-0003 | Confirm Sewage Submersible Pump Control Panel Scope | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
4 | Hydraulics | 523213-01-RFI-HY-0004 | Propose to use 20 Inched BSP SCh20 for Generator Exhaust Pipe | 0 |  | 2026-01-20 | 2026-01-22 |  |  | AUR | 20 | Pending | Overdue | Urgent
5 | Hydraulics | 523213-01-RFI-HY-0005 | Confirm to Connect with MWA by Existing Pipe or not | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
6 | Hydraulics | 523213-01-RFI-HY-0006 | Confirm to Install Digital Water Meter at Softener Drain Line | 0 |  | 2026-01-20 | 2026-02-09 |  |  | AUR | 2 | Pending
7 | Hydraulics | 523213-01-RFI-HY-0007 | Confirm Generator Exhaust Pipe (Head Type) | 0 |  | 2026-01-14 | 2026-01-22 |  |  | AUR | 20 | Pending | Overdue | Urgent
8 | Hydraulics | 523213-01-RFI-HY-0008 | Details of the FUS-A and FUS-B pipelines for the day tank | 0 |  | 2026-01-14 | 2026-02-09 |  |  | AUR | 2 | Pending
9 | Hydraulics | 523213-01-RFI-HY-0009 | Confirm whether flow meters are required for the FOU-A and FOU-B drain lines | 0 |  | 2026-02-10 | 2026-02-11 |  |  | AUR | 0 | Pending
10 | Hydraulics | 523213-01-RFI-HY-0010 | Confirmation of Gate Valve Installation Details for FUS-A, FUS-B, FUO-A, FUO-B and FUPSL Lines at Pump Room | 0 |  | 2026-01-19 | 2026-02-09 |  |  | AUR | 2 | Pending
11 | Hydraulics | 523213-01-RFI-HY-0011 | Clarification on Fuel Consumption Meter (FCM) Intent | 0 |  | 2026-01-27 | 2026-02-09 |  |  | AUR | 2 | Pending
MECHANICAL |  |  |  |  | *Put only this
1 | Mechanical | 523213-01-RFI-ME-0001 | FCU Fan Type | 0 |  | 2026-01-16 | 2026-01-22 | 2026-02-10 |  | STT | 1 | Pending |  | Urgent
2 | Mechanical | 523213-01-RFI-ME-0002 | Gas Purging Fan Tag Number is 02-01-GPF-002 or 02-02-GPF-002 for 2nd FL | 0 |  | 2026-01-20 |  |  |  | CTA | #N/A | CANCEL
3 | Mechanical | 523213-01-RFI-ME-0003 | Correct reference of the Supply Air of FCU 2nd FL (No. 001 to 012) | 0 |  | 2026-01-16 | 2026-01-22 | 2026-02-10 |  | STT | 1 | Pending |  | Urgent
4 | Mechanical | 523213-01-RFI-ME-0004 | CCU is not Equipped with a motorized Damper? 2nd - 4th FL | 0 |  | 2026-01-16 | 2026-01-21 | 2026-01-27 | 2026-01-27 | Closed |  | B |  | Urgent
5 | Mechanical | 523213-01-RFI-ME-0005 | MEP Pipe at 2.1m. conflict with door height 2.8 meters 1st Floor | 0 |  | 2026-01-21 | 2026-01-26 | 2026-01-28 | 2026-01-29 | Closed |  | B
6 | Mechanical | 523213-01-RFI-ME-0006 | Cooling Coil amount and type for PAHU 1st & Roof FL | 0 |  | 2026-01-12 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
7 | Mechanical | 523213-01-RFI-ME-0007 | PAHU Supply Air Conflict 1st FL | 0 |  | 2026-01-12 | 2026-01-22 | 2026-02-10 |  | STT | 1 | Pending |  | Urgent
8 | Mechanical | 523213-01-RFI-ME-0008 | Add Isolation Valve and Check Valve for DRG-ME-0103, 0104 and 0105 | 0 |  | 2026-01-12 | 2026-01-22 | 2026-02-10 |  | STT | #N/A | CANCEL |  | Urgent
9 | Mechanical | 523213-01-RFI-ME-0009 | Add Isolation Valves for 4th &5 th FL | 0 |  | 2026-01-22 |  | 2026-02-10 |  | STT | #N/A | CANCEL |  | Urgent
10 | Mechanical | 523213-01-RFI-ME-0010 | Change CVV Cable from 2C-1.5 mm2 to 4C-1.5 mm2 in MCC Panel for DRG-ME-8000, 8001, 8002, 8003 | 0 |  | 2026-01-22 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
11 | Mechanical | 523213-01-RFI-ME-0011 | Power Supply and cable size from MCC Panel in Drawing 523213-02-DRG-ME-0201 | 0 |  | 2026-01-12 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
12 | Mechanical | 523213-01-RFI-ME-0012 | DP Sensor for Fan Wall at DATA HALL is Required | 0 |  | 2026-01-22 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
13 | Mechanical | 523213-01-RFI-ME-0013 | Verify position for 02-01-EAF-019 | 0 |  | 2026-01-12 | 2026-02-09 | 2026-02-10 |  | STT | 1 | Pending
14 | Mechanical | 523213-01-RFI-ME-0014 | Pressure Gauge for ACMV Riser Needed? | 0 |  | 2026-01-20 | 2026-02-11 |  |  | AUR | 0 | Pending
15 | Mechanical | 523213-01-RFI-ME-0015 | Confirm Temp/Hum. amount In LV Room A and B 2nd Floor.(Total 4 or 6 set) 2nd FL | 0 |  | 2026-01-27 | 2026-02-09 |  |  | AUR | 2 | Pending
16 | Mechanical | 523213-01-RFI-ME-0016 | Confirm for Fresh Air Fan for TH-BKK2-02-01-FAF-005 N2 Cylinder Room 1st Floor | 0 |  | 2026-01-23 | 2026-02-09 |  |  | AUR | 2 | Pending
17 | Mechanical | 523213-01-RFI-ME-0017 | Please Confirm the Power Supply for the Motorized Damper 2nd to 6th FL | 0 |  | 2026-01-31 | 2026-02-09 |  |  | AUR | 2 | Pending
18 | Mechanical | 523213-01-RFI-ME-0018 | Confirmation of Harmonic Filter Type (AHF) | 0 |  | 2026-01-31 | 2026-02-11 |  |  | AUR | 0 | Pending
19 | Mechanical | 523213-01-RFI-ME-0019 | FCU as the Spec (HH-D Double Skin) Sizing too Big. It Can't Install in Room - 02-02-FCU-001&002 2nd FL | 0 |  | 2026-01-31 | 2026-02-11 |  |  | AUR | 0 | Pending
20 | Mechanical | 523213-01-RFI-ME-0020 | Confirm PRD at 5th FL (for TX LV MSB 3, UPS Room A, B, C and D) | 0 |  | 2026-02-06 | 2026-02-11 |  |  | AUR | 0 | Pending
21 | Mechanical | 523213-01-RFI-ME-0021 | Confirm Air Flow Value for TH-BKK2-02-01-FAF-001 and 002 1st FL | 0 |  | 2026-02-06 | 2026-02-11 |  |  | AUR | 0 | Pending
22 | Mechanical | 523213-01-RFI-ME-0022 | Need Slab to Beam Height 4.1 m for Installing DUCT at PAU Room Roof FL (Currently h=2.6m.) | 0 |  | 2026-02-06 | 2026-02-11 |  |  | AUR | 0 | Pending
23 | Mechanical | 523213-01-RFI-ME-0023 | Confirm weather TH-BKK2-02-06-CH-001, 002 and 003 are provided with MDV or not? | 0 |  | 2026-02-10 | 2026-02-11 |  |  | AUR | 0 | Pending
24 | Mechanical | 523213-01-RFI-ME-0024 | Confirm whether the FCU power supply requirement is 3 Phase or Single Phase on DRG-ME-0203 | 0 |  | 2026-02-10 |  |  |  | CTA | 1 | Pending
[6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
STRUCTURAL |  |  |  |  | *Put only this
1 | Civil & Structure | 523213-01-RFI-ST-0001 | Request for Additional Steel Manufacturers Approval due to Material Stock Unavailability | 0 |  | 2026-02-10 | 2026-02-11 | 2026-02-11 |  | STT | 0 | Pending
2 | Civil & Structure | 523213-01-RFI-ST-0002 | 0 | [6 empty] | 0 |  | #N/A | #N/A
[7 empty] | #N/A |  | #N/A | #N/A |  | #N/A | #N/A
Formulas:
Actual Submission Date = IF(VLOOKUP([Doc Ref No.],AR!$C4:J46,4,0)="","",VLOOKUP([Doc Ref No.],AR!$C4:J46,4,0))
Actual Submission Date = IF(VLOOKUP([Doc Ref No.],EL!$C4:J975,4,0)="","",VLOOKUP([Doc Ref No.],EL!$C4:J975,4,0))
Delays Date = IFS(AND([Rev]<>"",[Approved Status]="Pending",[Action By]="CTA"),TODAY()-[Actual Submission Date],AND([Rev]<>"",[Approved Status]="Pending",[Action By]="AUR"),TODAY()-[Approval Date],AND([Rev]<>"",[Approved Status]="Pending",[Action By]="STT"),TODAY()-[AUR],OR([Action By]="Closed",[Action By]=""),"")
Approval Date = IF(VLOOKUP([Doc Ref No.],AR!$C4:AA46,12,0)="","",IF([Rev]=0,VLOOKUP([Doc Ref No.],AR!$C4:AA46,12,0),IF([Rev]=1,VLOOKUP([Doc Ref No.],AR!$C4:AA46,18,0),IF([Rev]=2,VLOOKUP([Doc Ref No.],AR!$C4:AA46,23,0),""))))
Approval Date = IF(VLOOKUP([Doc Ref No.],EL!$C4:AA975,13,0)="","",IF([Rev]=0,VLOOKUP([Doc Ref No.],EL!$C4:AA975,13,0),IF([Rev]=1,VLOOKUP([Doc Ref No.],EL!$C4:AA975,17,0),IF([Rev]=2,VLOOKUP([Doc Ref No.],EL!$C4:AA975,22,0),""))))
AUR = IF(VLOOKUP([Doc Ref No.],AR!$C4:AA46,13,0)="","",IF([Rev]=0,VLOOKUP([Doc Ref No.],AR!$C4:AA46,13,0),IF([Rev]=1,VLOOKUP([Doc Ref No.],AR!$C4:AA46,18,0),IF([Rev]=2,VLOOKUP([Doc Ref No.],AR!$C4:AA46,23,0),""))))
AUR = IF(VLOOKUP([Doc Ref No.],EL!$C4:AA975,14,0)="","",IF([Rev]=0,VLOOKUP([Doc Ref No.],EL!$C4:AA975,14,0),IF([Rev]=1,VLOOKUP([Doc Ref No.],EL!$C4:AA975,18,0),IF([Rev]=2,VLOOKUP([Doc Ref No.],EL!$C4:AA975,23,0),""))))
STT = IF(VLOOKUP([Doc Ref No.],ME!$C4:AA46,15,0)="","",IF([Rev]=0,VLOOKUP([Doc Ref No.],ME!$C4:AA46,15,0),IF(E8=1,VLOOKUP([Doc Ref No.],ME!$C4:AA46,20,0),IF(E8=2,VLOOKUP([Doc Ref No.],ME!$C4:AA46,25,0),""))))