## Overview
Shop Drawing Approval Summary
Trade | Planned Equipment Shop Drawing | Rev0 | [10 empty] | Rev1 | [11 empty] | Rev2
|  | GAA Status | CTA Status |  | AUR Status |  | STT Status | [5 empty] | GAA Status |  | CTA Status |  | AUR Status |  | STT Status | [5 empty] | GAA Status |  | CTA Status |  | AUR Status |  | STT Status
|  | Total Submission | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C |  | Pending resubmission | Submitted | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C |  | Pending resubmission | Submitted | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Total reviewed | Total outstanding | Status A | Status B | Status C
Structural | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architectural | 83 | 26 | 26 | 0 | 23 | 3 | 15 | 11 | 0 | 14 | 2 |  | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical | 52 | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire Protection | 40 | 11 | 7 | 4 | 0 | 11 | 0 | 11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hydraulics | 31 | 11 | 11 | 0 | 0 | 11 | 0 | 11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical & Comms | 258 | 71 | 36 | 35 | 24 | 47 | 3 | 68 | 0 | 0 | 3 |  | 3 | 3 | 2 | 1 | 1 | 2 | 0 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combine services drawing | 27 | 13 | 0 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overall | 510 | 137 | 85 | 52 | 47 | 90 | 18 | 119 | 0 | 14 | 6 | 0 | 6 | 4 | 3 | 1 | 2 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Trade | Submission | Submitted | Approved by All | Rejected | Pending submission | CTA Approved | CTA Outstanding | AUR Approved | AUR Outstanding | STT Approved | STT outstanding
|  | Structural | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0
|  | Architectural | 83 | 25 | 14 | 1 | 58 | 26 | 0 | 24 | 2 | 15 | 9
|  | AR & ST | 102 | 25 | 14 | 1 | 77 | 26 | 0 | 24 | 2 | 15 | 9
|  | Mechanical | 52 | 4 | 0 | 1 | 48 | 5 | 0 | 0 | 4 | 0 | 0
|  | Fire | 40 | 11 | 0 | 0 | 29 | 7 | 4 | 0 | 7 | 0 | 0
|  | Hydraulics | 31 | 11 | 0 | 0 | 21 | 11 | 0 | 0 | 11 | 0 | 0
|  | Electrical & Comms | 258 | 0 | 0 | 0 | 188 | 42 | #VALUE! | 1 | #VALUE! | 0 | #VALUE!
|  | CSD | 27 | 13 | 0 | 0 | 14 | 0 | 13 | 0 | 0 | 0 | 0
|  | Overall | 510 | 64 | 14 | 2 | 377 | 91 | #VALUE! | 25 | #VALUE! | 15 | #VALUE!
|  | AR & ST |  | 24.51% | 13.73% | 0.9804% | 75.49% | 25.49% | 0% | 23.53% | 1.961% | 14.71% | 8.824%
|  | Mechanical |  | 7.692% | 0% | 1.923% | 92.31% | 9.615% | 0% | 0% | 7.692% | 0% | 0%
|  | Fire |  | 27.5% | 0% | 0% | 72.5% | 17.5% | 10% | 0% | 17.5% | 0% | 0%
|  | Hydraulics |  | 35.48% | 0% | 0% | 67.74% | 35.48% | 0% | 0% | 35.48% | 0% | 0%
|  | Electrical & Comms |  | 0% | 0% | 0% | 72.87% | 16.28% | #VALUE! | 0.3876% | #VALUE! | 0% | #VALUE!
|  | CSD |  | 48.15% | 0% | 0% | 51.85% | 0% | 48.15% | 0% | 0% | 0% | 0%
|  | Overall |  | 12.55% | 2.745% | 0.3922% | 73.92% | 17.84% | #VALUE! | 4.902% | #VALUE! | 2.941% | #VALUE!
Do not tounch
2025-02-08
2025-02-08
2025-02-08

## Summary
Shop Drawing Approval Summary
Structural
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-26 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-02-02 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architectural
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 83 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 83 | 12 | 1 | 0 | 0 | 0 | 0 | 1 | 0
| 2026-01-19 | 83 | 17 | 3 | 0 | 1 | 0 | 0 | 1 | 1
| 2026-01-26 | 83 | 21 | 14 | 0 | 1 | 0 | 0 | 12 | 1
| 2026-02-02 | 83 | 27 | 19 | 0 | 1 | 3 | 0 | 14 | 1
Electrical
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 255 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2026-01-12 | 255 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2026-01-19 | 255 | 37 | 0 | 12 | 0 | 7 | 0 | 0 | 1
| 2026-01-26 | 255 | 53 | 30 | 12 | 0 | 17 | 0 | 0 | 1
| 2026-02-02 | 255 | 73 | 36 | 12 | 2 | 21 | 0 | 0 | 1
Mechanical
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 52 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 52 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| 2026-01-19 | 52 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0
| 2026-01-26 | 52 | 5 | 3 | 0 | 3 | 0 | 0 | 0 | 0
| 2026-02-02 | 52 | 5 | 3 | 0 | 3 | 0 | 0 | 0 | 0
Fire Protection
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 40 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| 2026-01-19 | 40 | 10 | 5 | 0 | 5 | 0 | 0 | 0 | 0
| 2026-01-26 | 40 | 10 | 7 | 0 | 7 | 0 | 0 | 0 | 0
| 2026-02-02 | 40 | 15 | 7 | 0 | 7 | 0 | 0 | 0 | 0
Hydraulics
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 31 | 1 | 4 | 0 | 4 | 0 | 0 | 0 | 0
| 2026-01-19 | 31 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0
| 2026-01-26 | 31 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0
| 2026-02-02 | 31 | 14 | 11 | 0 | 11 | 0 | 0 | 0 | 0
Combined Service Drawing
| w/e | Total Expected | Planned Submission | Actual Submitted | Status
[5 empty] | Under Review |  |  | A | B | C
[5 empty] | CTA | AUR | STT
| 2026-01-05 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-12 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-19 | 27 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2026-01-26 | 27 | 2 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 2026-02-02 | 27 | 15 | 9 | 9 | 0 | 0 | 0 | 0 | 0
2025-02-08
2025-02-08
2025-02-08
Formulas:
w/e = [w/e, row above]+7

## AR
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [12 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. | Document Description | RFAS Doc No. | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Rev 6 |  |  |  |  | Rev 7 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Architectural | 523213-01-SDW-AR-0001 | Architectural Drawing Index | 523213-01-RFAS-AR-0001 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 0 | Closed | B | 2026-01-28 | GC |  | 2026-01-12 | 2026-01-21 | 2026-01-23 | 2026-01-28 | B | [35 empty] | NO
2 | Architectural | 523213-01-SDW-AR-0100 | Level 1 - Overall Base Plan | 523213-01-RFAS-AR-0002 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | GAA | C | 2026-01-28 | GC |  | 2026-01-19 | 2026-01-21 | 2026-01-23 | 2026-01-28 | C | [35 empty] | NO
3 | Architectural | 523213-01-SDW-AR-0200 | Level 2 - Overall Base Plan | 523213-01-RFAS-AR-0003 | 2026-01-12 | 2026-01-17 | 2026-01-24 | 0 | AUR | Pending |  | GC | RFI-EL-0018 | 2026-01-17 | 2026-01-21 | [38 empty] | NO
4 | Architectural | 523213-01-SDW-AR-0300 | Level 3 - Overall Base Plan | 523213-01-RFAS-AR-0004 | 2026-01-19 | 2026-01-20 | 2026-01-27 | 0 | Closed | B | 2026-02-02 | GC |  | 2026-01-20 | 2026-01-22 | 2026-01-28 | 2026-02-02 | B | [35 empty] | NO
5 | Architectural | 523213-01-SDW-AR-0400 | Level 4 - Overall Base Plan | 523213-01-RFAS-AR-0005 | 2026-01-26 | 2026-01-27 | 2026-02-03 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-27 | 2026-01-28 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
6 | Architectural | 523213-01-SDW-AR-0500 | Level 5 - Overall Base Plan | 523213-01-RFAS-AR-0006 | 2026-01-26 | 2026-01-28 | 2026-02-04 | 0 | STT | Pending |  | GC |  | 2026-01-28 | 2026-01-31 | 2026-02-04 | [37 empty] | NO
7 | Architectural | 523213-01-SDW-AR-0600 | Level 6 - Overall Base Plan | 523213-01-RFAS-AR-0007 | 2026-01-19 | 2026-01-22 | 2026-01-29 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-22 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
8 | Architectural | 523213-01-SDW-AR-0700 | Roof Deck - Overall Base Plan | 523213-01-RFAS-AR-0008 | 2026-01-19 | 2026-02-09 | 2026-02-16 | 0 | AUR | Pending |  | GC |  | 2026-02-09 | 2026-02-11 | [38 empty] | NO
9 | Architectural | 523213-01-SDW-AR-1100 | Level 1 - Floor Finishes & Details | 523213-01-RFAS-AR-0009 | 2026-01-19 | 2026-02-02 | 2026-02-09 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-02-02 | 2026-02-04 | 2026-02-06 | 2026-02-06 | B | [35 empty] | NO
10 | Architectural | 523213-01-SDW-AR-1200 | Level 2 - Floor Finishes & Details | 523213-01-RFAS-AR-0010 | 2026-01-12 | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-23 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
11 | Architectural | 523213-01-SDW-AR-1300 | Level 3 - Floor Finishes & Details | 523213-01-RFAS-AR-0011 | 2026-02-19 | 2026-02-04 | 2026-02-11 | 0 | STT | Pending |  | GC |  | 2026-02-04 | 2026-02-06 | 2026-02-09 | [37 empty] | NO
12 | Architectural | 523213-01-SDW-AR-1600 | Level 6 - Floor Finishes & Details | 523213-01-RFAS-AR-0012 | 2026-01-22 | 2026-02-03 | 2026-02-10 | 0 | STT | Pending |  | GC |  | 2026-02-03 | 2026-02-06 | 2026-02-09 | [37 empty] | NO
13 | Architectural | 523213-01-SDW-AR-2100 | Level 1 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0013 | 2026-02-05 | [6 empty] | GC | [41 empty] | NO
14 | Architectural | 523213-01-SDW-AR-2110 | Level 1 - Wall Finishes & Details | 523213-01-RFAS-AR-0014 | 2026-02-05 | [6 empty] | GC | [41 empty] | NO
15 | Architectural | 523213-01-SDW-AR-2140 | Level 1 - Block Wall Layout & Details | 523213-01-RFAS-AR-0015 | 2026-02-05 | [6 empty] | GC | [41 empty] | NO
16 | Architectural | 523213-01-SDW-AR-2200 | Level 2 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0016 | 2026-01-26 | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | B | [35 empty] | NO
17 | Architectural | 523213-01-SDW-AR-2210 | Level 2 - Wall Finishes & Details | 523213-01-RFAS-AR-0017 | 2026-01-29 | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | B | [35 empty] | NO
18 | Architectural | 523213-01-SDW-AR-2220 | Level 2 - Wall Setting-out | 523213-01-RFAS-AR-0018 | 2026-01-29 | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | B | [35 empty] | NO
19 | Architectural | 523213-01-SDW-AR-2230 | Level 2 - Block Wall Layout & Details | 523213-01-RFAS-AR-0019 | 2026-01-29 | 2026-02-06 | 2026-02-13 | 0 | STT | Pending |  | GC |  | 2026-02-06 | 2026-02-09 | 2026-02-12 | [37 empty] | NO
20 | Architectural | 523213-01-SDW-AR-2240 | Level 2 - Partition Wall Support Layout & Details | 523213-01-RFAS-AR-0020 | 2026-01-29 | 2026-02-06 | 2026-02-13 | 1 | STT | Pending |  | GC |  | 2026-02-02 | 2026-02-05 |  |  | C | 2026-02-06 | 2026-02-09 | 2026-02-12 | [32 empty] | NO
21 | Architectural | 523213-01-SDW-AR-2250 | Level 2 - Wire Mesh Layout & Details | 523213-01-RFAS-AR-0021 | 2026-02-05 | [6 empty] | GC | [41 empty] | NO
22 | Architectural | 523213-01-SDW-AR-2300 | Level 3 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0022 | 2026-02-19 | 2026-01-26 | 2026-02-02 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
23 | Architectural | 523213-01-SDW-AR-2340 | Level 3 - Partition Wall Support Layout & Details | 523213-01-RFAS-AR-0023 | 2026-02-19 | [6 empty] | GC | [41 empty] | NO
24 | Architectural | 523213-01-SDW-AR-2330 | Level 3 - Block Wall Layout & Details | 523213-01-RFAS-AR-0024 | 2026-02-19 | [6 empty] | GC | [41 empty] | NO
25 | Architectural | 523213-01-SDW-AR-2310 | Level 3 - Wall Finishes & Details | 523213-01-RFAS-AR-0025 | 2026-02-19 | 2026-02-03 | 2026-02-10 | 0 | STT | Pending |  | GC |  | 2026-02-03 | 2026-02-06 | 2026-02-09 | [37 empty] | NO
26 | Architectural | 523213-01-SDW-AR-2320 | Level 3 - Wall Setting-out | 523213-01-RFAS-AR-0026 | 2026-02-19 | 2026-01-28 | 2026-02-04 | 0 | STT | Pending |  | GC |  | 2026-01-28 | 2026-01-31 | 2026-02-04 | [37 empty] | NO
27 | Architectural | 523213-01-SDW-AR-2400 | Level 4 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0027 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
28 | Architectural | 523213-01-SDW-AR-2410 | Level 4 - Wall Finishes & Details | 523213-01-RFAS-AR-0028 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
29 | Architectural | 523213-01-SDW-AR-2420 | Level 4 - Wall Setting-out | 523213-01-RFAS-AR-0029 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
30 | Architectural | 523213-01-SDW-AR-2430 | Level 4 - Block Wall Layout & Details | 523213-01-RFAS-AR-0030 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
31 | Architectural | 523213-01-SDW-AR-2500 | Level 5 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0031 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
32 | Architectural | 523213-01-SDW-AR-2510 | Level 5 - Wall Finishes & Details | 523213-01-RFAS-AR-0032 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
33 | Architectural | 523213-01-SDW-AR-2520 | Level 5 - Wall Setting-out | 523213-01-RFAS-AR-0033 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
34 | Architectural | 523213-01-SDW-AR-2530 | Level 5 - Block Wall Layout & Details | 523213-01-RFAS-AR-0034 | 2026-04-02 | [6 empty] | GC | [41 empty] | NO
35 | Architectural | 523213-01-SDW-AR-2600 | Level 6 - Bund Wall Setting-out & Details | 523213-01-RFAS-AR-0035 | 2026-02-12 | 2026-01-26 | 2026-02-02 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
36 | Architectural | 523213-01-SDW-AR-2610 | Level 6 - Wall Finishes & Details | 523213-01-RFAS-AR-0036 | 2026-02-12 | 2026-02-03 | 2026-02-10 | 0 | STT | Pending |  | GC |  | 2026-02-03 | 2026-02-06 | 2026-02-09 | [37 empty] | NO
37 | Architectural | 523213-01-SDW-AR-2620 | Level 6 - Wall Setting-out | 523213-01-RFAS-AR-0037 | 2026-02-12 | 2026-01-28 | 2026-02-04 | 0 | STT | Pending |  | GC |  | 2026-01-28 | 2026-01-31 | 2026-02-04 | [37 empty] | NO
38 | Architectural | 523213-01-SDW-AR-2630 | Level 6 - Block Wall Layout & Details | 523213-01-RFAS-AR-0038 | 2026-02-12 | [6 empty] | GC | [41 empty] | NO
39 | Architectural | 523213-01-SDW-AR-2640 | Level 6 - Partition Wall Support Layout & Details | 523213-01-RFAS-AR-0039 | 2026-02-12 | [6 empty] | GC | [41 empty] | NO
40 | Architectural | 523213-01-SDW-AR-3100 | Level 1 - Crash Rail & Skirting Layout & Details | 523213-01-RFAS-AR-0040 | 2026-03-12 | [6 empty] | GC | [41 empty] | NO
41 | Architectural | 523213-01-SDW-AR-3200 | Level 2 - Crash Rail & Skirting Layout & Details | 523213-01-RFAS-AR-0041 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
42 | Architectural | 523213-01-SDW-AR-3600 | Level 6 - Crash Rail & Skirting Layout & Details | 523213-01-RFAS-AR-0042 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
43 | Architectural | 523213-01-SDW-AR-4100 | Level 1 - Door Schedule Layout & Details | 523213-01-RFAS-AR-0043 | 2026-03-26 | [6 empty] | GC | [41 empty] | NO
44 | Architectural | 523213-01-SDW-AR-4200 | Level 2 - Door Schedule Layout & Details | 523213-01-RFAS-AR-0044 | 2026-03-19 | [6 empty] | GC | [41 empty] | NO
45 | Architectural | 523213-01-SDW-AR-4300 | Level 3 - Door Schedule Layout & Details | 523213-01-RFAS-AR-0045 | 2026-03-31 | [6 empty] | GC | [41 empty] | NO
46 | Architectural | 523213-01-SDW-AR-4600 | Level 6 - Door Schedule Layout & Details | 523213-01-RFAS-AR-0046 | 2026-03-26 | [6 empty] | GC | [41 empty] | NO
47 | Architectural | 523213-01-SDW-AR-5100 | Level 1 - Soffit Finishes & Details | 523213-01-RFAS-AR-0047 | 2026-02-12 | [6 empty] | GC | [41 empty] | NO
48 | Architectural | 523213-01-SDW-AR-5110 | Level 1 - Ceiling Finishes & Details | 523213-01-RFAS-AR-0048 | 2026-02-12 | [6 empty] | GC | [41 empty] | NO
49 | Architectural | 523213-01-SDW-AR-5200 | Level 2 - Soffit Finishes & Details | 523213-01-RFAS-AR-0049 | 2026-01-29 | 2026-01-23 | 2026-01-30 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-23 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
50 | Architectural | 523213-01-SDW-AR-5210 | Level 2 - Ceiling Finishes & Details | 523213-01-RFAS-AR-0050 | 2026-01-29 | 2026-01-26 | 2026-02-02 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
51 | Architectural | 523213-01-SDW-AR-5220 | Level 2 - Structured Ceiling Anchor Layout & Details | 523213-01-RFAS-AR-0051 | 2026-03-05 | 2026-01-26 | 2026-02-02 | 0 | Closed | B | 2026-02-06 | GC |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | B | [35 empty] | NO
52 | Architectural | 523213-01-SDW-AR-5300 | Level 3 - Soffit Finishes & Details | 523213-01-RFAS-AR-0052 | 2026-03-19 | [6 empty] | GC | [41 empty] | NO
53 | Architectural | 523213-01-SDW-AR-5600 | Level 6 - Soffit Finishes & Details | 523213-01-RFAS-AR-0053 | 2026-02-05 | [6 empty] | GC | [41 empty] | NO
54 | Architectural | 523213-01-SDW-AR-5700 | Roof Deck - Soffit Finishes & Details | 523213-01-RFAS-AR-0054 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
55 | Architectural | 523213-01-SDW-AR-6110 | Level 1 - Interior Elevation Views, Layout & Details | 523213-01-RFAS-AR-0055 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
56 | Architectural | 523213-01-SDW-AR-6101 | Level 1 - Reception Hall Layout & Details | 523213-01-RFAS-AR-0056 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
57 | Architectural | 523213-01-SDW-AR-6102 | Level 1 - Security Room 1 Layout & Details | 523213-01-RFAS-AR-0057 | 2026-03-12 | [6 empty] | GC | [41 empty] | YES
58 | Architectural | 523213-01-SDW-AR-6103 | Level 1 - Security Room 2 Layout & Details | 523213-01-RFAS-AR-0058 | 2026-03-12 | [6 empty] | GC | [41 empty] | YES
59 | Architectural | 523213-01-SDW-AR-6104 | Level 1 - Pantry Layout & Details | 523213-01-RFAS-AR-0059 | 2026-03-19 | [6 empty] | GC | [41 empty] | NO
60 | Architectural | 523213-01-SDW-AR-6105 | Level 1 - Technical Assistant Room Layout & Details | 523213-01-RFAS-AR-0060 | 2026-03-19 | [6 empty] | GC | [41 empty] | YES
61 | Architectural | 523213-01-SDW-AR-6106 | Level 1 - Hall 1.1 Layout & Details | 523213-01-RFAS-AR-0061 | 2026-03-19 | [6 empty] | GC | [41 empty] | NO
62 | Architectural | 523213-01-SDW-AR-6120 | Level 1 - Fireman Lift Lobby Layout & Details | 523213-01-RFAS-AR-0062 | [7 empty] | GC | [41 empty] | NO
63 | Architectural | 523213-01-SDW-AR-6210 | Level 2 - Interior Elevation Views, Layout & Details | 523213-01-RFAS-AR-0063 | 2026-02-19 | [6 empty] | GC | [41 empty] | NO
64 | Architectural | 523213-01-SDW-AR-6230 | Level 2 - Toilet Layout & Details | 523213-01-RFAS-AR-0064 | 2026-02-19 | [6 empty] | GC | [41 empty] | NO
65 | Architectural | 523213-01-SDW-AR-6240 | Level 2 - GENSET Room Layout & Details | 523213-01-RFAS-AR-0065 | 2026-02-19 | [6 empty] | GC | [41 empty] | NO
66 | Architectural | 523213-01-SDW-AR-6290 | Level 2 - Hot Aisle Containment Layout Plan | 523213-01-RFAS-AR-0066 | 2026-03-05 | [6 empty] | GC | [41 empty] | YES
67 | Architectural | 523213-01-SDW-AR-6610 | Level 6 - Interior Elevation Views, Layout & Details | 523213-01-RFAS-AR-0067 | 2026-02-26 | [6 empty] | GC | [41 empty] | NO
68 | Architectural | 523213-01-SDW-AR-6640 | Level 6 - GENSET Room Layout & Details | 523213-01-RFAS-AR-0068 | 2026-02-26 | [6 empty] | GC | [41 empty] | NO
69 | Architectural | 523213-01-SDW-AR-7100 | Level 1 - Signage Layout Plan & Details | 523213-01-RFAS-AR-0069 | 2026-03-12 | [6 empty] | GC | [41 empty] | NO
70 | Architectural | 523213-01-SDW-AR-7200 | Level 2 - Signage Layout Plan & Details | 523213-01-RFAS-AR-0070 | 2026-03-05 | [6 empty] | GC | [41 empty] | NO
71 | Architectural | 523213-01-SDW-AR-7300 | Level 3 - Signage Layout Plan & Details | 523213-01-RFAS-AR-0071 | [7 empty] | GC | [41 empty] | NO
72 | Architectural | 523213-01-SDW-AR-7600 | Level 6 - Signage Layout Plan & Details | 523213-01-RFAS-AR-0072 | 2026-03-12 | [6 empty] | GC | [41 empty] | NO
73 | Architectural | 523213-01-SDW-AR-8100 | Level 1 - Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0073 | 2026-02-23 | [6 empty] | GC | [41 empty] | NO
74 | Architectural | 523213-01-SDW-AR-8200 | Level 2 - Data Hall 2-A Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0074 | 2026-02-09 | [6 empty] | GC | [41 empty] | NO
75 | Architectural | 523213-01-SDW-AR-8201 | Level 2 - Spare Space Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0075
76 | Architectural | 523213-01-SDW-AR-8202 | Level 2 - Data Hall 2-C Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0076
77 | Architectural | 523213-01-SDW-AR-8203 | Level 2 - ELV B Area Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0077
78 | Architectural | 523213-01-SDW-AR-8204 | Level 2 - ELV A Area Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0078
79 | Architectural | 523213-01-SDW-AR-8205 | Level 2 - LV Room Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0079
80 | Architectural | 523213-01-SDW-AR-8300 | Level 3 - TX Room Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0080 | 2026-03-16 | [6 empty] | GC | [41 empty] | NO
81 | Architectural | 523213-01-SDW-AR-8600 | Level 6 - MSB Room Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0081 | 2026-03-09 | [6 empty] | GC | [41 empty] | NO
82 | Architectural | 523213-01-SDW-AR-8601 | Level 6 - ELV Room Block-out & Pipe Sleeve Details | 523213-01-RFAS-AR-0082
83 | Architectural | 523213-01-SDW-AR-3300 | Level 3 - Level 3 Skirting Layout & Details
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Planned Submission = [Planned Submission, row below]+7
Planned Submission = [Planned Submission, row above]+7

## ST
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [13 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. |  | RFAS Doc No. | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Civil & Structure | 523213-01-SDW-ST-0001 | Structural Drawing Index | 523213-01-RFAS-ST-0001 |  |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
2 | Civil & Structure | 523213-01-SDW-ST-1100 | Level 1 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0002 | 2026-03-01 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
3 | Civil & Structure | 523213-01-SDW-ST-1200 | Level 2 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0003 | 2026-02-15 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
4 | Civil & Structure | 523213-01-SDW-ST-1201 | Level 2 - Ladder Cover Sections & Details | 523213-01-RFAS-ST-0004 | 2026-02-15 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
5 | Civil & Structure | 523213-01-SDW-ST-1300 | Level 3 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0005 | 2026-03-15 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
6 | Civil & Structure | 523213-01-SDW-ST-1310 | Level 3 - Ladder Cover Sections & Details | 523213-01-RFAS-ST-0006 | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
7 | Civil & Structure | 523213-01-SDW-ST-1400 | Level 4 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0007 | 2026-03-21 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
8 | Civil & Structure | 523213-01-SDW-ST-1410 | Level 4 - Ladder Cover Sections & Details | 523213-01-RFAS-ST-0008 | 2026-03-21 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
9 | Civil & Structure | 523213-01-SDW-ST-1500 | Level 5 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0009 | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
10 | Civil & Structure | 523213-01-SDW-ST-1510 | Level 5 - Ladder Cover Sections & Details | 523213-01-RFAS-ST-0010 | 2026-03-27 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
11 | Civil & Structure | 523213-01-SDW-ST-1300 | Level 6 - Concrete Plinth Layout Plan & Details | 523213-01-RFAS-ST-0011 | 2026-03-08 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
12 | Civil & Structure | 523213-01-SDW-ST-2100 | Level 1 - Steel Support & Details | 523213-01-RFAS-ST-0012 | 2026-03-08 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
13 | Civil & Structure | 523213-01-SDW-ST-2200 | Level 2 - Steel Support & Details | 523213-01-RFAS-ST-0013 | 2026-02-22 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
14 | Civil & Structure | 523213-01-SDW-ST-2300 | Level 3 - Steel Support & Details | 523213-01-RFAS-ST-0014 | 2026-03-19 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
15 | Civil & Structure | 523213-01-SDW-ST-2400 | Level 4 - Steel Support & Details | 523213-01-RFAS-ST-0015 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
16 | Civil & Structure | 523213-01-SDW-ST-2500 | Level 5 - Steel Support & Details | 523213-01-RFAS-ST-0016 | 2026-03-28 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
17 | Civil & Structure | 523213-01-SDW-ST-2600 | Level 6 - Steel Support & Details | 523213-01-RFAS-ST-0017 | 2026-03-15 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
18 | Civil & Structure | 523213-01-SDW-ST-2700 | Roof Deck Cooling Tower Platform Steel Details | 523213-01-RFAS-ST-0018 | 2026-03-22 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
19 | Civil & Structure | 523213-01-SDW-ST-3000 | Typical Detail | 523213-01-RFAS-ST-0019 | 2026-03-05 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Planned Submission = [Planned Submission, row below]+14
Planned Submission = [Planned Submission, row above]

## EL
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [14 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. |  | RFAS Doc No. | System | PIC | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Rev 6 |  |  |  |  | Rev 7 |  |  |  |  | Rev 8 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[16 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Electrical | 523213-01-SDW-EL-0001 | Electrical Drawing Index | 523213-01-RFAS-EL-0001 | General |  | 2026-03-31 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
2 | Electrical | 523213-01-SDW-EL-0002 | Legend, Abbreviation, And General Notes | 523213-01-RFAS-EL-0002 | General | Tong | 2026-01-16 | 2026-02-03 | 2026-02-10 | 1 | STT | Pending |  | GC |  | 2026-01-16 | 2026-01-21 | 2026-01-26 | 2026-02-02 | C | 2026-02-03 | 2026-02-04 | 2026-02-09 | [37 empty] | NO
3 | Electrical | 523213-01-SDW-EL-0010 | Medium Voltage Overall Distribution Schematic | 523213-01-RFAS-EL-0003 | MV | Ao | 2026-01-16 | 2026-01-23 | 2026-01-30 | 0 | STT | Pending |  | GC |  | 2026-01-23 | 2026-01-27 | 2026-01-29 | [42 empty] | YES
4 | Electrical | 523213-01-SDW-EL-0011 | Generator Allocation Schematic | 523213-01-RFAS-EL-0004 | SLD | AO | 2026-01-16 | 2026-01-17 | 2026-01-24 | 0 | STT | Pending |  | GC |  | 2026-01-17 | 2026-01-27 | 2026-01-29 | [42 empty] | YES
5 | Electrical | 523213-01-SDW-EL-0020 | Medium Voltage And Communications Routing Layout | 523213-01-RFAS-EL-0005 | MV | Yin | 2026-01-31 | [6 empty] | GC | ENG Review. Pending | [45 empty] | YES
6 | Electrical | 523213-01-SDW-EL-0101 | LV Single Line Diagram IT Load For Typical 4 MW With 2N Configuration Sheet 1 | 523213-01-RFAS-EL-0006 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
7 | Electrical | 523213-01-SDW-EL-0102 | LV Single Line Diagram IT Load For Typical 4 MW With 2N Configuration Sheet 2 | 523213-01-RFAS-EL-0007 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
8 | Electrical | 523213-01-SDW-EL-0103 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 1 | 523213-01-RFAS-EL-0008 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
9 | Electrical | 523213-01-SDW-EL-0104 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 2 | 523213-01-RFAS-EL-0009 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
10 | Electrical | 523213-01-SDW-EL-0105 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 3 | 523213-01-RFAS-EL-0010 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
11 | Electrical | 523213-01-SDW-EL-0106 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 4 | 523213-01-RFAS-EL-0011 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
12 | Electrical | 523213-01-SDW-EL-0107 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 5 | 523213-01-RFAS-EL-0012 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
13 | Electrical | 523213-01-SDW-EL-0108 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 6 | 523213-01-RFAS-EL-0013 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
14 | Electrical | 523213-01-SDW-EL-0109 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 1 | 523213-01-RFAS-EL-0014 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
15 | Electrical | 523213-01-SDW-EL-0110 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 2 | 523213-01-RFAS-EL-0015 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
16 | Electrical | 523213-01-SDW-EL-0111 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 3 | 523213-01-RFAS-EL-0016 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
17 | Electrical | 523213-01-SDW-EL-0112 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 4 | 523213-01-RFAS-EL-0017 | SLD | Ao | 2026-01-16 | 2026-01-16 | 2026-01-23 | 0 | CTA | Pending |  | GC |  | 2026-01-16 | [44 empty] | YES
18 | Electrical | 523213-01-SDW-EL-0113 | LV Single Line Diagram For Swing Power System Sheet 1 | 523213-01-RFAS-EL-0018 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-01-30 | 2026-02-02 | [42 empty] | YES
19 | Electrical | 523213-01-SDW-EL-0114 | LV Single Line Diagram For Swing Power System Sheet 2 | 523213-01-RFAS-EL-0019 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-01-30 | 2026-02-02 | [42 empty] | YES
20 | Electrical | 523213-01-SDW-EL-0115 | LV Single Line Diagram For Swing Power System Sheet 3 | 523213-01-RFAS-EL-0020 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-01-30 | 2026-02-02 | [42 empty] | YES
21 | Electrical | 523213-01-SDW-EL-0116 | LV Single Line Diagram For Non-It Power System Sheet 1 | 523213-01-RFAS-EL-0021 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-01-30 | 2026-02-02 | [42 empty] | YES
22 | Electrical | 523213-01-SDW-EL-0117 | LV Single Line Diagram For Non-It Power System Sheet 2 | 523213-01-RFAS-EL-0022 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-02-03 | 2026-02-09 | [42 empty] | YES
23 | Electrical | 523213-01-SDW-EL-0118 | LV Single Line Diagram For Non-It Power System Sheet 3 | 523213-01-RFAS-EL-0023 | SLD | Ao | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | STT | Pending |  | GC |  | 2026-01-19 | 2026-01-30 | 2026-02-02 | [42 empty] | YES
24 | Electrical | 523213-01-SDW-EL-0119 | LV Single Line Diagram Typical For Data Hall PDU | 523213-01-RFAS-EL-0024 | SLD | Ao | 2026-01-19 | 2026-01-22 | 2026-01-29 | 0 | STT | Pending |  | GC |  | 2026-01-22 | 2026-01-28 | 2026-01-29 | [42 empty] | YES
25 | Electrical | 523213-01-SDW-EL-0119-1 | LV Single Line Diagram PDU For MDF Room A |  |  | Ao | [7 empty] | GC
26 | Electrical | 523213-01-SDW-EL-0119-2 | LV Single Line Diagram PDU For MDF Room B |  |  | Ao | [7 empty] | GC
27 | Electrical | 523213-01-SDW-EL-0119-3 | LV Single Line Diagram PDU For MDF Room C |  |  | Ao | [7 empty] | GC
28 | Electrical | 523213-01-SDW-EL-0120 | DC Supply Schematic For HV Equipment | 523213-01-RFAS-EL-0025 | SLD | Ao | 2026-01-19 | 2026-01-22 | 2026-01-29 | 0 | STT | Pending |  | GC |  | 2026-01-22 | 2026-01-28 | 2026-01-30 | [42 empty] | NO
29 | Electrical | 523213-01-SDW-EL-0121 | LV Single Line Diagram For Fan Wall UPS For Level 2 | 523213-01-RFAS-EL-0026 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-28 | 2026-01-30 | [42 empty] | NO
30 | Electrical | 523213-01-SDW-EL-0122 | LV Single Line Diagram For Fan Wall UPS For Level 3 | 523213-01-RFAS-EL-0027 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-28 | 2026-01-30 | [42 empty] | NO
31 | Electrical | 523213-01-SDW-EL-0123 | LV Single Line Diagram For Fan Wall UPS For Level 4 | 523213-01-RFAS-EL-0028 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-28 | 2026-01-30 | [42 empty] | NO
32 | Electrical | 523213-01-SDW-EL-0124 | LV Single Line Diagram For Fan Wall UPS For Level 5 | 523213-01-RFAS-EL-0029 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-28 | 2026-01-30 | [42 empty] | NO
33 | Electrical | 523213-01-SDW-EL-0125 | LV Single Line Diagram For Fan Wall OUSB For Level 2 and Level 3 | 523213-01-RFAS-EL-0030 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-27 | 2026-01-30 | [42 empty] | NO
34 | Electrical | 523213-01-SDW-EL-0126 | LV Single Line Diagram For Fan Wall OUSB For Level 4 and Level 5 | 523213-01-RFAS-EL-0031 | SLD | Ao | 2026-01-23 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-27 | 2026-01-30 | [42 empty] | NO
35 | Electrical | 523213-01-SDW-EL-0130 | LV Single Line Diagram For Load Bank | 523213-01-RFAS-EL-0032 | SLD | Ao | 2026-01-19 | 2026-01-24 | 2026-01-31 | 0 | STT | Pending |  | GC |  | 2026-01-24 | 2026-01-27 | 2026-02-02 | [42 empty] | YES
36 | Electrical | 523213-01-SDW-EL-0140 | LV Single Line Diagram For Chiller Plant MSSB | 523213-01-RFAS-EL-0033 | SLD | Ao | 2026-01-23 | 2026-02-02 | 2026-02-09 | 0 | STT | Pending |  | GC |  | 2026-02-02 | 2026-02-04 | 2026-02-09 | [42 empty] | NO
37 | Electrical | 523213-01-SDW-EL-0141 | LV Single Line Diagram For Building NON-IT UPS | 523213-01-RFAS-EL-0034 | SLD | Ao | 2026-01-23 | 2026-02-02 | 2026-02-09 | 0 | STT | Pending |  | GC |  | 2026-02-02 | 2026-02-04 | 2026-02-09 | [42 empty] | NO
38 | Electrical | 523213-01-SDW-EL-0142 | LV Single Line Diagram For Building Load Sheet 1 | 523213-01-RFAS-EL-0035 | SLD | Ao | 2026-01-23 | 2026-02-05 | 2026-02-12 | 0 | AUR | Pending |  | GC |  | 2026-02-05 | 2026-02-11 | [43 empty] | NO
39 | Electrical | 523213-01-SDW-EL-0143 | LV Single Line Diagram For Building Load Sheet 2 | 523213-01-RFAS-EL-0036 | SLD | Ao | 2026-01-23 | 2026-02-05 | 2026-02-12 | 0 | AUR | Pending |  | GC |  | 2026-02-05 | 2026-02-11 | [43 empty] | NO
40 | Electrical | 523213-01-SDW-EL-0144 | LV Single Line Diagram For Building Load Sheet 3 | 523213-01-RFAS-EL-0037 | SLD | Ao | 2026-01-23 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
41 | Electrical | 523213-01-SDW-EL-0145 | LV Single Line Diagram For Building Load Sheet 4 | 523213-01-RFAS-EL-0038 | SLD | Ao | 2026-01-23 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
42 | Electrical | 523213-01-SDW-EL-0146 | LV Single Line Diagram For Building Load Sheet 5 | 523213-01-RFAS-EL-0039 | SLD | Ao | 2026-01-23 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
43 | Electrical | 523213-01-SDW-EL-0147 | LV Single Line Diagram For Building Load Sheet 6 | 523213-01-RFAS-EL-0040 | SLD | Ao | 2026-01-23 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
44 | Electrical | 523213-01-SDW-EL-0170 | Automatic Fire Detection And Alarm System Schematic | 523213-01-RFAS-EL-0041 | FA | Eimon | 2026-01-26 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | [45 empty] | NO
45 | Electrical | 523213-01-SDW-EL-0171 | Public Address And Voice Alarm System Schematic | 523213-01-RFAS-EL-0042 | PA | Eimon | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0021 | [45 empty] | NO
46 | Electrical | 523213-01-SDW-EL-0172 | Lighting Control System Schematic | 523213-01-RFAS-EL-0043 | LTG-C | Tone-Pang | 2026-02-04 | [6 empty] | GC | ENG Review. RFI-EL-0021 | [45 empty] | NO
47 | Electrical | 523213-01-SDW-EL-0173 | Data Cabling System Schematic | 523213-01-RFAS-EL-0044 | DATA | May | 2026-02-09 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC | ENG Review. RFI-EL-0021 | 2026-02-09 | [44 empty] | YES
48 | Electrical | 523213-01-SDW-EL-0174 | Overall Security System Schematic | 523213-01-RFAS-EL-0045 | SEC | Mon Max | 2026-02-20 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. RFI-EL-0021 | [45 empty] | YES
49 | Electrical | 523213-01-SDW-EL-0175 | Lightning Protection And Grounding System Schematic | 523213-01-RFAS-EL-0046 | EARTH | Ao | 2026-01-23 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. RFI-EL-0021 | [45 empty] | NO
50 | Electrical | 523213-01-SDW-EL-0176 | Building Management System Schematic | 523213-01-RFAS-EL-0047 | ECMS | Jang | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. RFI-EL-0021 | [45 empty] | YES
51 | Electrical | 523213-01-SDW-EL-0177 | Electrical Power Monitoring System Schematic | 523213-01-RFAS-EL-0048 | ECMS | Jang | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. RFI-EL-0021 | [45 empty] | YES
52 | Electrical | 523213-01-SDW-EL-0178 | Chiller Management System Schematic | 523213-01-RFAS-EL-0049 | ECMS | Jang | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. RFI-EL-0021 | [45 empty] | YES
53 | Electrical | 523213-03-SDW-EL-0179 | Load Schedule For Level 1 | 523213-01-RFAS-EL-0050 | LOAD | Tong | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0001,0014,0016,0017,0021 | [45 empty] | NO
54 | Electrical | 523213-04-SDW-EL-0180 | Load Schedule For Level 2 | 523213-01-RFAS-EL-0051 | LOAD | Tong | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0001,0014,0016,0017,0021 | [45 empty] | NO
55 | Electrical | 523213-05-SDW-EL-0181 | Load Schedule For Level 6 | 523213-01-RFAS-EL-0052 | LOAD | Tong | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0001,0014,0016,0017,0021 | [45 empty] | NO
56 | Electrical | 523213-01-SDW-EL-0220 | Fuel System Schematic | 523213-01-RFAS-EL-0053 | ECMS | May | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
57 | Electrical | 523213-01-SDW-EL-0300 | Ecms (Bms) Point List For Level 1 | 523213-01-RFAS-EL-0054 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
59 | Electrical | 523213-02-SDW-EL-0311 | Ecms (Pms) Point List For Level 1 | 523213-01-RFAS-EL-0055 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
60 | Electrical | 523213-02-SDW-EL-0312 | Ecms (Ems) Point List For Level 1 | 523213-01-RFAS-EL-0056 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
61 | Electrical | 523213-02-SDW-EL-0320 | Ecms (Bms) Point List For Level 2 | 523213-01-RFAS-EL-0057 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
62 | Electrical | 523213-02-SDW-EL-0321 | Ecms (Pms) Point List For Level 2 | 523213-01-RFAS-EL-0058 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
63 | Electrical | 523213-02-SDW-EL-0322 | Ecms (Ems) Point List For Level 2 | 523213-01-RFAS-EL-0059 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
64 | Electrical | 523213-02-SDW-EL-0360 | Ecms (Bms) Point List For Level 6 | 523213-01-RFAS-EL-0060 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
65 | Electrical | 523213-02-SDW-EL-0361 | Ecms (Pms) Point List For Level 6 | 523213-01-RFAS-EL-0061 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
66 | Electrical | 523213-02-SDW-EL-0362 | Ecms (Ems) Point List For Level 6 | 523213-01-RFAS-EL-0062 | ECMS | Jang-May | TBC-CX |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
67 | Electrical | 523213-01-SDW-EL-0400 | Lighting Control Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0063 | LTG-C | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
68 | Electrical | 523213-01-SDW-EL-0401 | Lighting Control Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0064 | LTG-C | Tone-Pang | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
69 | Electrical | 523213-01-SDW-EL-0402 | Lighting Control Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0065 | LTG-C | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
70 | Electrical | 523213-01-SDW-EL-0500 | Data Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0066 | DATA | May | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
71 | Electrical | 523213-01-SDW-EL-0501 | Data Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0067 | DATA | May | 2026-02-09 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
72 | Electrical | 523213-01-SDW-EL-0502 | Data Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0068 | DATA | May | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
74 | Electrical | 523213-01-SDW-EL-0601 | Fire Alarm Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0070 | FA | Max-Emon | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | [45 empty] | NO
75 | Electrical | 523213-01-SDW-EL-0602 | Fire Alarm Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0071 | FA | Max-Emon | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | [45 empty] | NO
73 | Electrical | 523213-01-SDW-EL-0600 | Fire Alarm Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0069 | FA | Max-Emon | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | [45 empty] | NO
76 | Electrical | 523213-01-SDW-EL-0603 | Fire Alarm Temincal Box Diagram For Level 1 | 523213-01-RFAS-EL-0072 | FA | Max-Emon | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | Pending subcon submit | [45 empty] | NO
77 | Electrical | 523213-01-SDW-EL-0604 | Fire Alarm Temincal Box Diagram For Level 2 | 523213-01-RFAS-EL-0073 | FA | Max-Emon | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | Pending subcon submit | [45 empty] | NO
78 | Electrical | 523213-01-SDW-EL-0605 | Fire Alarm Temincal Box Diagram For Level 6 | 523213-01-RFAS-EL-0074 | FA | Max-Emon | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | Pending subcon submit | [45 empty] | NO
79 | Electrical | 523213-01-SDW-EL-0610 | Public Address Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0075 | PA | Max-Emon | 2026-02-14 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
80 | Electrical | 523213-01-SDW-EL-0611 | Public Address Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0076 | PA | Max-Emon | 2026-01-30 | 2026-02-12 | 2026-02-19 | 0 | CTA | Pending |  | GC |  | 2026-02-12 | [44 empty] | NO
81 | Electrical | 523213-01-SDW-EL-0612 | Public Address Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0077 | PA | Max-Emon | 2026-02-07 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
82 | Electrical | 523213-01-SDW-EL-0620 | Pre-Action Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0078 | FI |  | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | Please Cancel from EL to FI | [45 empty] | NO
83 | Electrical | 523213-01-SDW-EL-0621 | Pre-Action Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0079 | FI |  | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | Please Cancel from EL to FI | [45 empty] | NO
84 | Electrical | 523213-01-SDW-EL-0622 | Pre-Action Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0080 | FI |  | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | Please Cancel from EL to FI | [45 empty] | NO
85 | Electrical | 523213-01-SDW-EL-0630 | Aspirated Smoke Detection System Diagram For Level 1 | 523213-01-RFAS-EL-0081 | ASD | May | 2026-03-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
86 | Electrical | 523213-01-SDW-EL-0631 | Aspirated Smoke Detection System Diagram For Level 2 | 523213-01-RFAS-EL-0082 | ASD | May | 2026-03-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
87 | Electrical | 523213-01-SDW-EL-0631 | Aspirated Smoke Detection System Diagram For Level 3 | 523213-01-RFAS-EL-0083 | ASD | May | 2026-03-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
88 | Electrical | 523213-01-SDW-EL-0632 | Aspirated Smoke Detection System Diagram For Level 6 | 523213-01-RFAS-EL-0084 | ASD | May | 2026-03-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
89 | Electrical | 523213-01-SDW-EL-0700 | Security (Cctv) Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0085 | SEC | Eimon | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | RFI-EL-0019 | [45 empty] | NO
90 | Electrical | 523213-01-SDW-EL-0701 | Security (Cctv) Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0086 | SEC | Eimon | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
91 | Electrical | 523213-01-SDW-EL-0702 | Security (Cctv) Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0087 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
92 | Electrical | 523213-01-SDW-EL-0703 | Security (Cctv) Schematic Diagram For Level Roof | 523213-01-RFAS-EL-0088 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
93 | Electrical | 523213-01-SDW-EL-0710 | Security (Acs) Schematic Diagram For Level 1 | 523213-01-RFAS-EL-0089 | SEC | Eimon | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
94 | Electrical | 523213-01-SDW-EL-0711 | Security (Acs) Schematic Diagram For Level 2 | 523213-01-RFAS-EL-0090 | SEC | Eimon | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
95 | Electrical | 523213-01-SDW-EL-0712 | Security (Acs) Schematic Diagram For Level 6 | 523213-01-RFAS-EL-0091 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
96 | Electrical | 523213-01-SDW-EL-0713 | Security (Acs) Schematic Diagram For Level Roof | 523213-01-RFAS-EL-0092 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
97 | Electrical | 523213-01-SDW-EL-1000 | TX | 523213-01-RFAS-EL-0093 | FACTORY | Max | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | YES
98 | Electrical | 523213-01-SDW-EL-1001 | HVSB | 523213-01-RFAS-EL-0094 | FACTORY | Max | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | YES
99 | Electrical | 523213-01-SDW-EL-1002 | RMU | 523213-01-RFAS-EL-0095 | FACTORY | Max | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | YES
100 | Electrical | 523213-01-SDW-EL-1003 | MVBTU and MVBATT Details | 523213-01-RFAS-EL-0096 | FACTORY | Max | TBC | 2026-01-27 | 2026-02-03 | 0 | STT | Pending |  | LLE | SE-BTU-523213-01-RFAS-EL-001 | 2026-01-27 | 2026-01-27 | 2026-02-02 | [42 empty] | YES
101 | Electrical | 523213-01-SDW-EL-1004 | RCP | 523213-01-RFAS-EL-0097 | FACTORY | Max | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | YES
102 | Electrical | 523213-01-SDW-EL-1005 | Schematic Diagram For AIS Switchgear | 523213-01-RFAS-EL-0098 | FACTORY | Max | TBC | 2026-01-27 | 2026-02-03 | 0 | STT | Pending |  | LLE | SE-AIS-523213-01-RFAS-EL-003 | 2026-01-27 | 2026-01-27 | 2026-02-02 | [42 empty] | YES
103 | Electrical | 523213-01-SDW-EL-1006 | Schematic Diagram for RMU | 523213-01-RFAS-EL-0099 | FACTORY | Max | TBC | 2026-01-30 | 2026-02-06 | 0 | AUR | Pending |  | LLE |  | 2026-01-30 | 2026-02-02 | [43 empty] | YES
104 | Electrical | 523213-01-SDW-EL-1007 | Control Logic for AIS Switchgear | 523213-01-RFAS-EL-0100 | FACTORY |  | TBC | 2026-02-05 | 2026-02-12 | 1 | AUR | Pending |  | LLE |  | 2025-12-16 | 2025-12-22 | 2026-01-13 | 2026-01-21 | C | 2026-02-05 | 2026-02-12 | [38 empty] | NO
105 | Electrical | 523213-01-SDW-EL-1008 | Control Logic for RMU | 523213-01-RFAS-EL-0101 | FACTORY |  | TBC | 2025-12-16 | 2025-12-23 | 0 | GAA | C |  | LLE |  | 2025-12-16 | 2025-12-22 | 2026-01-13 | 2026-01-21 | C | [40 empty] | NO
106 | Electrical | 523213-01-SDW-EL-1009 | For Manufacturing Drawing | 523213-01-RFAS-EL-0102 | FACTORY |  | TBC |  | 1900-01-06 |  |  |  |  | LLE |  | 2026-02-08 | [44 empty] | NO
107 | Electrical | 523213-01-SDW-EL-1010 | For Manufacturing Drawing | 523213-01-RFAS-EL-0103 | FACTORY |  | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | NO
108 | Electrical | 523213-01-SDW-EL-2100 | Level 1 - Mv Cable Routing Layout | 523213-01-RFAS-EL-0104 | MV | Yin | 2026-02-09 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. | [45 empty] | NO
110 | Electrical | 523213-01-SDW-EL-2101 | Level 1 - LV Cable Routing Layout | 523213-01-RFAS-EL-0105 | LV | Aon-Ao | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
112 | Electrical | 523213-01-SDW-EL-2102 | Level 1 - Aux Power Routing Layout | 523213-01-RFAS-EL-0106 | LV | Tong | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
113 | Electrical | 523213-01-SDW-EL-2103 | Level 1 - Mvdc Cable Routing Layout | 523213-01-RFAS-EL-0107 | MV | Tong | 2026-02-09 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
115 | Electrical | 523213-01-SDW-EL-2200 | Level 2 - MV Cable Routing Layout | 523213-01-RFAS-EL-0108 | MV | Ao | 2026-02-02 | 2026-02-02 | 2026-02-09 | 0 | AUR | Pending |  | GC |  | 2026-02-02 | 2026-02-12 | [43 empty] | NO
117 | Electrical | 523213-01-SDW-EL-2201 | Level 2 - LV Cable Routing Layout | 523213-01-RFAS-EL-0109 | LV | Aon-Ao | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
119 | Electrical | 523213-01-SDW-EL-2202 | Level 2 - Aux Power Routing Layout | 523213-01-RFAS-EL-0110 | LV | Tong-Yin | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0001,RFI-EL-0016 | [45 empty] | NO
120 | Electrical | 523213-01-SDW-EL-2203 | Level 2 - Mvdc Cable Routing Layout | 523213-01-RFAS-EL-0111 | MV | Tong | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. | [45 empty] | NO
122 | Electrical | 523213-01-SDW-EL-2204 | Level 2 - SUPS Batt Cable Routing Layout | 523213-01-RFAS-EL-0112 | LV | Ao | 2026-02-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
123 | Electrical | 523213-01-SDW-EL-2205 | Level 2 - SUPS Control Cable Routing Layout | 523213-01-RFAS-EL-0113 | LV | Ao | 2026-02-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
124 | Electrical | 523213-01-SDW-EL-2210 | Level 2 - Busduct Routing Layout Overall | 523213-01-RFAS-EL-0114 | BD | Aon-May | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
125 | Electrical | 523213-01-SDW-EL-2211 | Level 2 - LV Busduct Routing Layout | 523213-01-RFAS-EL-0115 | BD | Aon-May | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
126 | Electrical | 523213-01-SDW-EL-2212 | Level 2 - LV Busduct Isometric | 523213-01-RFAS-EL-0116 | BD | Aon-May | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
127 | Electrical | 523213-01-SDW-EL-2213 | Level 2 - Swing & Load Bank Routing Layout | 523213-01-RFAS-EL-0117 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
128 | Electrical | 523213-01-SDW-EL-2214 | Level 2 - Swing & Load Bank Busduct Isometric | 523213-01-RFAS-EL-0118 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
129 | Electrical | 523213-01-SDW-EL-2215 | Level 2 - IT Busduct Routing Layout | 523213-01-RFAS-EL-0119 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
130 | Electrical | 523213-01-SDW-EL-2216 | Level 2 - IT Busduct Isometric | 523213-01-RFAS-EL-0120 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
131 | Electrical | 523213-01-SDW-EL-2300 | Level 3 - Electrical Routing Layout | 523213-01-RFAS-EL-0121 | LV | Ao | 2026-02-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
132 | Electrical | 523213-01-SDW-EL-2400 | Level 4 - Electrical Routing Layout | 523213-01-RFAS-EL-0122 | LV | Ao | 2026-02-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
133 | Electrical | 523213-01-SDW-EL-2500 | Level 5 - Electrical Routing Layout | 523213-01-RFAS-EL-0123 | LV | Ao | 2026-02-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
134 | Electrical | 523213-01-SDW-EL-2601 | Level 6 - MV Cable Routing Layout | 523213-01-RFAS-EL-0124 | MV | Ao | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
136 | Electrical | 523213-01-SDW-EL-2602 | Level 6 - LV Cable Routing Layout | 523213-01-RFAS-EL-0125 | LV | Aon-Ao | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
138 | Electrical | 523213-01-SDW-EL-2603 | Level 6 - Aux Power Routing Layout | 523213-01-RFAS-EL-0126 | LV | Tong-Yin | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | ENG Review. Pending RFI-EL-0001,RFI-EL-0016 | [45 empty] | NO
139 | Electrical | 523213-01-SDW-EL-2604 | Level 6 - MVDC Cable Routing Layout | 523213-01-RFAS-EL-0127 | MV | Tong | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
122 | Electrical | 523213-01-SDW-EL-2605 | Level 6 - SUPS Batt Cable Routing Layout | 523213-01-RFAS-EL-0128 | LV | Ao | 2026-02-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
123 | Electrical | 523213-01-SDW-EL-2606 | Level 6 - SUPS Control Cable Routing Layout | 523213-01-RFAS-EL-0129 | LV | Ao | 2026-02-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
141 | Electrical | 523213-01-SDW-EL-2610 | Level 6 - Busduct Routing Layout Overall | 523213-01-RFAS-EL-0130 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
142 | Electrical | 523213-01-SDW-EL-2611 | Level 6 - LV Busduct Routing Layout | 523213-01-RFAS-EL-0131 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
143 | Electrical | 523213-01-SDW-EL-2612 | Level 6 - LV Busduct Isometric | 523213-01-RFAS-EL-0132 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
144 | Electrical | 523213-01-SDW-EL-2613 | Level 6 - Swing & Load Bang Busduct Routing Layout | 523213-01-RFAS-EL-0133 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
145 | Electrical | 523213-01-SDW-EL-2614 | Level 6 - Swing & Load Bang Busduct Isometric | 523213-01-RFAS-EL-0134 | BD | Aon-May |  |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
146 | Electrical | 523213-01-SDW-EL-2700 | Level Roof - LV Cable Routing Layout | 523213-01-RFAS-EL-0135 | LV | Max | 2026-03-31 |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
147 | Electrical | 523213-01-SDW-EL-3100 | Level 1 - Cable Basket Routinh Layout | 523213-01-RFAS-EL-0136 | COM | Jang-May | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
148 | Electrical | 523213-01-SDW-EL-3101 | Level 1 - Fiber Guide Routing Layout | 523213-01-RFAS-EL-0137 | COM | Jang-May | 2026-02-25 | Cancel | #VALUE! |  |  |  |  | GC | [46 empty] | NO
149 | Electrical | 523213-01-SDW-EL-3106 | Level 1 - ECMS Routing Layout | 523213-01-RFAS-EL-0138 | ECMS | Jang-May | 2026-03-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
150 | Electrical | 523213-01-SDW-EL-3107 | Level 1 - Bms Routing Layout | 523213-01-RFAS-EL-0139 | ECMS | Jang-May | 2026-03-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
151 | Electrical | 523213-01-SDW-EL-3108 | Level 1 - Pms&Ems Routing Layout | 523213-01-RFAS-EL-0140 | ECMS | Jang-May | 2026-03-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
152 | Electrical | 523213-01-SDW-EL-3109 | Level 1 - Fuel Control Routing Layout | 523213-01-RFAS-EL-0141 | ECMS | Jang-May | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
153 | Electrical | 523213-01-SDW-EL-3200 | Level 2 - Cable Basket Routing Layout | 523213-01-RFAS-EL-0142 | COM | Jang-May | 2026-02-18 | 2026-02-11 | 2026-02-18 | 0 | AUR | Pending |  | GC |  | 2026-02-11 | 2026-02-12 | [43 empty] | NO
154 | Electrical | 523213-01-SDW-EL-3201 | Level 2 - Fiber Guide Routing Layout | 523213-01-RFAS-EL-0143 | COM | Jang-May | 2026-02-18 | 2026-02-11 | 2026-02-18 | 0 | AUR | Pending |  | GC |  | 2026-02-11 | 2026-02-12 | [43 empty] | YES
155 | Electrical | 523213-01-SDW-EL-3206 | Level 2 - ECMS Routing Layout | 523213-01-RFAS-EL-0144 | ECMS | Jang-May | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
156 | Electrical | 523213-01-SDW-EL-3207 | Level 2 - BMS Routing Layout | 523213-01-RFAS-EL-0145 | ECMS | Jang-May | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
157 | Electrical | 523213-01-SDW-EL-3208 | Level 2 - PMS & EMS Routing Layout | 523213-01-RFAS-EL-0146 | ECMS | Jang-May | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
158 | Electrical | 523213-01-SDW-EL-3209 | Level 2 - Fuel Control Routing Layout | 523213-01-RFAS-EL-0147 | ECMS | Jang-May | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
159 | Electrical | 523213-01-SDW-EL-3300 | Level 3 - Communications Routing Layout | 523213-01-RFAS-EL-0148 | ECMS | Jang-May | 2026-02-27 | 2026-02-12 | 2026-02-19 | 0 | CTA | Pending |  | GC |  | 2026-02-12 | [44 empty] | NO
160 | Electrical | 523213-01-SDW-EL-3400 | Level 4 - Communications Routing Layout | 523213-01-RFAS-EL-0149 | ECMS | Jang-May | 2026-02-27 | 2026-02-12 | 2026-02-19 | 0 | CTA | Pending |  | GC |  | 2026-02-12 | [44 empty] | YES
161 | Electrical | 523213-01-SDW-EL-3500 | Level 5 - Communications Routing Layout | 523213-01-RFAS-EL-0150 | ECMS | Jang-May | 2026-02-27 | 2026-02-12 | 2026-02-19 | 0 | CTA | Pending |  | GC |  | 2026-02-12 | [44 empty] | YES
162 | Electrical | 523213-01-SDW-EL-3604 | Level 6 - ECMS Routing Layout | 523213-01-RFAS-EL-0151 | ECMS | Jang-May | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
163 | Electrical | 523213-01-SDW-EL-3605 | Level 6 - Bms Routing Layout | 523213-01-RFAS-EL-0152 | ECMS | Jang-May | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
164 | Electrical | 523213-01-SDW-EL-3606 | Level 6 - PMS & EMS Routing Layout | 523213-01-RFAS-EL-0153 | ECMS | Jang-May | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
165 | Electrical | 523213-01-SDW-EL-3607 | Level 6 - Fuel Control Routing Layout | 523213-01-RFAS-EL-0154 | ECMS | Jang-May | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
166 | Electrical | 523213-01-SDW-EL-3700 | Level Roof - Communications Routing Layout | 523213-01-RFAS-EL-0155 | ECMS | Jang-May | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
167 | Electrical | 523213-01-SDW-EL-4100 | Level 1 - General Lighting System Layout | 523213-01-RFAS-EL-0156 | LTG | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
168 | Electrical | 523213-01-SDW-EL-4101 | Level 1 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0157 | LTG-EMER | Tone-Pang | 2026-02-26 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
169 | Electrical | 523213-01-SDW-EL-4102 | Level 1 - Lighting Control Layout | 523213-01-RFAS-EL-0158 | LTG-C | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
170 | Electrical | 523213-01-SDW-EL-4200 | Level 2 - General Lighting System Layout | 523213-01-RFAS-EL-0159 | LTG | Tone-Pang | 2026-02-04 | 2026-02-10 | 2026-02-17 | 0 | CTA | Pending |  | GC |  | 2026-02-10 | [44 empty] | NO
171 | Electrical | 523213-01-SDW-EL-4201 | Level 2 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0160 | LTG-EMER | Tone-Pang | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
172 | Electrical | 523213-01-SDW-EL-4202 | Level 2 - Lighting Control Layout | 523213-01-RFAS-EL-0161 | LTG-C | Tone-Pang | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
173 | Electrical | 523213-01-SDW-EL-4300 | Level 3 - General Lighting System Layout | 523213-01-RFAS-EL-0162 | LTG | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC
174 | Electrical | 523213-01-SDW-EL-4301 | Level 3 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0163 | LTG-EMER | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
175 | Electrical | 523213-01-SDW-EL-4400 | Level 4 - General Lighting System Layout | 523213-01-RFAS-EL-0164 | LTG | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
176 | Electrical | 523213-01-SDW-EL-4401 | Level 4 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0165 | LTG-EMER | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
177 | Electrical | 523213-01-SDW-EL-4500 | Level 5 - General Lighting System Layout | 523213-01-RFAS-EL-0166 | LTG | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
178 | Electrical | 523213-01-SDW-EL-4501 | Level 5 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0167 | LTG-EMER | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
179 | Electrical | 523213-01-SDW-EL-4600 | Level 6 - General Lighting System Layout | 523213-01-RFAS-EL-0168 | LTG | Tone-Pang | 2026-02-11 | 2026-02-10 | 2026-02-17 | 0 | CTA | Pending |  | GC |  | 2026-02-10 | [44 empty] | NO
180 | Electrical | 523213-01-SDW-EL-4601 | Level 6 - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0169 | LTG-EMER | Tone-Pang | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
181 | Electrical | 523213-01-SDW-EL-4602 | Level 6 - Lighting Control Layout | 523213-01-RFAS-EL-0170 | LTG-C | Tone-Pang | 2026-02-18 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
182 | Electrical | 523213-01-SDW-EL-4700 | Level Roof - General Lighting System Layout | 523213-01-RFAS-EL-0171 | LTG | Tone-Pang | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
183 | Electrical | 523213-01-SDW-EL-4701 | Level Roof - Emergency Light And Exit Sign Systems Layout | 523213-01-RFAS-EL-0172 | LTG-EMER | Tone-Pang | 2026-02-26 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
184 | Electrical | 523213-01-SDW-EL-5100 | Level 1 - Power And Receptacle Outlet System Layout | 523213-01-RFAS-EL-0173 | PWR-REC | Tone-Pang | 2026-02-14 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
185 | Electrical | 523213-01-SDW-EL-5101 | Level 1 - Power Supply Mech System Layout, | 523213-01-RFAS-EL-0174 | PWR | Yin | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
186 | Electrical | 523213-01-SDW-EL-5102 | Level 1 - Power Supply Mcp System Layout | 523213-01-RFAS-EL-0175 | PWR | Yin | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
187 | Electrical | 523213-01-SDW-EL-5103 | Level 1 - Data Outlet System Layout | 523213-01-RFAS-EL-0176 | DATA | May | 2026-02-17 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
188 | Electrical | 523213-01-SDW-EL-5104 | Level 1 - Ceeform System Layout | 523213-01-RFAS-EL-0177 | PWR | Jang | 2026-03-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
189 | Electrical | 523213-01-SDW-EL-5200 | Level 2 - Power And Receptacle Outlet System Layout | 523213-01-RFAS-EL-0178 | PWR-REC | Tone-Pang | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
190 | Electrical | 523213-01-SDW-EL-5201 | Level 2 - Power Supply Mech System Layout | 523213-01-RFAS-EL-0179 | PWR | Tone | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
191 | Electrical | 523213-01-SDW-EL-5202 | Level 2 - Power Supply Mcp System Layout | 523213-01-RFAS-EL-0180 | PWR | Tone | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
192 | Electrical | 523213-01-SDW-EL-5203 | Level 2 - Data Outlet System Layout | 523213-01-RFAS-EL-0181 | DATA | May | 2026-02-09 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
193 | Electrical | 523213-01-SDW-EL-5204 | Level 2 - Ceeform System Layout | 523213-01-RFAS-EL-0182 | PWR | Jang | 2026-03-13 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
194 | Electrical | 523213-01-SDW-EL-5300 | Level 3 - Power ,Voice And Data Outlet System Layout | 523213-01-RFAS-EL-0183 | PWR-REC | Tone-Pang | 2026-02-21 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
195 | Electrical | 523213-01-SDW-EL-5400 | Level 4 - Power ,Voice And Data Outlet System Layout | 523213-01-RFAS-EL-0184 | PWR-REC | Tone-Pang | 2026-02-21 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
196 | Electrical | 523213-01-SDW-EL-5500 | Level 5 - Power ,Voice And Data Outlet System Layout | 523213-01-RFAS-EL-0185 | PWR-REC | Tone-Pang | 2026-02-21 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
197 | Electrical | 523213-01-SDW-EL-5600 | Level 6 - Power And Receptacle Outlet System Layout | 523213-01-RFAS-EL-0186 | PWR-REC | Tone-Pang | 2026-02-13 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
198 | Electrical | 523213-01-SDW-EL-5601 | Level 6 - Power Supply Mech System Layout | 523213-01-RFAS-EL-0187 | PWR | Yin | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
199 | Electrical | 523213-01-SDW-EL-5602 | Level 6 - Power Supply Mcp System Layout | 523213-01-RFAS-EL-0188 | PWR | Yin | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
200 | Electrical | 523213-01-SDW-EL-5603 | Level 6 - Data Outlet System Layout | 523213-01-RFAS-EL-0189 | DATA | May | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
201 | Electrical | 523213-01-SDW-EL-5700 | Level Roof - Power ,Voice And Data Outlet System Layout | 523213-01-RFAS-EL-0190 | PWR | Tone-Pang | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
202 | Electrical | 523213-01-SDW-EL-6100 | Level 1 - Fire Alarm System Layout | 523213-01-RFAS-EL-0191 | FA | MAX | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
203 | Electrical | 523213-01-SDW-EL-6101 | Level 1 - Public Address System Layout | 523213-01-RFAS-EL-0192 | PA | MAX | 2026-02-14 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
204 | Electrical | 523213-01-SDW-EL-6102 | Level 1 - Aspirated Smoke Detection Layout | 523213-01-RFAS-EL-0193 | ASD | MAY | 2026-03-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
205 | Electrical | 523213-01-SDW-EL-6200 | Level 2 - Fire Alarm System Layout | 523213-01-RFAS-EL-0194 | FA | MAX | 2026-01-30 | 2026-02-12 | 2026-02-19 | 0 | CTA | Pending |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | 2026-02-12 | [44 empty] | NO
206 | Electrical | 523213-01-SDW-EL-6201 | Level 2 - Public Address System Layout | 523213-01-RFAS-EL-0195 | PA | MAX | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | AUR | Pending |  | GC |  | 2026-02-05 | 2026-02-12 | [43 empty] | NO
207 | Electrical | 523213-01-SDW-EL-6202 | Level 2 - Aspirated Smoke Detection Layout | 523213-01-RFAS-EL-0196 | ASD | MAY | 2026-03-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
208 | Electrical | 523213-01-SDW-EL-6300 | Level 3 - Fire Alarm System Layout | 523213-01-RFAS-EL-0197 | FA | MAX | 2026-01-30 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-EL-0007,RFI-EL-0022,RFI-EL-0029 | [45 empty] | NO
209 | Electrical | 523213-01-SDW-EL-6301 | Level 3 - Public Address System Layout | 523213-01-RFAS-EL-0198 | PA | MAX | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | AUR | Pending |  | GC |  | 2026-02-05 | 2026-02-12 | [43 empty] | NO
210 | Electrical | 523213-01-SDW-EL-6302 | Level 3 - Aspirated Smoke Detection Layout | 523213-01-RFAS-EL-0199 | ASD | MAY | 2026-03-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
211 | Electrical | 523213-01-SDW-EL-6400 | Level 4 - Fire Alarm System Layout | 523213-01-RFAS-EL-0200 | FA | MAX | 2026-02-02 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
212 | Electrical | 523213-01-SDW-EL-6401 | Level 4 - Public Address System Layout | 523213-01-RFAS-EL-0201 | PA | MAX | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
213 | Electrical | 523213-01-SDW-EL-6500 | Level 5 - Fire Alarm System Layout | 523213-01-RFAS-EL-0202 | FA | MAX | 2026-02-02 | 2026-02-09 | 2026-02-16 | 0 | CTA | Pending |  | GC |  | 2026-02-09 | [44 empty] | NO
214 | Electrical | 523213-01-SDW-EL-6501 | Level 5 - Public Address System Layout | 523213-01-RFAS-EL-0203 | PA | MAX | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
215 | Electrical | 523213-01-SDW-EL-6600 | Level 6 - Fire Alarm System Layout | 523213-01-RFAS-EL-0204 | FA | MAX | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | ENG Review | [45 empty] | NO
216 | Electrical | 523213-01-SDW-EL-6601 | Level 6 - Public Address System Layout | 523213-01-RFAS-EL-0205 | PA | MAX | 2026-02-07 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
217 | Electrical | 523213-01-SDW-EL-6602 | Level 6 - Aspirated Smoke Detection Layout | 523213-01-RFAS-EL-0206 | ASD | May | 2026-03-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
218 | Electrical | 523213-01-SDW-EL-6700 | Level Roof - Fire Alarm System Layout | 523213-01-RFAS-EL-0207 | FA | Max | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
219 | Electrical | 523213-01-SDW-EL-6701 | Level Roof - Public Address System Layout | 523213-01-RFAS-EL-0208 | PA | Max | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
220 | Electrical | 523213-01-SDW-EL-7100 | Level 1 - Security CCTV System Layout | 523213-01-RFAS-EL-0209 | SEC | Eimon | 2026-03-17 | 2026-02-12 | 2026-02-19 | 1 | CTA | Pending |  | GC |  | 2026-02-05 | 2026-02-12 |  |  |  | 2026-02-12 | [39 empty] | NO
221 | Electrical | 523213-01-SDW-EL-7101 | Level 1 - Security Access Control System Layout | 523213-01-RFAS-EL-0210 | SEC | Eimon | 2026-03-17 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
222 | Electrical | 523213-01-SDW-EL-7200 | Level 2 - Security CCTV System Layout | 523213-01-RFAS-EL-0211 | SEC | Eimon | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
223 | Electrical | 523213-01-SDW-EL-7201 | Level 2 - Security Access Control System Layout | 523213-01-RFAS-EL-0212 | SEC | Eimon | 2026-03-03 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
224 | Electrical | 523213-01-SDW-EL-7300 | Level 3 - Security CCTV System Layout | 523213-01-RFAS-EL-0213 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
225 | Electrical | 523213-01-SDW-EL-7301 | Level 3 - Security Access Control System Layout | 523213-01-RFAS-EL-0214 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
226 | Electrical | 523213-01-SDW-EL-7400 | Level 4 - Security CCTV System Layout | 523213-01-RFAS-EL-0215 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
227 | Electrical | 523213-01-SDW-EL-7401 | Level 4 - Security Access Control System Layout | 523213-01-RFAS-EL-0216 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
228 | Electrical | 523213-01-SDW-EL-7500 | Level 5 - Security CCTV System Layout | 523213-01-RFAS-EL-0217 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
229 | Electrical | 523213-01-SDW-EL-7501 | Level 5 - Security Access Control System Layout | 523213-01-RFAS-EL-0218 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
230 | Electrical | 523213-01-SDW-EL-7600 | Level 6 - Security CCTV System Layout | 523213-01-RFAS-EL-0219 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
231 | Electrical | 523213-01-SDW-EL-7601 | Level 6 - Security Access Control System Layout | 523213-01-RFAS-EL-0220 | SEC | Eimon | 2026-03-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
232 | Electrical | 523213-01-SDW-EL-7700 | Level Roof - Security CCTV System Layout | 523213-01-RFAS-EL-0221 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
233 | Electrical | 523213-01-SDW-EL-7701 | Level Roof - Security Access Control System Layout | 523213-01-RFAS-EL-0222 | SEC | Eimon | 2026-03-24 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
234 | Electrical | 523213-01-SDW-EL-8100 | Level 1 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0223 | EARTH | Tong | 2026-02-19 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
235 | Electrical | 523213-01-SDW-EL-8200 | Level 2 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0224 | EARTH | Tong | 2026-02-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
236 | Electrical | 523213-01-SDW-EL-8300 | Level 3 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0225 | EARTH | Tong | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
237 | Electrical | 523213-01-SDW-EL-8400 | Level 4 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0226 | EARTH | Tong | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
238 | Electrical | 523213-01-SDW-EL-8500 | Level 5 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0227 | EARTH | Tong | 2026-02-12 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
239 | Electrical | 523213-01-SDW-EL-8600 | Level 6 - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0228 | EARTH | Tong | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
240 | Electrical | 523213-01-SDW-EL-8700 | Level Roof - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0229 | EARTH | Tong | 2026-03-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | YES
241 | Electrical | 523213-01-SDW-EL-8701 | Level Top Roof - Earthing And Lightning Protection System Layout | 523213-01-RFAS-EL-0230 | EARTH | Tong | 2026-03-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
242 | Electrical | 523213-01-SDW-EL-8800 | Level 1 Equipment Setting out | 523213-01-RFAS-EL-0231 |  | ARM | 2026-03-25 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
243 | Electrical | 523213-01-SDW-EL-8801 | Level 2 Equipment Setting out | 523213-01-RFAS-EL-0232 |  | PING | 2026-03-15 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
244 | Electrical | 523213-01-SDW-EL-8802 | Level 3 Equipment Setting out | 523213-01-RFAS-EL-0233 |  | ARM | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
245 | Electrical | 523213-01-SDW-EL-8803 | Level 4 Equipment Setting out | 523213-01-RFAS-EL-0234 |  | PING | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
246 | Electrical | 523213-01-SDW-EL-8804 | Level 5 Equipment Setting out | 523213-01-RFAS-EL-0235 |  | ARM | 2026-04-10 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
247 | Electrical | 523213-01-SDW-EL-8805 | Level 6 Equipment Setting out | 523213-01-RFAS-EL-0236 |  | PING | 2026-03-20 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
248 | Electrical | 523213-01-SDW-EL-8806 | Level Roof Equipment Setting out | 523213-01-RFAS-EL-0237 |  | ARM |  |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
249 | Electrical | 523213-01-SDW-EL-9800 | Typical Details For Access Control System Sheet 1 | 523213-01-RFAS-EL-0238 | SEC | Eimon | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
250 | Electrical | 523213-01-SDW-EL-9801 | Typical Details For Access Control System Sheet 2 | 523213-01-RFAS-EL-0239 | SEC | Eimon | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
251 | Electrical | 523213-01-SDW-EL-9802 | Access Control System Schematic | 523213-01-RFAS-EL-0240 | SEC | Eimon | 2026-02-27 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
252 | Electrical | 523213-01-SDW-EL-9803 | Typical Details Sheet 1 | 523213-01-RFAS-EL-0241 | EL-Section |  | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | This Drawing Section detail. We will submit this detail in Shop drawing by Each system. | [45 empty] | NO
253 | Electrical | 523213-01-SDW-EL-9804 | Typical Details Sheet 2 | 523213-01-RFAS-EL-0242 | EL-Section |  | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
254 | Electrical | 523213-01-SDW-EL-9805 | Typical Details Sheet 3 | 523213-01-RFAS-EL-0243 | EL-Section |  | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
255 | Electrical | 523213-01-SDW-EL-9806 | Typical Details Sheet 4 | 523213-01-RFAS-EL-0244 | EL-Section |  | 2026-02-11 |  | 1900-01-06 |  |  |  |  | GC | [46 empty] | NO
256 | Electrical | 523213-01-SDW-EL-9807 | Typical Details Sheet 5 | 523213-01-RFAS-EL-0245 | Typical |  | 2026-02-11 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
257 | Electrical | 523213-01-SDW-EL-9808 | Typical Details Sheet 6 | 523213-01-RFAS-EL-0246 | Typical |  | 2026-02-11 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
258 | Electrical | 523213-01-SDW-EL-9809 | Typical Details Sheet 7 | 523213-01-RFAS-EL-0247 | Typical |  | 2026-02-11 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
259 | Electrical | 523213-01-SDW-EL-9810 | Typical Details Sheet 8 | 523213-01-RFAS-EL-0248 | Typical |  | 2026-02-11 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [44 empty] | NO
260 | Electrical | 523213-01-SDW-EL-1011 | For LLE GEN | 523213-01-RFAS-EL-0249 | LLE-GEN |  | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | NO
261 | Electrical | 523213-01-SDW-EL-1012 | For LLE GEN | 523213-01-RFAS-EL-0250 | LLE-GEN |  | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | NO
262 | Electrical | 523213-01-SDW-EL-1013 | 63A DB Aux Panel | 523213-01-RFAS-EL-0251 | LLE-GEN |  | TBC | 2026-02-10 | 2026-02-17 | 0 | AUR | Pending |  | LLE |  | 2026-02-10 | 2026-02-12 | [43 empty] | NO
263 | Electrical | 523213-01-SDW-EL-1014 | 4000A SLD GA Control | 523213-01-RFAS-EL-0252 | LLE-GEN |  | TBC | 2026-02-10 | 2026-02-17 | 0 | AUR | Pending |  | LLE |  | 2026-02-10 | 2026-02-11 | [43 empty] | NO
264 | Electrical | 523213-01-SDW-EL-1015 | For LLE GEN | 523213-01-RFAS-EL-0253 | LLE-GEN |  | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | NO
265 | Electrical | 523213-01-SDW-EL-1016 | For LLE GEN | 523213-01-RFAS-EL-0254 | LLE-GEN |  | TBC |  | 1900-01-06 |  |  |  |  | LLE | [46 empty] | NO
266 | Electrical | 523213-01-SDW-EL-1017 | Junction Box | 523213-01-RFAS-EL-0255 | LLE-GEN |  | TBC | 2026-02-11 | 2026-02-18 | 0 | AUR | Pending |  | LLE |  | 2026-02-11 | 2026-02-12 | [43 empty] | NO
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Note on R7: Panjarin Insuan: CTA ส่งเมล์ให้ AUR ไม่ได้ CC
Note on V216: Panjarin Insuan: R0 ตัวนี้ ที่ขอส่งเป็น Revise 1 เนื่องจากต้อง ขยับตำแหน่งบางตัว กล้องบางตัว หลบงาน ที่ TTI เท คอนกรีตไปแล้วครับ

## ME
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [12 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. |  | RFAS Doc No. | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Mechanical | 523213-01-SDW-ME-0001 | Mechanical Drawing Index | 523213-01-RFAS-ME-0001 |  |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
2 | Mechanical | 523213-01-SDW-ME-0010 | Mechanical Legend & Abbreviation | 523213-01-RFAS-ME-0002 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-02 | [28 empty] | NO
3 | Mechanical | 523213-01-SDW-ME-0020 | ACMV Air Side Schematic | 523213-01-RFAS-ME-0003 | 2026-01-19 | 2026-02-09 | 2026-02-16 | 0 | AUR | Pending |  | GC |  | 2026-02-09 | 2026-02-12 | [28 empty] | YES
4 | Mechanical | 523213-01-SDW-ME-0030 | Stair And Fireman Lift Lobby Pressurization Schematic | 523213-01-RFAS-ME-0004 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | AUR | Pending |  | GC |  | 2026-01-19 | 2026-02-02 | [28 empty] | YES
5 | Mechanical | 523213-01-SDW-ME-0040 | ACMV Piping System Schematic - Risers - Sheet 1 | 523213-01-RFAS-ME-0005 | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | Eng Review | [30 empty] | YES
6 | Mechanical | 523213-01-SDW-ME-0041 | ACMV Piping System Schematic - Risers - Sheet 2 |  | 2026-02-05 | [6 empty] | GC | Eng Review | [30 empty] | YES
7 | Mechanical | 523213-01-SDW-ME-0050 | ACMV Piping System Schematic - Chiller Plant | 523213-01-RFAS-ME-0006 | 2026-02-07 |  | 1900-01-06 |  |  |  |  | GC | Eng Review | [30 empty] | YES
8 | Mechanical | 523213-01-SDW-ME-0060 | Equipment Schedule | 523213-01-RFAS-ME-0007 | 2026-02-25 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0011 | [30 empty] | YES
9 | Mechanical | 523213-01-SDW-ME-1100 | Level 1 - Ducting Layout Plan | 523213-01-RFAS-ME-0008 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0013, ME-0005 | [30 empty] | NO
10 | Mechanical | 523213-01-SDW-ME-1200 | Level 2 - Ducting Layout Plan | 523213-01-RFAS-ME-0009 | 2026-02-09 | 2026-02-09 | 2026-02-16 | 0 | GAA | C | 2026-02-12 | GC |  | 2026-02-09 | 2026-02-12 |  |  | C | [25 empty] | NO
11 | Mechanical | 523213-01-SDW-ME-1600 | Level 6 - Ducting Layout Plan | 523213-01-RFAS-ME-0010 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
12 | Mechanical | 523213-01-SDW-ME-1700 | Level Roof - Ducting Layout Plan | 523213-01-RFAS-ME-0011 | 2026-04-06 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
13 | Mechanical | 523213-01-SDW-ME-2100 | Level 1 - ACMV Pipe Routing Layout Plan | 523213-01-RFAS-ME-0012 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0014, ME-0005 | [30 empty] | NO
14 | Mechanical | 523213-01-SDW-ME-2110 | Level 1 - Condensate Drain PIpe Routing Layout Plan | 523213-01-RFAS-ME-0013 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
15 | Mechanical | 523213-01-SDW-ME-2200 | Level 2 - ACMV Pipe Routing Layout Plan | 523213-01-RFAS-ME-0014 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0014 | [30 empty] | YES
16 | Mechanical | 523213-01-SDW-ME-2210 | Level 2 - Condensate Drain Pipe Routing Layout Plan | 523213-01-RFAS-ME-0015 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
17 | Mechanical | 523213-01-SDW-ME-2220 | Level 2 - Liquid Cooling Pipe Routing Layout Plan | 523213-01-RFAS-ME-0016 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
18 | Mechanical | 523213-01-SDW-ME-2600 | Level 6 - ACMV Pipe Routing Layout Plan | 523213-01-RFAS-ME-0017 | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0014 | [30 empty] | YES
19 | Mechanical | 523213-01-SDW-ME-2610 | Level 6 - Condensate Drain Pipe Routing Layout Plan | 523213-01-RFAS-ME-0018 | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
20 | Mechanical | 523213-01-SDW-ME-2620 | Level 6 - Liquid Cooling Pipe Routing Layout Plan | 523213-01-RFAS-ME-0019 | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
21 | Mechanical | 523213-01-SDW-ME-2700 | Level Roof - ACMV Pipe Routing Layout Plan | 523213-01-RFAS-ME-0020 | 2026-04-06 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0014 | [30 empty] | YES
22 | Mechanical | 523213-01-SDW-ME-2710 | Level Roof - Liquid Cooling Pipe Routing Layout Plan | 523213-01-RFAS-ME-0021 | 2026-04-06 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
23 | Mechanical | 523213-01-SDW-ME-3100 | Level 1 - Gas Leak Detection Layout Plan | 523213-01-RFAS-ME-0022 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
24 | Mechanical | 523213-01-SDW-ME-3110 | Level 1 - Water And Fuel Leak Detection Layout Plan | 523213-01-RFAS-ME-0023 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
25 | Mechanical | 523213-01-SDW-ME-3111 | Level 1 - Space Temperature And Humidity Sensor Layout Plan | 523213-01-RFAS-ME-0024 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
26 | Mechanical | 523213-01-SDW-ME-3200 | Level 2 - Gas Leak Detection Layout Plan | 523213-01-RFAS-ME-0025 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
27 | Mechanical | 523213-01-SDW-ME-3210 | Level 2 - Water And Fuel Leak Detection Layout Plan | 523213-01-RFAS-ME-0026 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
28 | Mechanical | 523213-01-SDW-ME-3220 | Level 2 - Space Temperature And Humidity Sensor Layout Plan | 523213-01-RFAS-ME-0027 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
29 | Mechanical | 523213-01-SDW-ME-3230 | Level 2 - Fan Wall Sensor Layout And Details | 523213-01-RFAS-ME-0028 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
30 | Mechanical | 523213-01-SDW-ME-3600 | Level 6 - Fuel Leak Detection Layout Plan | 523213-01-RFAS-ME-0029 | 2026-04-06 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
31 | Mechanical | 523213-01-SDW-ME-4100 | Level 1 - Cms Cable Routing Layout Plan | 523213-01-RFAS-ME-0030 | 2026-05-04 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
32 | Mechanical | 523213-01-SDW-ME-4200 | Level 2 - Cms Cable Routing Layout Plan | 523213-01-RFAS-ME-0031 | 2026-04-13 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
33 | Mechanical | 523213-01-SDW-ME-4600 | Level 6 - Cms Cable Routing Layout Plan | 523213-01-RFAS-ME-0032 | 2026-05-04 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
34 | Mechanical | 523213-01-SDW-ME-5000 | Typical Detail | 523213-01-RFAS-ME-0033 | 2026-01-26 | 2026-01-26 | 2026-02-02 | 0 | AUR | Pending |  | GC |  | 2026-01-26 | 2026-02-02 | [28 empty] | NO
35 | Mechanical | 523213-01-SDW-ME-6000 | Mechanical Service Electrical Single Line Diagram Sheet-1 | 523213-01-RFAS-ME-0034 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
36 | Mechanical | 523213-01-SDW-ME-6001 | Mechanical Service Electrical Single Line Diagram Sheet-2 | 523213-01-RFAS-ME-0035 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
37 | Mechanical | 523213-01-SDW-ME-6002 | Mechanical Service Electrical Single Line Diagram Sheet-3 | 523213-01-RFAS-ME-0036 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
38 | Mechanical | 523213-01-SDW-ME-6003 | Mechanical Service Electrical Single Line Diagram Sheet-4 | 523213-01-RFAS-ME-0037 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
39 | Mechanical | 523213-01-SDW-ME-6004 | Mechanical Service Electrical Single Line Diagram Sheet-5 | 523213-01-RFAS-ME-0038 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
40 | Mechanical | 523213-01-SDW-ME-6005 | Mechanical Service Electrical Single Line Diagram Sheet-6 | 523213-01-RFAS-ME-0039 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
41 | Mechanical | 523213-01-SDW-ME-6006 | Mechanical Service Electrical Single Line Diagram Sheet-7 | 523213-01-RFAS-ME-0040 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
42 | Mechanical | 523213-01-SDW-ME-6007 | Mechanical Service Electrical Single Line Diagram Sheet-8 | 523213-01-RFAS-ME-0041 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
43 | Mechanical | 523213-01-SDW-ME-6008 | Mechanical Service Electrical Single Line Diagram Sheet-9 | 523213-01-RFAS-ME-0042 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
44 | Mechanical | 523213-01-SDW-ME-6009 | Mechanical Service Electrical Single Line Diagram Sheet-10 | 523213-01-RFAS-ME-0043 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
45 | Mechanical | 523213-01-SDW-ME-6010 | Mechanical Service Electrical Single Line Diagram Sheet-11 | 523213-01-RFAS-ME-0044 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
46 | Mechanical | 523213-01-SDW-ME-6011 | Mechanical Service Electrical Single Line Diagram Sheet-12 | 523213-01-RFAS-ME-0045 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
47 | Mechanical | 523213-01-SDW-ME-6012 | Mechanical Service Electrical Single Line Diagram Sheet-13 | 523213-01-RFAS-ME-0046 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
48 | Mechanical | 523213-01-SDW-ME-6013 | Mechanical Service Electrical Single Line Diagram Sheet-14 | 523213-01-RFAS-ME-0047 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
49 | Mechanical | 523213-01-SDW-ME-6014 | Mechanical Service Electrical Single Line Diagram Sheet-15 | 523213-01-RFAS-ME-0048 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
50 | Mechanical | 523213-01-SDW-ME-6015 | Mechanical Service Electrical Single Line Diagram Sheet-16 | 523213-01-RFAS-ME-0049 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
51 | Mechanical | 523213-01-SDW-ME-6016 | Mechanical Service Electrical Single Line Diagram Sheet-17 | 523213-01-RFAS-ME-0050 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
52 | Mechanical | 523213-01-SDW-ME-6017 | Mechanical Service Electrical Single Line Diagram Sheet-18 | 523213-01-RFAS-ME-0051 | 2026-02-28 | [6 empty] | GC | Check with RFI No.523213-01-RFI-ME-0010 | [30 empty] | YES
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Planned Submission = [Planned Submission, row above]+7
Planned Submission = [Planned Submission, row above]

## HY
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [12 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. |  | RFAS Doc No. | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Hydraulics | 523213-01-SDW-HY-0001 | Hydraulic Drawing Index | 523213-01-RFAS-HY-0001 |  |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
2 | Hydraulics | 523213-01-SDW-HY-0100 | Hydraulic Legend & Abbreviation | 523213-01-RFAS-HY-0002 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-02 | [28 empty] | NO
3 | Hydraulics | 523213-01-SDW-HY-0150 | Make Up Water Schematic Diagram | 523213-01-RFAS-HY-0003 | 2026-01-19 | 2026-01-13 | 2026-01-20 | 0 | AUR | Pending |  | GC |  | 2026-01-13 | 2026-02-02 | [28 empty] | YES
4 | Hydraulics | 523213-01-SDW-HY-0200 | Domestic Water Schematic Diagram | 523213-01-RFAS-HY-0004 | 2026-01-19 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-02 | [28 empty] | NO
5 | Hydraulics | 523213-01-SDW-HY-0250 | Waste water System Schematic Diagram | 523213-01-RFAS-HY-0005 | 2026-01-19 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-02 | [28 empty] | YES
6 | Hydraulics | 523213-01-SDW-HY-0300 | Storm Water Drainage Schematic Diagram | 523213-01-RFAS-HY-0006 | 2026-01-19 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-02 | [28 empty] | NO
7 | Hydraulics | 523213-01-SDW-HY-0350 | Fuel Supply Schematic Diagram | 523213-01-RFAS-HY-0007 | 2026-01-19 | 2026-01-13 | 2026-01-20 | 0 | AUR | Pending |  | GC |  | 2026-01-13 | 2026-02-02 | [28 empty] | YES
8 | Hydraulics | 523213-01-SDW-HY-0400 | Equipment Schedule | 523213-01-RFAS-HY-0008 | 2026-01-19 | 2026-01-13 | 2026-01-20 | 0 | AUR | Pending |  | GC |  | 2026-01-13 | 2026-02-02 | [28 empty] | YES
9 | Hydraulics | 523213-01-SDW-HY-0450 | Electrical Single Line Diagram | 523213-01-RFAS-HY-0009 | 2026-01-19 | 2026-01-14 | 2026-01-21 | 0 | AUR | Pending |  | GC |  | 2026-01-14 | 2026-02-02 | [28 empty] | NO
10 | Hydraulics | 523213-01-SDW-HY-1000 | Site Plan - Water Supply System Layout | 523213-01-RFAS-HY-0010 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
11 | Hydraulics | 523213-01-SDW-HY-1100 | Level 1 - Water Supply System Layout Plan | 523213-01-RFAS-HY-0011 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
12 | Hydraulics | 523213-01-SDW-HY-1200 | Level 2 - Water Supply System Layout Plan | 523213-01-RFAS-HY-0012 | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | Pending sanitary ware Inlet-Outlet position. | [30 empty] | NO
13 | Hydraulics | 523213-01-SDW-HY-1600 | Level 6 - Water Supply System Layout Plan | 523213-01-RFAS-HY-0013 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
14 | Hydraulics | 523213-01-SDW-HY-1700 | Level Roof - Water Supply System Layout Plan | 523213-01-RFAS-HY-0014 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
15 | Hydraulics | 523213-01-SDW-HY-2000 | Site Plan - Wastewater And Stromwater System Layout Plan | 523213-01-RFAS-HY-0015 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
16 | Hydraulics | 523213-01-SDW-HY-2100 | Level 1 - Wastewater And Stormwater System Layout | 523213-01-RFAS-HY-0016 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
17 | Hydraulics | 523213-01-SDW-HY-2200 | Level 2 - Wastewater And Stormwater System Layout | 523213-01-RFAS-HY-0017 | 2026-02-09 |  | 1900-01-06 |  |  |  |  | TTI | TTI Scope | [30 empty] | NO
18 | Hydraulics | 523213-01-SDW-HY-2600 | Level 6 - Wastewater And Stormwater System Layout | 523213-01-RFAS-HY-0018 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
19 | Hydraulics | 523213-01-SDW-HY-2700 | Level Roof - Wastewater And Stormwater System Layout | 523213-01-RFAS-HY-0019 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
20 | Hydraulics | 523213-01-SDW-HY-3000 | Pump Room Details - Sheet 1 | 523213-01-RFAS-HY-0020 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
21 | Hydraulics | 523213-01-SDW-HY-3010 | Pump Room Details - Sheet 2 | 523213-01-RFAS-HY-0021 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
22 | Hydraulics | 523213-01-SDW-HY-3020 | Pump Room Details - Sheet 3 | 523213-01-RFAS-HY-0022 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
23 | Hydraulics | 523213-01-SDW-HY-3100 | Fuel Pump Room Details - Sheet 1 | 523213-01-RFAS-HY-0023 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
24 | Hydraulics | 523213-01-SDW-HY-3110 | Fuel Pump Room Details - Sheet 2 | 523213-01-RFAS-HY-0024 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | YES
25 | Hydraulics | 523213-01-SDW-HY-3200 | Softener Detail | 523213-01-RFAS-HY-0025 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
26 | Hydraulics | 523213-01-SDW-HY-3300 | Pump Room & Water Tank - Level 6 Detail | 523213-01-RFAS-HY-0026 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
27 | Hydraulics | 523213-01-SDW-HY-4200 | Level 2 - Toilet Details | 523213-01-RFAS-HY-0027 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
28 | Hydraulics | 523213-01-SDW-HY-5000 | Scope Demarcation - Sheet 1 | 523213-01-RFAS-HY-0028 | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
29 | Hydraulics | 523213-01-SDW-HY-5001 | Scope Demarcation - Sheet 2 | 523213-01-RFAS-HY-0029 | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
30 | Hydraulics | 523213-01-SDW-HY-5002 | Typical Details Sheet 1 | 523213-01-RFAS-HY-0030 | 2026-02-02 | 2026-01-30 | 2026-02-06 | 0 | AUR | Pending |  | GC |  | 2026-01-30 | 2026-02-02 | [28 empty] | NO
31 | Hydraulics | 523213-01-SDW-HY-5003 | Typical Details Sheet 2 | 523213-01-RFAS-HY-0031 | 2026-02-02 | 2026-01-30 | 2026-02-06 | 0 | AUR | Pending |  | GC |  | 2026-01-30 | 2026-02-02 | [28 empty] | NO
32 | Hydraulics | 523213-01-SDW-HY-5004 | Typical Details Sheet 3 | 523213-01-RFAS-HY-0032 | 2026-02-02 | 2026-01-30 | 2026-02-06 | 0 | AUR | Pending |  | GC |  | 2026-01-30 | 2026-02-02 | [28 empty] | NO
NO
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Planned Submission = [Planned Submission, row above]+7
Planned Submission = [Planned Submission, row above]

## FI
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [12 empty] | Action by | GAA | CTA | AUR
S/N | Trade | SDW Doc No. |  | RFAS Doc No. | Planned Submission | Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Fire Protection | 523213-01-SDW-FI-0001 | Fire Protection Drawing Index | 523213-01-RFAS-FI-0001 |  |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
2 | Fire Protection | 523213-01-SDW-FI-0002 | Fire Protection Legend & Abbreviation | 523213-01-RFAS-FI-0002 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 0 | AUR | Pending |  | GC |  | 2026-01-12 | 2026-02-04 | [28 empty] | NO
3 | Fire Protection | 523213-01-SDW-FI-0010 | Fire Protection System Schematic Diagram | 523213-01-RFAS-FI-0003 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | AUR | Pending |  | GC |  | 2026-01-19 | 2026-02-04 | [28 empty] | NO
4 | Fire Protection | 523213-01-SDW-FI-0020 | Schematic Diagram For Fire Pump | 523213-01-RFAS-FI-0004 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | AUR | Pending |  | GC |  | 2026-01-19 | 2026-02-04 | [28 empty] | NO
5 | Fire Protection | 523213-01-SDW-FI-0030 | Nitrogen Suppression Schematic Diagram | 523213-01-RFAS-FI-0005 | 2026-01-19 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI | [30 empty] | NO
6 | Fire Protection | 523213-01-SDW-FI-0040 | Nitrogen Suppression Flow Chart Diagram | 523213-01-RFAS-FI-0006 | 2026-01-19 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI | [30 empty] | NO
7 | Fire Protection | 523213-01-SDW-FI-0050 | Table For Nitrogen Gas Suppression | 523213-01-RFAS-FI-0007 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 0 | AUR | Pending |  | GC |  | 2026-01-26 | 2026-02-04 | [28 empty] | NO
8 | Fire Protection | 523213-01-SDW-FI-0060 | Pre-Action System Diagram | 523213-01-RFAS-FI-0008 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 0 | AUR | Pending |  | GC |  | 2026-01-26 | 2026-02-04 | [28 empty] | NO
9 | Fire Protection | 523213-01-SDW-FI-0070 | Equipment Schedule | 523213-01-RFAS-FI-0009 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | AUR | Pending |  | GC |  | 2026-01-19 | 2026-02-04 | [28 empty] | NO
10 | Fire Protection | 523213-01-SDW-FI-0080 | Electrical Single Line Diagram | 523213-01-RFAS-FI-0010 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 0 | AUR | Pending |  | GC |  | 2026-01-19 | 2026-02-04 | [28 empty] | NO
11 | Fire Protection | 523213-01-SDW-FI-1100 | Fire Protection Matrix For Level 1 | 523213-01-RFAS-FI-0011 | 2026-02-02 | 2026-02-11 | 2026-02-18 | 0 | CTA | Pending |  | GC |  | 2026-02-11 | [29 empty] | NO
12 | Fire Protection | 523213-01-SDW-FI-1200 | Fire Protection Matrix For Level 2 | 523213-01-RFAS-FI-0012 | 2026-02-02 | 2026-02-11 | 2026-02-18 | 0 | CTA | Pending |  | GC |  | 2026-02-11 | [29 empty] | NO
13 | Fire Protection | 523213-01-SDW-FI-1600 | Fire Protection Matrix For Level 6 | 523213-01-RFAS-FI-0013 | 2026-02-02 | 2026-02-11 | 2026-02-18 | 0 | CTA | Pending |  | GC |  | 2026-02-11 | [29 empty] | NO
14 | Fire Protection | 523213-01-SDW-FI-1700 | Fire Protection Matrix For Level Roof | 523213-01-RFAS-FI-0014 | 2026-02-02 | 2026-02-11 | 2026-02-18 | 0 | CTA | Pending |  | GC |  | 2026-02-11 | [29 empty] | NO
15 | Fire Protection | 523213-01-SDW-FI-2100 | Level 1 - Fire Sprinkler System Layout Plan | 523213-01-RFAS-FI-0015 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-FI-0004, FI-0007 | [30 empty] | NO
16 | Fire Protection | 523213-01-SDW-FI-2200 | Level 2 - Fire Sprinkler System Layout Plan | 523213-01-RFAS-FI-0016 | 2026-02-16 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-FI-0007 | [30 empty] | NO
17 | Fire Protection | 523213-01-SDW-FI-2600 | Level 6 - Fire Sprinkler System Layout Plan | 523213-01-RFAS-FI-0017 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-FI-0007 | [30 empty] | NO
18 | Fire Protection | 523213-01-SDW-FI-2700 | Level Roof - Fire Sprinkler System Layout Plan | 523213-01-RFAS-FI-0018 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
19 | Fire Protection | 523213-01-SDW-FI-3100 | Level 1 - Nitrogen Fire Suppression Ststem Layout Plan | 523213-01-RFAS-FI-0019 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-FI-0004, 0008 | [30 empty] | NO
20 | Fire Protection | 523213-01-SDW-FI-3150 | Level 1 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | 523213-01-RFAS-FI-0020 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | Pending RFI-FI-0004, 0008 | [30 empty] | NO
21 | Fire Protection | 523213-01-SDW-FI-3200 | Level 2 - Nitrogen Fire Suppression Ststem Layout Plan | 523213-01-RFAS-FI-0021 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
22 | Fire Protection | 523213-01-SDW-FI-3250 | Level 2 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | 523213-01-RFAS-FI-0022 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
23 | Fire Protection | 523213-01-SDW-FI-3600 | Level 6 - Nitrogen Fire Suppression Ststem Layout Plan | 523213-01-RFAS-FI-0023 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
24 | Fire Protection | 523213-01-SDW-FI-3650 | Level 6 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | 523213-01-RFAS-FI-0024 | 2026-03-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
25 | Fire Protection | 523213-01-SDW-FI-4100 | Level 1 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | 523213-01-RFAS-FI-0025 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
26 | Fire Protection | 523213-01-SDW-FI-4200 | Level 2 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | 523213-01-RFAS-FI-0026 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
27 | Fire Protection | 523213-01-SDW-FI-4600 | Level 6 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | 523213-01-RFAS-FI-0027 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
28 | Fire Protection | 523213-01-SDW-FI-4700 | Level Roof - Fire Hose Cabinet And Fire Extinguisher Layout Plan | 523213-01-RFAS-FI-0028 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
29 | Fire Protection | 523213-01-SDW-FI-5001 | Pump Room Detail Sheet 1 | 523213-01-RFAS-FI-0029 | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
30 | Fire Protection | 523213-01-SDW-FI-5002 | Pump Room Detail Sheet 2 | 523213-01-RFAS-FI-0030 | 2026-03-30 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
31 | Fire Protection | 523213-01-SDW-FI-5003 | Fire Service Room Detail Sheet 1 | 523213-01-RFAS-FI-0031 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
32 | Fire Protection | 523213-01-SDW-FI-5004 | Fire Service Room Detail Sheet 2 | 523213-01-RFAS-FI-0032 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
33 | Fire Protection | 523213-01-SDW-FI-5005 | Fire Service Room Detail Sheet 3 | 523213-01-RFAS-FI-0033 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
34 | Fire Protection | 523213-01-SDW-FI-5006 | Fire Scope Demarcation | 523213-01-RFAS-FI-0034 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
35 | Fire Protection | 523213-01-SDW-FI-6001 | Typical Details Sheet 1 | 523213-01-RFAS-FI-0035 | 2026-02-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
36 | Fire Protection | 523213-01-SDW-FI-6002 | Typical Details Sheet 2 | 523213-01-RFAS-FI-0036 | 2026-02-03 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
37 | Fire Protection | 523213-01-SDW-FI-6003 | Typical Details Sheet 3 | 523213-01-RFAS-FI-0037 | 2026-02-04 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
38 | Fire Protection | 523213-01-SDW-FI-6004 | Typical Details Sheet 4 | 523213-01-RFAS-FI-0038 | 2026-02-05 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
39 | Fire Protection | 523213-01-SDW-FI-6005 | Typical Details Sheet 5 | 523213-01-RFAS-FI-0039 | 2026-02-06 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
40 | Fire Protection | 523213-01-SDW-FI-6006 | Typical Details Sheet 6 | 523213-01-RFAS-FI-0040 | 2026-02-07 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
DO NOT DELETE
GAA
CTA
AUR
STT
Closed
Formulas:
Consultant Respond Date = [Submission Date]+7
Planned Submission = [Planned Submission, row above]+7
Planned Submission = [Planned Submission, row above]

## CSD
Status: (A) Approved with No Comments, (B) Approved with Comments, (C) Revise & Resubmit | [12 empty] | Action by | GAA | CTA | AUR
S/N | Trade | Shop Drawing No. |  | RFAS No. | Planned Submission | Actual Submission Date | Consultant Respond Date | Rev | Action | Status | Approval Date | Scope | Remarks | Rev 0 |  |  |  |  | Rev 1 |  |  |  |  | Rev 2 |  |  |  |  | Rev 3 |  |  |  |  | Rev 4 |  |  |  |  | Rev 5 |  |  |  |  | Required Review by STT's Engineering Team (YES/NO)
[14 empty] | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status | Submitted | CTA | AUR | STT | Status
1 | Combine Service | 528207-04-SDW-CSD-1100 | Level 1 - Combine Wall Layout Plan Index | 523213-01-RFAS-CSD-0001 | 2026-02-23 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
2 | Combine Service | 528207-04-SDW-CSD-1200 | Level 2 - Combine Wall Genset 1-2 | 523213-01-RFAS-CSD-0002 | 2026-02-02 | 2026-01-21 | 2026-01-28 | 0 | CTA | Pending |  | GC |  | 2026-01-21 | [29 empty] | NO
3 | Combine Service | 528207-04-SDW-CSD-1201 | Level 2 - Combine Wall Lv Switch Room A | 523213-01-RFAS-CSD-0003 | 2026-02-02 | 2026-01-21 | 2026-01-28 | 0 | CTA | Pending |  | GC |  | 2026-01-21 | [29 empty] | NO
4 | Combine Service | 528207-04-SDW-CSD-1202 | Level 2 - Combine Wall Lv Switch Room B | 523213-01-RFAS-CSD-0004 | 2026-02-02 | 2026-01-21 | 2026-01-28 | 0 | CTA | Pending |  | GC |  | 2026-01-21 | [29 empty] | NO
5 | Combine Service | 528207-04-SDW-CSD-1203 | Level 2 - Combine Wall Genset 3-4 | 523213-01-RFAS-CSD-0005 | 2026-02-02 | 2026-01-21 | 2026-01-28 | 0 | CTA | Pending |  | GC |  | 2026-01-21 | [29 empty] | NO
6 | Combine Service | 528207-04-SDW-CSD-1204 | Level 2 - Combine Wall Goods Lift Lobby , Stair ST-2 | 523213-01-RFAS-CSD-0006 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 0 | CTA | Pending |  | GC |  | 2026-01-26 | [29 empty] | NO
7 | Combine Service | 528207-04-SDW-CSD-1205 | Level 2 - Combine Wall MDF A , ELV A , Fire Service , Battery A1 | 523213-01-RFAS-CSD-0007 | 2026-02-02 | 2026-01-26 | 2026-02-02 | 0 | CTA | Pending |  | GC |  | 2026-01-26 | [29 empty] | NO
8 | Combine Service | 528207-04-SDW-CSD-1206 | Level 2 - Combine Wall MDF B , ELV B , Battery B1 , Spare Room | 523213-01-RFAS-CSD-0008 | 2026-02-02 | 2026-01-28 | 2026-02-04 | 0 | CTA | Pending |  | GC |  | 2026-01-28 | [29 empty] | NO
9 | Combine Service | 528207-04-SDW-CSD-1207 | Level 2 - Combine Wall Fireman Lift , Toilet , Janitor , Stair 1 | 523213-01-RFAS-CSD-0009 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 0 | CTA | Pending |  | GC |  | 2026-02-02 | [29 empty] | NO
10 | Combine Service | 528207-04-SDW-CSD-1208 | Level 2 - Combine Wall Data Hall A , Fan Wall A | 523213-01-RFAS-CSD-0010 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 0 | CTA | Pending |  | GC |  | 2026-02-02 | [29 empty] | NO
11 | Combine Service | 528207-04-SDW-CSD-1209 | Level 2 - Combine Wall Spare Space , Battery Room A2 & B2 | 523213-01-RFAS-CSD-0011 | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05 | [29 empty] | NO
12 | Combine Service | 528207-04-SDW-CSD-1210 | Level 2 - Combine Wall Data Hall C , Fan Wall C | 523213-01-RFAS-CSD-0012 | 2026-02-02 | 2026-02-07 | 2026-02-14 | 0 | CTA | Pending |  | GC |  | 2026-02-07 | [29 empty] | NO
13 | Combine Service | 528207-04-SDW-CSD-1211 | Level 2 - Combine Wall Air Lock 2.1 , Comm Riser C1 , Stair ST-3 | 523213-01-RFAS-CSD-0013 | 2026-02-02 | 2026-02-04 | 2026-02-11 | 0 | CTA | Pending |  | GC |  | 2026-02-04 | [29 empty] | NO
14 | Combine Service | 528207-04-SDW-CSD-1212 | Level 2 - Combine Wall Air Lock 2.2 , Comm Riser C1 , Stair ST-4 | 523213-01-RFAS-CSD-0014 | 2026-02-02 | 2026-02-05 | 2026-02-12 | 0 | CTA | Pending |  | GC |  | 2026-02-05
11 | Combine Service | 528207-04-SDW-CSD-1300 | Level 3 - Combine Wall Layout Plan | 523213-01-RFAS-CSD-0015 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
12 | Combine Service | 528207-04-SDW-CSD-1400 | Level 4 - Combine Wall Layout Plan | 523213-01-RFAS-CSD-0016 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
13 | Combine Service | 528207-04-SDW-CSD-1500 | Level 5 - Combine Wall Layout Plan | 523213-01-RFAS-CSD-0017 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
14 | Combine Service | 528207-04-SDW-CSD-1600 | Level 6 - Combine Wall Layout Plan | 523213-01-RFAS-CSD-0018 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
15 | Combine Service | 528207-04-SDW-CSD-1700 | Level Roof - Combine Wall Layout Plan | 523213-01-RFAS-CSD-0019 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
16 | Combine Service | 528207-04-SDW-CSD-2100 | Level 1 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0020 | 2026-02-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
17 | Combine Service | 528207-04-SDW-CSD-2200 | Level 2 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0021 | 2026-01-19 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
18 | Combine Service | 528207-04-SDW-CSD-2201 | Level 2 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0022 | 2026-01-19 |  | 1900-01-06
18 | Combine Service | 528207-04-SDW-CSD-2300 | Level 3 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0022 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
19 | Combine Service | 528207-04-SDW-CSD-2400 | Level 4 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0023 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
20 | Combine Service | 528207-04-SDW-CSD-2500 | Level 5 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0024 | 2026-03-16 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
21 | Combine Service | 528207-04-SDW-CSD-2600 | Level 6 - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0025 | 2026-03-02 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
22 | Combine Service | 528207-04-SDW-CSD-2700 | Level Roof - Combine Ceiling Layout Plan | 523213-01-RFAS-CSD-0026 | 2026-03-09 |  | 1900-01-06 |  |  |  |  | GC | [31 empty] | NO
Formulas:
Planned Submission = [Planned Submission, row below]+21
Planned Submission = [Planned Submission, row above]
Consultant Respond Date = [Actual Submission Date]+7

## Internal Progress (hidden)
Material Approval Summary
Trade | Planned Equipment Material Approval | Priority |  |  | Complete with note |  |  | Complete |  |  | Complete with note | % Progress | Complete | % Progress | Overall Completion | % Progress
|  | High | Medium | Low | High | Medium | Low | High | Medium | Low
Structural | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Architectural | 83 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Mechanical | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Fire Protection | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Hydraulics | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Electrical & Comms | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Overall | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | #REF! | #REF! | #REF!
[11 empty] | Total | #REF!

## Priority
S/N | Trade | Doc Ref No. | Document Description | Rev | Plan Date | Actual Submission Date | Approval Date |  |  | Action By | Delays Date | Status | Priority | Scope | Required Review by STT's Engineering Team (YES/NO)
[7 empty] | CTA | AUR | STT
ARCHITECTURAL |  |  |  |  | *Put only this | dd/mm/yy
1 | Architectural | 523213-01-RFAS-AR-0001 | Architectural Drawing Index | 0 | 2026-01-12 | 2026-01-12 | 2026-01-21 | 2026-01-23 | 2026-01-28 | Closed |  | B |  | GC | NO
2 | Architectural | 523213-01-RFAS-AR-0002 | Level 1 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-19 | 2026-01-21 | 2026-01-23 | 2026-01-28 | GAA | #N/A | C |  | GC | NO
3 | Architectural | 523213-01-RFAS-AR-0003 | Level 2 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-17 | 2026-01-21 |  |  | AUR | 23 | Pending | Overdue | GC | NO
4 | Architectural | 523213-01-RFAS-AR-0004 | Level 3 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-20 | 2026-01-22 | 2026-01-28 | 2026-02-02 | Closed |  | B |  | GC | NO
5 | Architectural | 523213-01-RFAS-AR-0005 | Level 4 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-27 | 2026-01-28 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
6 | Architectural | 523213-01-RFAS-AR-0006 | Level 5 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-28 | 2026-01-31 | 2026-02-04 |  | STT | 9 | Pending | Overdue | GC | NO
7 | Architectural | 523213-01-RFAS-AR-0007 | Level 6 - Overall Base Plan | 0 | 2026-01-12 | 2026-01-22 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
8 | Architectural | 523213-01-RFAS-AR-0008 | Roof Deck - Overall Base Plan | 0 |  | 2026-02-09 | 2026-02-11 |  |  | AUR | 2 | Pending |  | GC | NO
9 | Architectural | 523213-01-RFAS-AR-0009 | Level 1 - Floor Finishes & Details | 0 |  | 2026-02-02 | 2026-02-04 | 2026-02-06 | 2026-02-06 | Closed |  | B |  | GC | NO
10 | Architectural | 523213-01-RFAS-AR-0010 | Level 2 - Floor Finishes & Details | 0 |  | 2026-01-23 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
11 | Architectural | 523213-01-RFAS-AR-0011 | Level 3 - Floor Finishes & Details | 0 |  | 2026-02-04 | 2026-02-06 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
12 | Architectural | 523213-01-RFAS-AR-0012 | Level 6 - Floor Finishes & Details | 0 |  | 2026-02-03 | 2026-02-06 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
13 | Architectural | 523213-01-RFAS-AR-0013 | Level 1 - Bund Wall Setting-out & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
14 | Architectural | 523213-01-RFAS-AR-0014 | Level 1 - Wall Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
15 | Architectural | 523213-01-RFAS-AR-0015 | Level 1 - Block Wall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
16 | Architectural | 523213-01-RFAS-AR-0016 | Level 2 - Bund Wall Setting-out & Details | 0 |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | Closed |  | B |  | GC | NO
17 | Architectural | 523213-01-RFAS-AR-0017 | Level 2 - Wall Finishes & Details | 0 |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | Closed |  | B |  | GC | NO
18 | Architectural | 523213-01-RFAS-AR-0018 | Level 2 - Wall Setting-out | 0 |  | 2026-01-23 | 2026-01-26 | 2026-02-06 | 2026-02-06 | Closed |  | B |  | GC | NO
19 | Architectural | 523213-01-RFAS-AR-0019 | Level 2 - Block Wall Layout & Details | 0 |  | 2026-02-06 | 2026-02-09 | 2026-02-12 |  | STT | 1 | Pending |  | GC | NO
20 | Architectural | 523213-01-RFAS-AR-0020 | Level 2 - Partition Wall Support Layout & Details | 1 |  | 2026-02-06 | 2026-02-09 | 2026-02-12 |  | STT | 1 | Pending |  | GC | NO
21 | Architectural | 523213-01-RFAS-AR-0021 | Level 2 - Wire Mesh Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
22 | Architectural | 523213-01-RFAS-AR-0022 | Level 3 - Bund Wall Setting-out & Details | 0 |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
23 | Architectural | 523213-01-RFAS-AR-0023 | Level 3 - Partition Wall Support Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
24 | Architectural | 523213-01-RFAS-AR-0024 | Level 3 - Block Wall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
25 | Architectural | 523213-01-RFAS-AR-0025 | Level 3 - Wall Finishes & Details | 0 |  | 2026-02-03 | 2026-02-06 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
26 | Architectural | 523213-01-RFAS-AR-0026 | Level 3 - Wall Setting-out | 0 |  | 2026-01-28 | 2026-01-31 | 2026-02-04 |  | STT | 9 | Pending | Overdue | GC | NO
27 | Architectural | 523213-01-RFAS-AR-0027 | Level 4 - Bund Wall Setting-out & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
28 | Architectural | 523213-01-RFAS-AR-0028 | Level 4 - Wall Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
29 | Architectural | 523213-01-RFAS-AR-0029 | Level 4 - Wall Setting-out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
30 | Architectural | 523213-01-RFAS-AR-0030 | Level 4 - Block Wall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
31 | Architectural | 523213-01-RFAS-AR-0031 | Level 5 - Bund Wall Setting-out & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
32 | Architectural | 523213-01-RFAS-AR-0032 | Level 5 - Wall Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
33 | Architectural | 523213-01-RFAS-AR-0033 | Level 5 - Wall Setting-out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
34 | Architectural | 523213-01-RFAS-AR-0034 | Level 5 - Block Wall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
35 | Architectural | 523213-01-RFAS-AR-0035 | Level 6 - Bund Wall Setting-out & Details | 0 |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
36 | Architectural | 523213-01-RFAS-AR-0036 | Level 6 - Wall Finishes & Details | 0 |  | 2026-02-03 | 2026-02-06 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
37 | Architectural | 523213-01-RFAS-AR-0037 | Level 6 - Wall Setting-out | 0 |  | 2026-01-28 | 2026-01-31 | 2026-02-04 |  | STT | 9 | Pending | Overdue | GC | NO
38 | Architectural | 523213-01-RFAS-AR-0038 | Level 6 - Block Wall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
39 | Architectural | 523213-01-RFAS-AR-0039 | Level 6 - Partition Wall Support Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
40 | Architectural | 523213-01-RFAS-AR-0040 | Level 1 - Crash Rail & Skirting Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
41 | Architectural | 523213-01-RFAS-AR-0041 | Level 2 - Crash Rail & Skirting Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
42 | Architectural | 523213-01-RFAS-AR-0042 | Level 6 - Crash Rail & Skirting Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
43 | Architectural | 523213-01-RFAS-AR-0043 | Level 1 - Door Schedule Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
44 | Architectural | 523213-01-RFAS-AR-0044 | Level 2 - Door Schedule Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
45 | Architectural | 523213-01-RFAS-AR-0045 | Level 3 - Door Schedule Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
46 | Architectural | 523213-01-RFAS-AR-0046 | Level 6 - Door Schedule Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
47 | Architectural | 523213-01-RFAS-AR-0047 | Level 1 - Soffit Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
48 | Architectural | 523213-01-RFAS-AR-0048 | Level 1 - Ceiling Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
49 | Architectural | 523213-01-RFAS-AR-0049 | Level 2 - Soffit Finishes & Details | 0 |  | 2026-01-23 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
50 | Architectural | 523213-01-RFAS-AR-0050 | Level 2 - Ceiling Finishes & Details | 0 |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
51 | Architectural | 523213-01-RFAS-AR-0051 | Level 2 - Structured Ceiling Anchor Layout & Details | 0 |  | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-02-06 | Closed |  | B |  | GC | NO
52 | Architectural | 523213-01-RFAS-AR-0052 | Level 3 - Soffit Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
53 | Architectural | 523213-01-RFAS-AR-0053 | Level 6 - Soffit Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
54 | Architectural | 523213-01-RFAS-AR-0054 | Roof Deck - Soffit Finishes & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
55 | Architectural | 523213-01-RFAS-AR-0055 | Level 1 - Interior Elevation Views, Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
56 | Architectural | 523213-01-RFAS-AR-0056 | Level 1 - Reception Hall Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
57 | Architectural | 523213-01-RFAS-AR-0057 | Level 1 - Security Room 1 Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | YES
58 | Architectural | 523213-01-RFAS-AR-0058 | Level 1 - Security Room 2 Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | YES
59 | Architectural | 523213-01-RFAS-AR-0059 | Level 1 - Pantry Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
60 | Architectural | 523213-01-RFAS-AR-0060 | Level 1 - Technical Assistant Room Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | YES
61 | Architectural | 523213-01-RFAS-AR-0061 | Level 1 - Hall 1.1 Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
62 | Architectural | 523213-01-RFAS-AR-0062 | Level 1 - Fireman Lift Lobby Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
63 | Architectural | 523213-01-RFAS-AR-0063 | Level 2 - Interior Elevation Views, Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
64 | Architectural | 523213-01-RFAS-AR-0064 | Level 2 - Toilet Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
65 | Architectural | 523213-01-RFAS-AR-0065 | Level 2 - GENSET Room Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
66 | Architectural | 523213-01-RFAS-AR-0066 | Level 2 - Hot Aisle Containment Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
67 | Architectural | 523213-01-RFAS-AR-0067 | Level 6 - Interior Elevation Views, Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
68 | Architectural | 523213-01-RFAS-AR-0068 | Level 6 - GENSET Room Layout & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
69 | Architectural | 523213-01-RFAS-AR-0069 | Level 1 - Signage Layout Plan & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
70 | Architectural | 523213-01-RFAS-AR-0070 | Level 2 - Signage Layout Plan & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
71 | Architectural | 523213-01-RFAS-AR-0071 | Level 3 - Signage Layout Plan & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
72 | Architectural | 523213-01-RFAS-AR-0072 | Level 6 - Signage Layout Plan & Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
73 | Architectural | 523213-01-RFAS-AR-0073 | Level 1 - Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
74 | Architectural | 523213-01-RFAS-AR-0074 | Level 2 - Data Hall 2-A Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
75 | Architectural | 523213-01-RFAS-AR-0075 | Level 2 - Spare Space Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | GC | 0
76 | Architectural | 523213-01-RFAS-AR-0076 | Level 2 - Data Hall 2-C Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | GC | 0
77 | Architectural | 523213-01-RFAS-AR-0077 | Level 2 - ELV B Area Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | 0 | 0
78 | Architectural | 523213-01-RFAS-AR-0078 | Level 2 - ELV A Area Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | 0 | 0
79 | Architectural | 523213-01-RFAS-AR-0079 | Level 2 - LV Room Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | 0 | 0
80 | Architectural | 523213-01-RFAS-AR-0080 | Level 3 - TX Room Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | 0 | NO
81 | Architectural | 523213-01-RFAS-AR-0081 | Level 6 - MSB Room Block-out & Pipe Sleeve Details | [6 empty] | 0 | #N/A | 0 |  | 0 | NO
82 | Architectural | 523213-01-RFAS-AR-0082 | #N/A | [6 empty] | 0 | #N/A | 0 |  | 0
[10 empty] | 0 | #N/A | #N/A | #N/A
[10 empty] | 0 | #N/A | #N/A | #N/A
[10 empty] | 0 | #N/A | #N/A | #N/A
ELECTRICAL |  |  |  |  | *Put only this
1 | Electrical | 523213-01-RFAS-EL-0001 | Electrical Drawing Index | [6 empty] | 0 | #N/A | 0 |  | GC | NO
2 | Electrical | 523213-01-RFAS-EL-0002 | Legend, Abbreviation, And General Notes | 1 |  | 2026-02-03 | 2026-02-04 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
3 | Electrical | 523213-01-RFAS-EL-0003 | Medium Voltage Overall Distribution Schematic | 0 |  | 2026-01-23 | 2026-01-27 | 2026-01-29 |  | STT | 15 | Pending | Overdue | GC | YES
4 | Electrical | 523213-01-RFAS-EL-0004 | Generator Allocation Schematic | 0 |  | 2026-01-17 | 2026-01-27 | 2026-01-29 |  | STT | 15 | Pending | Overdue | GC | YES
5 | Electrical | 523213-01-RFAS-EL-0005 | Medium Voltage And Communications Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
6 | Electrical | 523213-01-RFAS-EL-0006 | LV Single Line Diagram IT Load For Typical 4 MW With 2N Configuration Sheet 1 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
7 | Electrical | 523213-01-RFAS-EL-0007 | LV Single Line Diagram IT Load For Typical 4 MW With 2N Configuration Sheet 2 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
8 | Electrical | 523213-01-RFAS-EL-0008 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 1 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
9 | Electrical | 523213-01-RFAS-EL-0009 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 2 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
10 | Electrical | 523213-01-RFAS-EL-0010 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 3 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
11 | Electrical | 523213-01-RFAS-EL-0011 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 4 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
12 | Electrical | 523213-01-RFAS-EL-0012 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 5 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
13 | Electrical | 523213-01-RFAS-EL-0013 | LV Single Line Diagram IT Load For Typical 6 MW With 4M3 DR Configuration Sheet 6 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
14 | Electrical | 523213-01-RFAS-EL-0014 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 1 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
15 | Electrical | 523213-01-RFAS-EL-0015 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 2 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
16 | Electrical | 523213-01-RFAS-EL-0016 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 3 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
17 | Electrical | 523213-01-RFAS-EL-0017 | LV Single Line Diagram IT Load For Typical 8 MW With 4M3 DR Configuration Sheet 4 | 0 |  | 2026-01-16 |  |  |  | CTA | 28 | Pending | Overdue | GC | YES
18 | Electrical | 523213-01-RFAS-EL-0018 | LV Single Line Diagram For Swing Power System Sheet 1 | 0 |  | 2026-01-19 | 2026-01-30 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
19 | Electrical | 523213-01-RFAS-EL-0019 | LV Single Line Diagram For Swing Power System Sheet 2 | 0 |  | 2026-01-19 | 2026-01-30 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
20 | Electrical | 523213-01-RFAS-EL-0020 | LV Single Line Diagram For Swing Power System Sheet 3 | 0 |  | 2026-01-19 | 2026-01-30 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
21 | Electrical | 523213-01-RFAS-EL-0021 | LV Single Line Diagram For Non-It Power System Sheet 1 | 0 |  | 2026-01-19 | 2026-01-30 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
22 | Electrical | 523213-01-RFAS-EL-0022 | LV Single Line Diagram For Non-It Power System Sheet 2 | 0 |  | 2026-01-19 | 2026-02-03 | 2026-02-09 |  | STT | 4 | Pending | High | GC | YES
23 | Electrical | 523213-01-RFAS-EL-0023 | LV Single Line Diagram For Non-It Power System Sheet 3 | 0 |  | 2026-01-19 | 2026-01-30 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
24 | Electrical | 523213-01-RFAS-EL-0024 | LV Single Line Diagram Typical For Data Hall PDU | 0 |  | 2026-01-22 | 2026-01-28 | 2026-01-29 |  | STT | 15 | Pending | Overdue | GC | YES
|  |  | LV Single Line Diagram PDU For MDF Room A |  |  | #N/A | [7 empty] | GC
|  |  | LV Single Line Diagram PDU For MDF Room A |  |  | #N/A | [7 empty] | GC
|  |  | LV Single Line Diagram PDU For MDF Room A |  |  | #N/A | [7 empty] | GC
25 | Electrical | 523213-01-RFAS-EL-0025 | DC Supply Schematic For HV Equipment | 0 |  | 2026-01-22 | 2026-01-28 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
26 | Electrical | 523213-01-RFAS-EL-0026 | LV Single Line Diagram For Fan Wall UPS For Level 2 | 0 |  | 2026-01-24 | 2026-01-28 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
27 | Electrical | 523213-01-RFAS-EL-0027 | LV Single Line Diagram For Fan Wall UPS For Level 3 | 0 |  | 2026-01-24 | 2026-01-28 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
28 | Electrical | 523213-01-RFAS-EL-0028 | LV Single Line Diagram For Fan Wall UPS For Level 4 | 0 |  | 2026-01-24 | 2026-01-28 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
29 | Electrical | 523213-01-RFAS-EL-0029 | LV Single Line Diagram For Fan Wall UPS For Level 5 | 0 |  | 2026-01-24 | 2026-01-28 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
30 | Electrical | 523213-01-RFAS-EL-0030 | LV Single Line Diagram For Fan Wall OUSB For Level 2 and Level 3 | 0 |  | 2026-01-24 | 2026-01-27 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
31 | Electrical | 523213-01-RFAS-EL-0031 | LV Single Line Diagram For Fan Wall OUSB For Level 4 and Level 5 | 0 |  | 2026-01-24 | 2026-01-27 | 2026-01-30 |  | STT | 14 | Pending | Overdue | GC | NO
32 | Electrical | 523213-01-RFAS-EL-0032 | LV Single Line Diagram For Load Bank | 0 |  | 2026-01-24 | 2026-01-27 | 2026-02-02 |  | STT | 11 | Pending | Overdue | GC | YES
33 | Electrical | 523213-01-RFAS-EL-0033 | LV Single Line Diagram For Chiller Plant MSSB | 0 |  | 2026-02-02 | 2026-02-04 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
34 | Electrical | 523213-01-RFAS-EL-0034 | LV Single Line Diagram For Building NON-IT UPS | 0 |  | 2026-02-02 | 2026-02-04 | 2026-02-09 |  | STT | 4 | Pending | High | GC | NO
35 | Electrical | 523213-01-RFAS-EL-0035 | LV Single Line Diagram For Building Load Sheet 1 | 0 |  | 2026-02-05 | 2026-02-11 |  |  | AUR | 2 | Pending |  | GC | NO
36 | Electrical | 523213-01-RFAS-EL-0036 | LV Single Line Diagram For Building Load Sheet 2 | 0 |  | 2026-02-05 | 2026-02-11 |  |  | AUR | 2 | Pending |  | GC | NO
37 | Electrical | 523213-01-RFAS-EL-0037 | LV Single Line Diagram For Building Load Sheet 3 | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
38 | Electrical | 523213-01-RFAS-EL-0038 | LV Single Line Diagram For Building Load Sheet 4 | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
39 | Electrical | 523213-01-RFAS-EL-0039 | LV Single Line Diagram For Building Load Sheet 5 | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
40 | Electrical | 523213-01-RFAS-EL-0040 | LV Single Line Diagram For Building Load Sheet 6 | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
41 | Electrical | 523213-01-RFAS-EL-0041 | Automatic Fire Detection And Alarm System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | NO
42 | Electrical | 523213-01-RFAS-EL-0042 | Public Address And Voice Alarm System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | NO
43 | Electrical | 523213-01-RFAS-EL-0043 | Lighting Control System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | NO
44 | Electrical | 523213-01-RFAS-EL-0044 | Data Cabling System Schematic | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | YES
45 | Electrical | 523213-01-RFAS-EL-0045 | Overall Security System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | YES
46 | Electrical | 523213-01-RFAS-EL-0046 | Lightning Protection And Grounding System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | NO
47 | Electrical | 523213-01-RFAS-EL-0047 | Building Management System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | YES
48 | Electrical | 523213-01-RFAS-EL-0048 | Electrical Power Monitoring System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | YES
49 | Electrical | 523213-01-RFAS-EL-0049 | Chiller Management System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | YES
50 | Electrical | 523213-01-RFAS-EL-0050 | Load Schedule For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
51 | Electrical | 523213-01-RFAS-EL-0051 | Load Schedule For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
52 | Electrical | 523213-01-RFAS-EL-0052 | Load Schedule For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
53 | Electrical | 523213-01-RFAS-EL-0053 | Fuel System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | YES
54 | Electrical | 523213-01-RFAS-EL-0054 | Ecms (Bms) Point List For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
55 | Electrical | 523213-01-RFAS-EL-0055 | Ecms (Pms) Point List For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
56 | Electrical | 523213-01-RFAS-EL-0056 | Ecms (Ems) Point List For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
57 | Electrical | 523213-01-RFAS-EL-0057 | Ecms (Bms) Point List For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
58 | Electrical | 523213-01-RFAS-EL-0058 | Ecms (Pms) Point List For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
59 | Electrical | 523213-01-RFAS-EL-0059 | Ecms (Ems) Point List For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
60 | Electrical | 523213-01-RFAS-EL-0060 | Ecms (Bms) Point List For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
61 | Electrical | 523213-01-RFAS-EL-0061 | Ecms (Pms) Point List For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
62 | Electrical | 523213-01-RFAS-EL-0062 | Ecms (Ems) Point List For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
63 | Electrical | 523213-01-RFAS-EL-0063 | Lighting Control Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
64 | Electrical | 523213-01-RFAS-EL-0064 | Lighting Control Schematic Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
65 | Electrical | 523213-01-RFAS-EL-0065 | Lighting Control Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
66 | Electrical | 523213-01-RFAS-EL-0066 | Data Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
67 | Electrical | 523213-01-RFAS-EL-0067 | Data Schematic Diagram For Level 2 | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
68 | Electrical | 523213-01-RFAS-EL-0068 | Data Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
69 | Electrical | 523213-01-RFAS-EL-0069 | Fire Alarm Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
70 | Electrical | 523213-01-RFAS-EL-0070 | Fire Alarm Schematic Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
71 | Electrical | 523213-01-RFAS-EL-0071 | Fire Alarm Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
72 | Electrical | 523213-01-RFAS-EL-0072 | Fire Alarm Temincal Box Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
73 | Electrical | 523213-01-RFAS-EL-0073 | Fire Alarm Temincal Box Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
74 | Electrical | 523213-01-RFAS-EL-0074 | Fire Alarm Temincal Box Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
75 | Electrical | 523213-01-RFAS-EL-0075 | Public Address Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
76 | Electrical | 523213-01-RFAS-EL-0076 | Public Address Schematic Diagram For Level 2 | 0 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | NO
77 | Electrical | 523213-01-RFAS-EL-0077 | Public Address Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
78 | Electrical | 523213-01-RFAS-EL-0078 | Pre-Action Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
79 | Electrical | 523213-01-RFAS-EL-0079 | Pre-Action Schematic Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
80 | Electrical | 523213-01-RFAS-EL-0080 | Pre-Action Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
81 | Electrical | 523213-01-RFAS-EL-0081 | Aspirated Smoke Detection System Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
82 | Electrical | 523213-01-RFAS-EL-0082 | Aspirated Smoke Detection System Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
83 | Electrical | 523213-01-RFAS-EL-0083 | Aspirated Smoke Detection System Diagram For Level 3 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
84 | Electrical | 523213-01-RFAS-EL-0084 | Aspirated Smoke Detection System Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
85 | Electrical | 523213-01-RFAS-EL-0085 | Security (Cctv) Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
86 | Electrical | 523213-01-RFAS-EL-0086 | Security (Cctv) Schematic Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
87 | Electrical | 523213-01-RFAS-EL-0087 | Security (Cctv) Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
88 | Electrical | 523213-01-RFAS-EL-0088 | Security (Cctv) Schematic Diagram For Level Roof | [6 empty] | 0 | #N/A | 0 |  | GC | NO
89 | Electrical | 523213-01-RFAS-EL-0089 | Security (Acs) Schematic Diagram For Level 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
90 | Electrical | 523213-01-RFAS-EL-0090 | Security (Acs) Schematic Diagram For Level 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
91 | Electrical | 523213-01-RFAS-EL-0091 | Security (Acs) Schematic Diagram For Level 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
92 | Electrical | 523213-01-RFAS-EL-0092 | Security (Acs) Schematic Diagram For Level Roof | [6 empty] | 0 | #N/A | 0 |  | GC | NO
93 | Electrical | 523213-01-RFAS-EL-0093 | TX | [6 empty] | 0 | #N/A | 0 |  | LLE | YES
94 | Electrical | 523213-01-RFAS-EL-0094 | HVSB | [6 empty] | 0 | #N/A | 0 |  | LLE | YES
95 | Electrical | 523213-01-RFAS-EL-0095 | RMU | [6 empty] | 0 | #N/A | 0 |  | LLE | YES
96 | Electrical | 523213-01-RFAS-EL-0096 | MVBTU and MVBATT Details | 0 |  | 2026-01-27 | 2026-01-27 | 2026-02-02 |  | STT | 11 | Pending | Overdue | LLE | YES
97 | Electrical | 523213-01-RFAS-EL-0097 | RCP | [6 empty] | 0 | #N/A | 0 |  | LLE | YES
98 | Electrical | 523213-01-RFAS-EL-0098 | Schematic Diagram For AIS Switchgear | 0 |  | 2026-01-27 | 2026-01-27 | 2026-02-02 |  | STT | 11 | Pending | Overdue | LLE | YES
99 | Electrical | 523213-01-RFAS-EL-0099 | Schematic Diagram for RMU | 0 |  | 2026-01-30 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | LLE | YES
100 | Electrical | 523213-01-RFAS-EL-0100 | Control Logic for AIS Switchgear | 1 |  | 2026-02-05 | 2026-02-12 |  |  | AUR | 1 | Pending |  | LLE | NO
101 | Electrical | 523213-01-RFAS-EL-0101 | Control Logic for RMU | 0 |  | 2025-12-16 | 2025-12-22 | 2026-01-13 | 2026-01-21 | GAA | #N/A | C |  | LLE | NO
102 | Electrical | 523213-01-RFAS-EL-0102 | For Manufacturing Drawing | [6 empty] | 0 | #N/A | 0 |  | LLE | NO
103 | Electrical | 523213-01-RFAS-EL-0103 | For Manufacturing Drawing | [6 empty] | 0 | #N/A | 0 |  | LLE | NO
104 | Electrical | 523213-01-RFAS-EL-0104 | Level 1 - Mv Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
105 | Electrical | 523213-01-RFAS-EL-0105 | Level 1 - LV Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
106 | Electrical | 523213-01-RFAS-EL-0106 | Level 1 - Aux Power Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
107 | Electrical | 523213-01-RFAS-EL-0107 | Level 1 - Mvdc Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
108 | Electrical | 523213-01-RFAS-EL-0108 | Level 2 - MV Cable Routing Layout | 0 |  | 2026-02-02 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | NO
109 | Electrical | 523213-01-RFAS-EL-0109 | Level 2 - LV Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
110 | Electrical | 523213-01-RFAS-EL-0110 | Level 2 - Aux Power Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
111 | Electrical | 523213-01-RFAS-EL-0111 | Level 2 - Mvdc Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
112 | Electrical | 523213-01-RFAS-EL-0112 | Level 2 - SUPS Batt Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
113 | Electrical | 523213-01-RFAS-EL-0113 | Level 2 - SUPS Control Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
114 | Electrical | 523213-01-RFAS-EL-0114 | Level 2 - Busduct Routing Layout Overall | [6 empty] | 0 | #N/A | 0 |  | GC | NO
115 | Electrical | 523213-01-RFAS-EL-0115 | Level 2 - LV Busduct Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
116 | Electrical | 523213-01-RFAS-EL-0116 | Level 2 - LV Busduct Isometric | [6 empty] | 0 | #N/A | 0 |  | GC | NO
117 | Electrical | 523213-01-RFAS-EL-0117 | Level 2 - Swing & Load Bank Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
118 | Electrical | 523213-01-RFAS-EL-0118 | Level 2 - Swing & Load Bank Busduct Isometric | [6 empty] | 0 | #N/A | 0 |  | GC | NO
119 | Electrical | 523213-01-RFAS-EL-0119 | Level 2 - IT Busduct Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | 0
120 | Electrical | 523213-01-RFAS-EL-0120 | Level 2 - IT Busduct Isometric | [6 empty] | 0 | #N/A | 0 |  | GC | NO
121 | Electrical | 523213-01-RFAS-EL-0121 | Level 3 - Electrical Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
122 | Electrical | 523213-01-RFAS-EL-0122 | Level 4 - Electrical Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
123 | Electrical | 523213-01-RFAS-EL-0123 | Level 5 - Electrical Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
124 | Electrical | 523213-01-RFAS-EL-0124 | Level 6 - MV Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
125 | Electrical | 523213-01-RFAS-EL-0125 | Level 6 - LV Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
126 | Electrical | 523213-01-RFAS-EL-0126 | Level 6 - Aux Power Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
127 | Electrical | 523213-01-RFAS-EL-0127 | Level 6 - MVDC Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
128 | Electrical | 523213-01-RFAS-EL-0128 | Level 6 - SUPS Batt Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
129 | Electrical | 523213-01-RFAS-EL-0129 | Level 6 - SUPS Control Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
130 | Electrical | 523213-01-RFAS-EL-0130 | Level 6 - Busduct Routing Layout Overall | [6 empty] | 0 | #N/A | 0 |  | GC | NO
131 | Electrical | 523213-01-RFAS-EL-0131 | Level 6 - LV Busduct Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
132 | Electrical | 523213-01-RFAS-EL-0132 | Level 6 - LV Busduct Isometric | [6 empty] | 0 | #N/A | 0 |  | GC | NO
133 | Electrical | 523213-01-RFAS-EL-0133 | Level 6 - Swing & Load Bang Busduct Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
134 | Electrical | 523213-01-RFAS-EL-0134 | Level 6 - Swing & Load Bang Busduct Isometric | [6 empty] | 0 | #N/A | 0 |  | GC | NO
135 | Electrical | 523213-01-RFAS-EL-0135 | Level Roof - LV Cable Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
136 | Electrical | 523213-01-RFAS-EL-0136 | Level 1 - Cable Basket Routinh Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
137 | Electrical | 523213-01-RFAS-EL-0137 | Level 1 - Fiber Guide Routing Layout |  |  | Cancel |  |  |  | 0 | #N/A | 0 |  | GC | NO
138 | Electrical | 523213-01-RFAS-EL-0138 | Level 1 - ECMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
139 | Electrical | 523213-01-RFAS-EL-0139 | Level 1 - Bms Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
140 | Electrical | 523213-01-RFAS-EL-0140 | Level 1 - Pms&Ems Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
141 | Electrical | 523213-01-RFAS-EL-0141 | Level 1 - Fuel Control Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
142 | Electrical | 523213-01-RFAS-EL-0142 | Level 2 - Cable Basket Routing Layout | 0 |  | 2026-02-11 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | NO
143 | Electrical | 523213-01-RFAS-EL-0143 | Level 2 - Fiber Guide Routing Layout | 0 |  | 2026-02-11 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | NO
144 | Electrical | 523213-01-RFAS-EL-0144 | Level 2 - ECMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
145 | Electrical | 523213-01-RFAS-EL-0145 | Level 2 - BMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
146 | Electrical | 523213-01-RFAS-EL-0146 | Level 2 - PMS & EMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
147 | Electrical | 523213-01-RFAS-EL-0147 | Level 2 - Fuel Control Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
148 | Electrical | 523213-01-RFAS-EL-0148 | Level 3 - Communications Routing Layout | 0 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | NO
149 | Electrical | 523213-01-RFAS-EL-0149 | Level 4 - Communications Routing Layout | 0 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | NO
150 | Electrical | 523213-01-RFAS-EL-0150 | Level 5 - Communications Routing Layout | 0 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | YES
151 | Electrical | 523213-01-RFAS-EL-0151 | Level 6 - ECMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
152 | Electrical | 523213-01-RFAS-EL-0152 | Level 6 - Bms Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
153 | Electrical | 523213-01-RFAS-EL-0153 | Level 6 - PMS & EMS Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
154 | Electrical | 523213-01-RFAS-EL-0154 | Level 6 - Fuel Control Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
155 | Electrical | 523213-01-RFAS-EL-0155 | Level Roof - Communications Routing Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
156 | Electrical | 523213-01-RFAS-EL-0156 | Level 1 - General Lighting System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
157 | Electrical | 523213-01-RFAS-EL-0157 | Level 1 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
158 | Electrical | 523213-01-RFAS-EL-0158 | Level 1 - Lighting Control Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
159 | Electrical | 523213-01-RFAS-EL-0159 | Level 2 - General Lighting System Layout | 0 |  | 2026-02-10 |  |  |  | CTA | 3 | Pending | High | GC | NO
160 | Electrical | 523213-01-RFAS-EL-0160 | Level 2 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
161 | Electrical | 523213-01-RFAS-EL-0161 | Level 2 - Lighting Control Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
162 | Electrical | 523213-01-RFAS-EL-0162 | Level 3 - General Lighting System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
163 | Electrical | 523213-01-RFAS-EL-0163 | Level 3 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | 0
164 | Electrical | 523213-01-RFAS-EL-0164 | Level 4 - General Lighting System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
165 | Electrical | 523213-01-RFAS-EL-0165 | Level 4 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
166 | Electrical | 523213-01-RFAS-EL-0166 | Level 5 - General Lighting System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
167 | Electrical | 523213-01-RFAS-EL-0167 | Level 5 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
168 | Electrical | 523213-01-RFAS-EL-0168 | Level 6 - General Lighting System Layout | 0 |  | 2026-02-10 |  |  |  | CTA | 3 | Pending | High | GC | NO
169 | Electrical | 523213-01-RFAS-EL-0169 | Level 6 - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
170 | Electrical | 523213-01-RFAS-EL-0170 | Level 6 - Lighting Control Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
171 | Electrical | 523213-01-RFAS-EL-0171 | Level Roof - General Lighting System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
172 | Electrical | 523213-01-RFAS-EL-0172 | Level Roof - Emergency Light And Exit Sign Systems Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
173 | Electrical | 523213-01-RFAS-EL-0173 | Level 1 - Power And Receptacle Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
174 | Electrical | 523213-01-RFAS-EL-0174 | Level 1 - Power Supply Mech System Layout, | [6 empty] | 0 | #N/A | 0 |  | GC | NO
175 | Electrical | 523213-01-RFAS-EL-0175 | Level 1 - Power Supply Mcp System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
176 | Electrical | 523213-01-RFAS-EL-0176 | Level 1 - Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
177 | Electrical | 523213-01-RFAS-EL-0177 | Level 1 - Ceeform System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
178 | Electrical | 523213-01-RFAS-EL-0178 | Level 2 - Power And Receptacle Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
179 | Electrical | 523213-01-RFAS-EL-0179 | Level 2 - Power Supply Mech System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
180 | Electrical | 523213-01-RFAS-EL-0180 | Level 2 - Power Supply Mcp System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
181 | Electrical | 523213-01-RFAS-EL-0181 | Level 2 - Data Outlet System Layout | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
182 | Electrical | 523213-01-RFAS-EL-0182 | Level 2 - Ceeform System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
183 | Electrical | 523213-01-RFAS-EL-0183 | Level 3 - Power ,Voice And Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
184 | Electrical | 523213-01-RFAS-EL-0184 | Level 4 - Power ,Voice And Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
185 | Electrical | 523213-01-RFAS-EL-0185 | Level 5 - Power ,Voice And Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
186 | Electrical | 523213-01-RFAS-EL-0186 | Level 6 - Power And Receptacle Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
187 | Electrical | 523213-01-RFAS-EL-0187 | Level 6 - Power Supply Mech System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
188 | Electrical | 523213-01-RFAS-EL-0188 | Level 6 - Power Supply Mcp System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
189 | Electrical | 523213-01-RFAS-EL-0189 | Level 6 - Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
190 | Electrical | 523213-01-RFAS-EL-0190 | Level Roof - Power ,Voice And Data Outlet System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
191 | Electrical | 523213-01-RFAS-EL-0191 | Level 1 - Fire Alarm System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
192 | Electrical | 523213-01-RFAS-EL-0192 | Level 1 - Public Address System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
193 | Electrical | 523213-01-RFAS-EL-0193 | Level 1 - Aspirated Smoke Detection Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
194 | Electrical | 523213-01-RFAS-EL-0194 | Level 2 - Fire Alarm System Layout | 0 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | NO
195 | Electrical | 523213-01-RFAS-EL-0195 | Level 2 - Public Address System Layout | 0 |  | 2026-02-05 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | NO
196 | Electrical | 523213-01-RFAS-EL-0196 | Level 2 - Aspirated Smoke Detection Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
197 | Electrical | 523213-01-RFAS-EL-0197 | Level 3 - Fire Alarm System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
198 | Electrical | 523213-01-RFAS-EL-0198 | Level 3 - Public Address System Layout | 0 |  | 2026-02-05 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | NO
199 | Electrical | 523213-01-RFAS-EL-0199 | Level 3 - Aspirated Smoke Detection Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
200 | Electrical | 523213-01-RFAS-EL-0200 | Level 4 - Fire Alarm System Layout | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
201 | Electrical | 523213-01-RFAS-EL-0201 | Level 4 - Public Address System Layout | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
202 | Electrical | 523213-01-RFAS-EL-0202 | Level 5 - Fire Alarm System Layout | 0 |  | 2026-02-09 |  |  |  | CTA | 4 | Pending | High | GC | NO
203 | Electrical | 523213-01-RFAS-EL-0203 | Level 5 - Public Address System Layout | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
204 | Electrical | 523213-01-RFAS-EL-0204 | Level 6 - Fire Alarm System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
205 | Electrical | 523213-01-RFAS-EL-0205 | Level 6 - Public Address System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
206 | Electrical | 523213-01-RFAS-EL-0206 | Level 6 - Aspirated Smoke Detection Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
207 | Electrical | 523213-01-RFAS-EL-0207 | Level Roof - Fire Alarm System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
208 | Electrical | 523213-01-RFAS-EL-0208 | Level Roof - Public Address System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
209 | Electrical | 523213-01-RFAS-EL-0209 | Level 1 - Security CCTV System Layout | 1 |  | 2026-02-12 |  |  |  | CTA | 1 | Pending |  | GC | NO
210 | Electrical | 523213-01-RFAS-EL-0210 | Level 1 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
211 | Electrical | 523213-01-RFAS-EL-0211 | Level 2 - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
212 | Electrical | 523213-01-RFAS-EL-0212 | Level 2 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
213 | Electrical | 523213-01-RFAS-EL-0213 | Level 3 - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
214 | Electrical | 523213-01-RFAS-EL-0214 | Level 3 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
215 | Electrical | 523213-01-RFAS-EL-0215 | Level 4 - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
216 | Electrical | 523213-01-RFAS-EL-0216 | Level 4 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
217 | Electrical | 523213-01-RFAS-EL-0217 | Level 5 - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
218 | Electrical | 523213-01-RFAS-EL-0218 | Level 5 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
219 | Electrical | 523213-01-RFAS-EL-0219 | Level 6 - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
220 | Electrical | 523213-01-RFAS-EL-0220 | Level 6 - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
221 | Electrical | 523213-01-RFAS-EL-0221 | Level Roof - Security CCTV System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
222 | Electrical | 523213-01-RFAS-EL-0222 | Level Roof - Security Access Control System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
223 | Electrical | 523213-01-RFAS-EL-0223 | Level 1 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
224 | Electrical | 523213-01-RFAS-EL-0224 | Level 2 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
225 | Electrical | 523213-01-RFAS-EL-0225 | Level 3 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
226 | Electrical | 523213-01-RFAS-EL-0226 | Level 4 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
227 | Electrical | 523213-01-RFAS-EL-0227 | Level 5 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
228 | Electrical | 523213-01-RFAS-EL-0228 | Level 6 - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
229 | Electrical | 523213-01-RFAS-EL-0229 | Level Roof - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
230 | Electrical | 523213-01-RFAS-EL-0230 | Level Top Roof - Earthing And Lightning Protection System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | YES
231 | Electrical | 523213-01-RFAS-EL-0231 | Level 1 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
232 | Electrical | 523213-01-RFAS-EL-0232 | Level 2 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
233 | Electrical | 523213-01-RFAS-EL-0233 | Level 3 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
234 | Electrical | 523213-01-RFAS-EL-0234 | Level 4 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
235 | Electrical | 523213-01-RFAS-EL-0235 | Level 5 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
236 | Electrical | 523213-01-RFAS-EL-0236 | Level 6 Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
237 | Electrical | 523213-01-RFAS-EL-0237 | Level Roof Equipment Setting out | [6 empty] | 0 | #N/A | 0 |  | GC | NO
238 | Electrical | 523213-01-RFAS-EL-0238 | Typical Details For Access Control System Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
239 | Electrical | 523213-01-RFAS-EL-0239 | Typical Details For Access Control System Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
240 | Electrical | 523213-01-RFAS-EL-0240 | Access Control System Schematic | [6 empty] | 0 | #N/A | 0 |  | GC | NO
241 | Electrical | 523213-01-RFAS-EL-0241 | Typical Details Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
242 | Electrical | 523213-01-RFAS-EL-0242 | Typical Details Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
243 | Electrical | 523213-01-RFAS-EL-0243 | Typical Details Sheet 3 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
244 | Electrical | 523213-01-RFAS-EL-0244 | Typical Details Sheet 4 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
245 | Electrical | 523213-01-RFAS-EL-0245 | Typical Details Sheet 5 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
246 | Electrical | 523213-01-RFAS-EL-0246 | Typical Details Sheet 6 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
247 | Electrical | 523213-01-RFAS-EL-0247 | Typical Details Sheet 7 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
248 | Electrical | 523213-01-RFAS-EL-0248 | Typical Details Sheet 8 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
249 | Electrical | 523213-01-RFAS-EL-0249 | For LLE GEN | [6 empty] | 0 | #N/A | 0 |  | LLE | NO
250 | Electrical | 523213-01-RFAS-EL-0250 | For LLE GEN | [6 empty] | 0 | #N/A | 0 |  | LLE
251 | Electrical | 523213-01-RFAS-EL-0251 | 63A DB Aux Panel | 0 |  | 2026-02-10 | 2026-02-12 |  |  | AUR | 1 | Pending |  | LLE
252 | Electrical | 523213-01-RFAS-EL-0252 | 4000A SLD GA Control | 0 |  | 2026-02-10 | 2026-02-11 |  |  | AUR | 2 | Pending |  | LLE
253 | Electrical | 523213-01-RFAS-EL-0253 | For LLE GEN | [6 empty] | 0 | #N/A | 0 |  | LLE
254 | Electrical | 523213-01-RFAS-EL-0254 | For LLE GEN | [6 empty] | 0 | #N/A | 0 |  | LLE
255 | Electrical | 523213-01-RFAS-EL-0255 | Junction Box | 0 |  | 2026-02-11 | 2026-02-12 |  |  | AUR | 1 | Pending |  | LLE
FIRE PROTECTION |  |  |  |  | *Put only this
1 | Fire Protection | 523213-01-RFAS-FI-0001 | Fire Protection Drawing Index | [6 empty] | 0 | #N/A | 0 |  | GC | NO
2 | Fire Protection | 523213-01-RFAS-FI-0002 | Fire Protection Legend & Abbreviation | 0 | 2026-01-12 | 2026-01-12 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
3 | Fire Protection | 523213-01-RFAS-FI-0003 | Fire Protection System Schematic Diagram | 0 |  | 2026-01-19 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
4 | Fire Protection | 523213-01-RFAS-FI-0004 | Schematic Diagram For Fire Pump | 0 |  | 2026-01-19 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
5 | Fire Protection | 523213-01-RFAS-FI-0005 | Nitrogen Suppression Schematic Diagram | [6 empty] | 0 | #N/A | 0 |  | GC | NO
6 | Fire Protection | 523213-01-RFAS-FI-0006 | Nitrogen Suppression Flow Chart Diagram | [6 empty] | 0 | #N/A | 0 |  | GC | NO
7 | Fire Protection | 523213-01-RFAS-FI-0007 | Table For Nitrogen Gas Suppression | 0 |  | 2026-01-26 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
8 | Fire Protection | 523213-01-RFAS-FI-0008 | Pre-Action System Diagram | 0 |  | 2026-01-26 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
9 | Fire Protection | 523213-01-RFAS-FI-0009 | Equipment Schedule | 0 |  | 2026-01-19 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
10 | Fire Protection | 523213-01-RFAS-FI-0010 | Electrical Single Line Diagram | 0 |  | 2026-01-19 | 2026-02-04 |  |  | AUR | 9 | Pending | Overdue | GC | NO
11 | Fire Protection | 523213-01-RFAS-FI-0011 | Fire Protection Matrix For Level 1 | 0 |  | 2026-02-11 |  |  |  | CTA | 2 | Pending |  | GC | NO
12 | Fire Protection | 523213-01-RFAS-FI-0012 | Fire Protection Matrix For Level 2 | 0 |  | 2026-02-11 |  |  |  | CTA | 2 | Pending |  | GC | NO
13 | Fire Protection | 523213-01-RFAS-FI-0013 | Fire Protection Matrix For Level 6 | 0 |  | 2026-02-11 |  |  |  | CTA | 2 | Pending |  | GC | NO
14 | Fire Protection | 523213-01-RFAS-FI-0014 | Fire Protection Matrix For Level Roof | 0 |  | 2026-02-11 |  |  |  | CTA | 2 | Pending |  | GC | NO
15 | Fire Protection | 523213-01-RFAS-FI-0015 | Level 1 - Fire Sprinkler System Layout Plan | [6 empty] | CTA | #N/A | 0 |  | GC | NO
16 | Fire Protection | 523213-01-RFAS-FI-0016 | Level 2 - Fire Sprinkler System Layout Plan | [6 empty] | CTA | #N/A | 0 |  | GC | NO
17 | Fire Protection | 523213-01-RFAS-FI-0017 | Level 6 - Fire Sprinkler System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
18 | Fire Protection | 523213-01-RFAS-FI-0018 | Level Roof - Fire Sprinkler System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
19 | Fire Protection | 523213-01-RFAS-FI-0019 | Level 1 - Nitrogen Fire Suppression Ststem Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
20 | Fire Protection | 523213-01-RFAS-FI-0020 | Level 1 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
21 | Fire Protection | 523213-01-RFAS-FI-0021 | Level 2 - Nitrogen Fire Suppression Ststem Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
22 | Fire Protection | 523213-01-RFAS-FI-0022 | Level 2 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
23 | Fire Protection | 523213-01-RFAS-FI-0023 | Level 6 - Nitrogen Fire Suppression Ststem Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
24 | Fire Protection | 523213-01-RFAS-FI-0024 | Level 6 - Nitrogen Fire Suppression Ststem Wiring Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
25 | Fire Protection | 523213-01-RFAS-FI-0025 | Level 1 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
26 | Fire Protection | 523213-01-RFAS-FI-0026 | Level 2 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
27 | Fire Protection | 523213-01-RFAS-FI-0027 | Level 6 - Fire Hose Cabinet And Fire Extinguisher Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
28 | Fire Protection | 523213-01-RFAS-FI-0028 | Level Roof - Fire Hose Cabinet And Fire Extinguisher Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
29 | Fire Protection | 523213-01-RFAS-FI-0029 | Pump Room Detail Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
30 | Fire Protection | 523213-01-RFAS-FI-0030 | Pump Room Detail Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
31 | Fire Protection | 523213-01-RFAS-FI-0031 | Fire Service Room Detail Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
32 | Fire Protection | 523213-01-RFAS-FI-0032 | Fire Service Room Detail Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
33 | Fire Protection | 523213-01-RFAS-FI-0033 | Fire Service Room Detail Sheet 3 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
34 | Fire Protection | 523213-01-RFAS-FI-0034 | Fire Scope Demarcation | [6 empty] | 0 | #N/A | 0 |  | GC | NO
35 | Fire Protection | 523213-01-RFAS-FI-0035 | Typical Details Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
36 | Fire Protection | 523213-01-RFAS-FI-0036 | Typical Details Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
37 | Fire Protection | 523213-01-RFAS-FI-0037 | Typical Details Sheet 3 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
38 | Fire Protection | 523213-01-RFAS-FI-0038 | Typical Details Sheet 4 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
39 | Fire Protection | 523213-01-RFAS-FI-0039 | Typical Details Sheet 5 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
40 | Fire Protection | 523213-01-RFAS-FI-0040 | Typical Details Sheet 6 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
41 | Fire Protection | 523213-01-RFAS-FI-0041 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
42 | Fire Protection | 523213-01-RFAS-FI-0042 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
43 | Fire Protection | 523213-01-RFAS-FI-0043 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
44 | Fire Protection | 523213-01-RFAS-FI-0044 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
45 | Fire Protection | 523213-01-RFAS-FI-0045 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
46 | Fire Protection | 523213-01-RFAS-FI-0046 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
47 | Fire Protection | 523213-01-RFAS-FI-0047 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
48 | Fire Protection | 523213-01-RFAS-FI-0048 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
49 | Fire Protection | 523213-01-RFAS-FI-0049 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
50 | Fire Protection | 523213-01-RFAS-FI-0050 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
51 | Fire Protection | 523213-01-RFAS-FI-0051 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
52 | Fire Protection | 523213-01-RFAS-FI-0052 | #N/A | #N/A |  | #N/A |  |  |  | #REF! | #N/A | #N/A | #N/A | 0
53 | Fire Protection |  |  |  |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
54 | Fire Protection |  |  |  |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
55 | Fire Protection |  |  |  |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
HYDRAULIC |  |  |  |  | *Put only this
1 | Hydraulics | 523213-01-RFAS-HY-0001 | Hydraulic Drawing Index | [6 empty] | 0 | #N/A | 0 |  | GC | NO
2 | Hydraulics | 523213-01-RFAS-HY-0002 | Hydraulic Legend & Abbreviation | 0 | 2026-01-12 | 2026-01-12 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
3 | Hydraulics | 523213-01-RFAS-HY-0003 | Make Up Water Schematic Diagram | 0 |  | 2026-01-13 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | YES
4 | Hydraulics | 523213-01-RFAS-HY-0004 | Domestic Water Schematic Diagram | 0 | 2026-01-12 | 2026-01-12 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
5 | Hydraulics | 523213-01-RFAS-HY-0005 | Waste water System Schematic Diagram | 0 | 2026-01-12 | 2026-01-12 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | YES
6 | Hydraulics | 523213-01-RFAS-HY-0006 | Storm Water Drainage Schematic Diagram | 0 | 2026-01-12 | 2026-01-12 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
7 | Hydraulics | 523213-01-RFAS-HY-0007 | Fuel Supply Schematic Diagram | 0 |  | 2026-01-13 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | YES
8 | Hydraulics | 523213-01-RFAS-HY-0008 | Equipment Schedule | 0 |  | 2026-01-13 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | YES
9 | Hydraulics | 523213-01-RFAS-HY-0009 | Electrical Single Line Diagram | 0 |  | 2026-01-14 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
10 | Hydraulics | 523213-01-RFAS-HY-0010 | Site Plan - Water Supply System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
11 | Hydraulics | 523213-01-RFAS-HY-0011 | Level 1 - Water Supply System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
12 | Hydraulics | 523213-01-RFAS-HY-0012 | Level 2 - Water Supply System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
13 | Hydraulics | 523213-01-RFAS-HY-0013 | Level 6 - Water Supply System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
14 | Hydraulics | 523213-01-RFAS-HY-0014 | Level Roof - Water Supply System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
15 | Hydraulics | 523213-01-RFAS-HY-0015 | Site Plan - Wastewater And Stromwater System Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
16 | Hydraulics | 523213-01-RFAS-HY-0016 | Level 1 - Wastewater And Stormwater System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
17 | Hydraulics | 523213-01-RFAS-HY-0017 | Level 2 - Wastewater And Stormwater System Layout | [6 empty] | 0 | #N/A | 0 |  | TTI | NO
18 | Hydraulics | 523213-01-RFAS-HY-0018 | Level 6 - Wastewater And Stormwater System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
19 | Hydraulics | 523213-01-RFAS-HY-0019 | Level Roof - Wastewater And Stormwater System Layout | [6 empty] | 0 | #N/A | 0 |  | GC | NO
20 | Hydraulics | 523213-01-RFAS-HY-0020 | Pump Room Details - Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
21 | Hydraulics | 523213-01-RFAS-HY-0021 | Pump Room Details - Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
22 | Hydraulics | 523213-01-RFAS-HY-0022 | Pump Room Details - Sheet 3 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
23 | Hydraulics | 523213-01-RFAS-HY-0023 | Fuel Pump Room Details - Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
24 | Hydraulics | 523213-01-RFAS-HY-0024 | Fuel Pump Room Details - Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
25 | Hydraulics | 523213-01-RFAS-HY-0025 | Softener Detail | [6 empty] | 0 | #N/A | 0 |  | GC | NO
26 | Hydraulics | 523213-01-RFAS-HY-0026 | Pump Room & Water Tank - Level 6 Detail | [6 empty] | 0 | #N/A | 0 |  | GC | NO
27 | Hydraulics | 523213-01-RFAS-HY-0027 | Level 2 - Toilet Details | [6 empty] | 0 | #N/A | 0 |  | GC | NO
28 | Hydraulics | 523213-01-RFAS-HY-0028 | Scope Demarcation - Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
29 | Hydraulics | 523213-01-RFAS-HY-0029 | Scope Demarcation - Sheet 2 | [6 empty] | 0 | #N/A | 0 |  | GC | NO
30 | Hydraulics | 523213-01-RFAS-HY-0030 | Typical Details Sheet 1 | 0 |  | 2026-01-30 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
31 | Hydraulics | 523213-01-RFAS-HY-0031 | Typical Details Sheet 2 | 0 |  | 2026-01-30 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
32 | Hydraulics | 523213-01-RFAS-HY-0032 | Typical Details Sheet 3 | 0 |  | 2026-01-30 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
33 | Hydraulics | 523213-01-RFAS-HY-0033 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
34 | Hydraulics | 523213-01-RFAS-HY-0034 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
35 | Hydraulics | 523213-01-RFAS-HY-0035 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
36 | Hydraulics | 523213-01-RFAS-HY-0036 | #N/A | #N/A |  | #N/A |  |  |  | 0 | #N/A | #N/A | #N/A | 0
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
MECHANICAL |  |  |  |  | *Put only this
1 | Mechanical | 523213-01-RFAS-ME-0001 | Mechanical Drawing Index | [6 empty] | 0 | #N/A | 0 |  | GC | NO
2 | Mechanical | 523213-01-RFAS-ME-0002 | Mechanical Legend & Abbreviation | 0 | 2026-01-12 | 2026-01-12 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
3 | Mechanical | 523213-01-RFAS-ME-0003 | ACMV Air Side Schematic | 0 |  | 2026-02-09 | 2026-02-12 |  |  | AUR | 1 | Pending |  | GC | YES
4 | Mechanical | 523213-01-RFAS-ME-0004 | Stair And Fireman Lift Lobby Pressurization Schematic | 0 |  | 2026-01-19 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | YES
5 | Mechanical | 523213-01-RFAS-ME-0005 | ACMV Piping System Schematic - Risers - Sheet 1 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
6 | Mechanical | 523213-01-RFAS-ME-0006 | ACMV Piping System Schematic - Chiller Plant | [6 empty] | 0 | #N/A | 0 |  | GC | YES
7 | Mechanical | 523213-01-RFAS-ME-0007 | Equipment Schedule | [6 empty] | 0 | #N/A | 0 |  | GC | YES
8 | Mechanical | 523213-01-RFAS-ME-0008 | Level 1 - Ducting Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
9 | Mechanical | 523213-01-RFAS-ME-0009 | Level 2 - Ducting Layout Plan | 0 |  | 2026-02-09 | 2026-02-12 |  |  | GAA | #N/A | C |  | GC | NO
10 | Mechanical | 523213-01-RFAS-ME-0010 | Level 6 - Ducting Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
11 | Mechanical | 523213-01-RFAS-ME-0011 | Level Roof - Ducting Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
12 | Mechanical | 523213-01-RFAS-ME-0012 | Level 1 - ACMV Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
13 | Mechanical | 523213-01-RFAS-ME-0013 | Level 1 - Condensate Drain PIpe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
14 | Mechanical | 523213-01-RFAS-ME-0014 | Level 2 - ACMV Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
15 | Mechanical | 523213-01-RFAS-ME-0015 | Level 2 - Condensate Drain Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
16 | Mechanical | 523213-01-RFAS-ME-0016 | Level 2 - Liquid Cooling Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
17 | Mechanical | 523213-01-RFAS-ME-0017 | Level 6 - ACMV Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
18 | Mechanical | 523213-01-RFAS-ME-0018 | Level 6 - Condensate Drain Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
19 | Mechanical | 523213-01-RFAS-ME-0019 | Level 6 - Liquid Cooling Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
20 | Mechanical | 523213-01-RFAS-ME-0020 | Level Roof - ACMV Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
21 | Mechanical | 523213-01-RFAS-ME-0021 | Level Roof - Liquid Cooling Pipe Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
22 | Mechanical | 523213-01-RFAS-ME-0022 | Level 1 - Gas Leak Detection Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
23 | Mechanical | 523213-01-RFAS-ME-0023 | Level 1 - Water And Fuel Leak Detection Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
24 | Mechanical | 523213-01-RFAS-ME-0024 | Level 1 - Space Temperature And Humidity Sensor Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
25 | Mechanical | 523213-01-RFAS-ME-0025 | Level 2 - Gas Leak Detection Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
26 | Mechanical | 523213-01-RFAS-ME-0026 | Level 2 - Water And Fuel Leak Detection Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
27 | Mechanical | 523213-01-RFAS-ME-0027 | Level 2 - Space Temperature And Humidity Sensor Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | YES
28 | Mechanical | 523213-01-RFAS-ME-0028 | Level 2 - Fan Wall Sensor Layout And Details | [6 empty] | 0 | #N/A | 0 |  | GC | YES
29 | Mechanical | 523213-01-RFAS-ME-0029 | Level 6 - Fuel Leak Detection Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
30 | Mechanical | 523213-01-RFAS-ME-0030 | Level 1 - Cms Cable Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
31 | Mechanical | 523213-01-RFAS-ME-0031 | Level 2 - Cms Cable Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
32 | Mechanical | 523213-01-RFAS-ME-0032 | Level 6 - Cms Cable Routing Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
33 | Mechanical | 523213-01-RFAS-ME-0033 | Typical Detail | 0 |  | 2026-01-26 | 2026-02-02 |  |  | AUR | 11 | Pending | Overdue | GC | NO
34 | Mechanical | 523213-01-RFAS-ME-0034 | Mechanical Service Electrical Single Line Diagram Sheet-1 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
35 | Mechanical | 523213-01-RFAS-ME-0035 | Mechanical Service Electrical Single Line Diagram Sheet-2 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
36 | Mechanical | 523213-01-RFAS-ME-0036 | Mechanical Service Electrical Single Line Diagram Sheet-3 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
37 | Mechanical | 523213-01-RFAS-ME-0037 | Mechanical Service Electrical Single Line Diagram Sheet-4 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
38 | Mechanical | 523213-01-RFAS-ME-0038 | Mechanical Service Electrical Single Line Diagram Sheet-5 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
39 | Mechanical | 523213-01-RFAS-ME-0039 | Mechanical Service Electrical Single Line Diagram Sheet-6 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
40 | Mechanical | 523213-01-RFAS-ME-0040 | Mechanical Service Electrical Single Line Diagram Sheet-7 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
41 | Mechanical | 523213-01-RFAS-ME-0041 | Mechanical Service Electrical Single Line Diagram Sheet-8 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
42 | Mechanical | 523213-01-RFAS-ME-0042 | Mechanical Service Electrical Single Line Diagram Sheet-9 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
43 | Mechanical | 523213-01-RFAS-ME-0043 | Mechanical Service Electrical Single Line Diagram Sheet-10 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
44 | Mechanical | 523213-01-RFAS-ME-0044 | Mechanical Service Electrical Single Line Diagram Sheet-11 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
45 | Mechanical | 523213-01-RFAS-ME-0045 | Mechanical Service Electrical Single Line Diagram Sheet-12 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
46 | Mechanical | 523213-01-RFAS-ME-0046 | Mechanical Service Electrical Single Line Diagram Sheet-13 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
47 | Mechanical | 523213-01-RFAS-ME-0047 | Mechanical Service Electrical Single Line Diagram Sheet-14 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
48 | Mechanical | 523213-01-RFAS-ME-0048 | Mechanical Service Electrical Single Line Diagram Sheet-15 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
49 | Mechanical | 523213-01-RFAS-ME-0049 | Mechanical Service Electrical Single Line Diagram Sheet-16 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
50 | Mechanical | 523213-01-RFAS-ME-0050 | Mechanical Service Electrical Single Line Diagram Sheet-17 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
51 | Mechanical | 523213-01-RFAS-ME-0051 | Mechanical Service Electrical Single Line Diagram Sheet-18 | [6 empty] | 0 | #N/A | 0 |  | GC | YES
STRUCTURAL
1 | Civil & Structure | 523213-01-RFAS-ST-0001 | Structural Drawing Index | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
2 | Civil & Structure | 523213-01-RFAS-ST-0002 | Level 1 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
3 | Civil & Structure | 523213-01-RFAS-ST-0003 | Level 2 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
4 | Civil & Structure | 523213-01-RFAS-ST-0004 | Level 2 - Ladder Cover Sections & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
5 | Civil & Structure | 523213-01-RFAS-ST-0005 | Level 3 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
6 | Civil & Structure | 523213-01-RFAS-ST-0006 | Level 3 - Ladder Cover Sections & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
7 | Civil & Structure | 523213-01-RFAS-ST-0007 | Level 4 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
8 | Civil & Structure | 523213-01-RFAS-ST-0008 | Level 4 - Ladder Cover Sections & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
9 | Civil & Structure | 523213-01-RFAS-ST-0009 | Level 5 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
10 | Civil & Structure | 523213-01-RFAS-ST-0010 | Level 5 - Ladder Cover Sections & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
11 | Civil & Structure | 523213-01-RFAS-ST-0011 | Level 6 - Concrete Plinth Layout Plan & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
12 | Civil & Structure | 523213-01-RFAS-ST-0012 | Level 1 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
13 | Civil & Structure | 523213-01-RFAS-ST-0013 | Level 2 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
14 | Civil & Structure | 523213-01-RFAS-ST-0014 | Level 3 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
15 | Civil & Structure | 523213-01-RFAS-ST-0015 | Level 4 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
16 | Civil & Structure | 523213-01-RFAS-ST-0016 | Level 5 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
17 | Civil & Structure | 523213-01-RFAS-ST-0017 | Level 6 - Steel Support & Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
18 | Civil & Structure | 523213-01-RFAS-ST-0018 | Roof Deck Cooling Tower Platform Steel Details | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
19 | Civil & Structure | 523213-01-RFAS-ST-0019 | Typical Detail | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
20 | Civil & Structure
CSD (Combine Shop Drawing) |  |  |  |  | *Put only this
1 | Combine Service | 523213-01-RFAS-CSD-0001 | Level 1 - Combine Wall Layout Plan Index | [6 empty] | 0 | #N/A | #N/A | #N/A | GC | NO
2 | Combine Service | 523213-01-RFAS-CSD-0002 | Level 2 - Combine Wall Genset 1-2 | 0 |  | 2026-01-21 |  |  |  | CTA | 23 | Pending | Overdue | GC | NO
3 | Combine Service | 523213-01-RFAS-CSD-0003 | Level 2 - Combine Wall Lv Switch Room A | 0 |  | 2026-01-21 |  |  |  | CTA | 23 | Pending | Overdue | GC | NO
4 | Combine Service | 523213-01-RFAS-CSD-0004 | Level 2 - Combine Wall Lv Switch Room B | 0 |  | 2026-01-21 |  |  |  | CTA | 23 | Pending | Overdue | GC | NO
5 | Combine Service | 523213-01-RFAS-CSD-0005 | Level 2 - Combine Wall Genset 3-4 | 0 |  | 2026-01-21 |  |  |  | CTA | 23 | Pending | Overdue | GC | NO
6 | Combine Service | 523213-01-RFAS-CSD-0006 | Level 2 - Combine Wall Goods Lift Lobby , Stair ST-2 | 0 |  | 2026-01-26 |  |  |  | CTA | 18 | Pending | Overdue | GC | NO
7 | Combine Service | 523213-01-RFAS-CSD-0007 | Level 2 - Combine Wall MDF A , ELV A , Fire Service , Battery A1 | 0 |  | 2026-01-26 |  |  |  | CTA | 18 | Pending | Overdue | GC | NO
8 | Combine Service | 523213-01-RFAS-CSD-0008 | Level 2 - Combine Wall MDF B , ELV B , Battery B1 , Spare Room | 0 |  | 2026-01-28 |  |  |  | CTA | 16 | Pending | Overdue | GC | NO
9 | Combine Service | 523213-01-RFAS-CSD-0009 | Level 2 - Combine Wall Fireman Lift , Toilet , Janitor , Stair 1 | 0 |  | 2026-02-02 |  |  |  | CTA | 11 | Pending | Overdue | GC | NO
10 | Combine Service | 523213-01-RFAS-CSD-0010 | Level 2 - Combine Wall Data Hall A , Fan Wall A | 0 |  | 2026-02-02 |  |  |  | CTA | 11 | Pending | Overdue | GC | NO
11 | Combine Service | 523213-01-RFAS-CSD-0011 | Level 2 - Combine Wall Spare Space , Battery Room A2 & B2 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | NO
12 | Combine Service | 523213-01-RFAS-CSD-0012 | Level 2 - Combine Wall Data Hall C , Fan Wall C | 0 |  | 2026-02-07 |  |  |  | CTA | 6 | Pending | Overdue | GC | NO
13 | Combine Service | 523213-01-RFAS-CSD-0013 | Level 2 - Combine Wall Air Lock 2.1 , Comm Riser C1 , Stair ST-3 | 0 |  | 2026-02-04 |  |  |  | CTA | 9 | Pending | Overdue | GC | NO
14 | Combine Service | 523213-01-RFAS-CSD-0014 | Level 2 - Combine Wall Air Lock 2.2 , Comm Riser C1 , Stair ST-4 | 0 |  | 2026-02-05 |  |  |  | CTA | 8 | Pending | Overdue | GC | 0
15 | Combine Service | 523213-01-RFAS-CSD-0015 | Level 3 - Combine Wall Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
16 | Combine Service | 523213-01-RFAS-CSD-0016 | Level 4 - Combine Wall Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
17 | Combine Service | 523213-01-RFAS-CSD-0017 | Level 5 - Combine Wall Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
18 | Combine Service | 523213-01-RFAS-CSD-0018 | Level 6 - Combine Wall Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
19 | Combine Service | 523213-01-RFAS-CSD-0019 | Level Roof - Combine Wall Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
20 | Combine Service | 523213-01-RFAS-CSD-0020 | Level 1 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
21 | Combine Service | 523213-01-RFAS-CSD-0021 | Level 2 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
22 | Combine Service | 523213-01-RFAS-CSD-0022 | Level 2 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | 0
23 | Combine Service | 523213-01-RFAS-CSD-0023 | Level 4 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
24 | Combine Service | 523213-01-RFAS-CSD-0024 | Level 5 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
25 | Combine Service | 523213-01-RFAS-CSD-0025 | Level 6 - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
26 | Combine Service | 523213-01-RFAS-CSD-0026 | Level Roof - Combine Ceiling Layout Plan | [6 empty] | 0 | #N/A | 0 |  | GC | NO
NO
Formulas:
Actual Submission Date = IF(VLOOKUP([Doc Ref No.],AR!$E4:AC512,3,0)="","",VLOOKUP([Doc Ref No.],AR!$E4:AC512,3,0))
Actual Submission Date = IF(VLOOKUP([Doc Ref No.],EL!$E4:AC514,5,0)="","",VLOOKUP([Doc Ref No.],EL!$E4:AC514,5,0))
Delays Date = IFS(AND([Rev]<>"",[Status]="Pending",[Action By]="CTA"),TODAY()-[Actual Submission Date],AND([Rev]<>"",[Status]="Pending",[Action By]="AUR"),TODAY()-[Approval Date],AND([Rev]<>"",[Status]="Pending",[Action By]="STT"),TODAY()-[AUR],OR([Action By]="Closed",[Action By]=""),"")
Action By = VLOOKUP([Doc Ref No.],ME!$E4:J1009,6,0)